## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 09/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-09
Name of the builder group |  |  |  |  | M/s.Akshar Realtors
Name of the builder company |  |  |  |  | M/s.Akshar Realtors
Name of the Project |  |  |  |  | One Akshar
Contact Details ( Name & Conact No.) |  |  |  |  | 022-27889991
Site Person - Contact Details (Name & Contact No.) |  |  |  |  | Mr. Akshay 9930185848
Name / No of the Building |  |  |  |  | Building No.1 & Building No.2 (EWS)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC |  |  |  |  | 205.9368 | 850.2807
RERA Name & No. |  |  |  |  | P51700020810 |  |  |  |  | 308.9053 | 1275.421
Project location details |  | One Akshar, Sector.13, Plot No.7, Palm Beach Road, Sanpada, Vashi, Thane. | [7 empty] | 22660.6686 | 33714.3584
Sector |  | 13 |  |  | Plot No |  | 7
Road |  | Palm Beach Road |  |  | Locality/Village |  | Sanpada
City |  | Vashi |  |  | District |  | Thane
Taluka |  | Thane |  |  | Pin Code |  | 400705
Near by Landmark |  | Jyeshta Nagarik Virangula Kendra |  |  | Distance from city centre: |  | 2.6Km from Vashi Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Open Plot |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.060135,73.0018841
Location Link |  | https://goo.gl/maps/Br7qyE4QWUcVGxrr9
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 4902.41
Permissible FSI |  |  |  |  | 3.5
Permissible TDR/Paid FSI |  |  |  |  | 1.5645
Total FSI availaible for the project |  |  |  |  | 5.0645
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 24828.058
Area Statement Details : Building No.2 (EWS)
Total land area of the project in Sq. Mt. |  |  |  |  | 4902.41
Permissible FSI |  |  |  |  | 0.3
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.3
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 1470.723
Total number of Buildings |  |  |  |  | 2 Buildings
Approval Detail : Plan approval
Layout Approval No |  | 2019/CNMMC14789/NRV/A-/1483 |  |  |  | Dated | 12/04/2019.
Approved Floor plan No. |  | 2019/CNMMC14789/NRV/A-/1483 |  |  |  | Dated | 12/04/2019.
Approved Floor plan No. (29th to 32nd Floor) |  | NRV/A/19944 |  |  |  | Dated | 2023-11-10
Commencement Certificate No. |  | 2019/CNMMC14789/NRV/A-/1483/2019 |  |  |  | Dated | 21/04/2019.
Valid Up to: Building No.1(Main Building) = G + 1st to 29th Floor Building No.2 (EWS) = G + 1st to 4th Floor
Commencement Certificate No. |  | NMMC/TPO/BP/19944/2023 |  |  |  | Dated | 2023-11-10
Valid For : Builtup Area = 24828.058sqm (Residential Unit = 73, Commercial Unit = 15 & Showroom = 1 )
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 21/04/2019. |  | Expected Completion |  | As per RERA- 30/12/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  | 9192.018 | Approved no of units |  |  | Blg No.1 - Flats = 54, Shop = 05, Office = 10, Show Room = 01 Blg No.2 (EWS) Flats = 16
Approved no of Floors |  | Building No.1(Main Building) = G + 1st to 32nd Floor Building No.2 (EWS) = G + 1st to 4th Floor
Proposed no of Floors |  | Building No.1(Main Building) = G + 1st to 32nd Floor Building No.2 = G + 1st to 32nd Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Building No.1(Main Building) = G + 1st to 32nd Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 32
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% |  | 100% |  | 100% |  | Excavation in process | 16
Plinth |  | 32 | 100% | [5 empty] | Excavation Completed | 32
RCC (Including podiums) |  | 33 | 100% | [5 empty] | Footing in Process | 8
Brickwork | Brickwork & Internal Plaster | 32 | 100% | [5 empty] | Footing Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 32 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 32 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 32 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 32 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 32 | 100% | [5 empty] | Plinth in process | 24
Possession |  | 32 | 100% | [5 empty] | Plinth completed | 32
Construction details: |  | Building No.2 (EWS) = G + 1st to 32nd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 31 Floor, Internal Plaster upto 28 Floor, External Plaster upto 28 Floor, Flooring upto 15 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 31 Floor, Internal Plaster upto 28 Floor, External Plaster upto 28 Floor, Flooring upto 15 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% |  | 77.27% |  | 90.94% |  | Excavation in process | 16
Plinth |  | 32 | 100% | [5 empty] | Excavation Completed | 32
RCC (Including podiums) |  | 33 | 100% | [5 empty] | Footing in Process | 8
Brickwork | Brickwork & Internal Plaster | 31 | 96.88% | [5 empty] | Footing Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 28 | 87.5% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28 | 87.5% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 46.88% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 24
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 32
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) For Building No.1 | [5 empty] | 22250 |  |  |  | 22222 to 22250 for case 3202 (90% loading) by nilesh & Ganesh Sir
Recommended rate of the flat Per Sq. Ft. (on Saleable area) For Building No.2 (EWS) | [5 empty] | 18000/-
Recommended rate of the Shop & Office Per Sq. Ft. (on Saleable area) | [5 empty] | 35000/-
Recommended rate of the Show Room Per Sq. Ft. (on Saleable area) | [5 empty] | 30000/-
Floor Rise per sq.ft from 6th Floor | [5 empty] | 100/-
Society Formation Charges | [5 empty] | 1,00,000/-
Recommended rate of Parking | [5 empty] | 10,00,000/-
Distressed valuation of the Property | [5 empty] | 17800
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Shop |  | 5 | 2122.5639 |  |  | 3502.2305
Office |  | 10 | 4207.1309 |  |  | 6941.766
Show Room |  | 1 | 2286.1444 |  |  | 3772.1383
Total |  | 16 | 8615.8393 |  |  | 14216.1348
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Building No.1 |  | 54 | 94499.6102 |  |  | 223162.4923
Building No.2 (EWS) |  | 16 | 6255.3479 |  |  | 9070.2545
Total |  | 70 | 100754.9581 |  |  | 232232.7467
Grand Total |  | 86 | 109370.7974 |  |  | 246448.8816
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | Floor
Building No.1
Ground Floor For Parking & Commercial
1 |  | Shop | 497.4798 |  | 0 | 820.8417 | Ground Floor For Parking & Commercial
2 |  | Shop | 441.5931 |  | 0 | 728.6286
3 |  | Shop | 450.1397 |  | 0 | 742.7305
4 |  | Shop | 372.5743 |  | 0 | 614.7476
5 |  | Shop | 360.777 |  | 0 | 595.282
1 |  | Office | 463.7885 |  | 0 | 765.251
2 |  | Office | 342.8657 |  | 0 | 565.7284
3 |  | Office | 342.8657 |  | 0 | 565.7284
4 |  | Office | 430.0433 |  | 0 | 709.5715
5 |  | Office | 429.8819 |  | 0 | 709.3051
6 |  | Office | 429.8819 |  | 0 | 709.3051
7 |  | Office | 430.0433 |  | 0 | 709.5715
8 |  | Office | 387.095 |  | 0 | 638.7067
9 |  | Office | 507.7056 |  | 0 | 837.7142
10 |  | Office | 442.9601 |  | 0 | 730.8842
1st Floor is For Commercial (Part Podium)
1 |  | Show Room | 2286.1444 |  | 0 | 3772.1383 | 1st Floor
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | Floor
2nd Floor is For Podium
3rd & 4th Floor is For Podium
5th Floor is For Ammenities
6th & 12th Floor
1 |  | 6BHK | 1567.0124 |  | 47.6307 | 3800 | 6th & 12th Floor
2 |  | 6BHK | 1567.0124 |  | 47.6307 | 3800
7th & 13th Floor
1 |  | 6BHK | 1374.5628 |  | 247.346 | 3700 | 7th & 13th Floor
2 |  | 6BHK | 1374.5628 |  | 247.346 | 3700
8th & 14th Floor
1 |  | 6BHK | 1354.4341 |  | 47.6307 | 3450 | 8th & 14th Floor
2 |  | 6BHK | 1354.4341 |  | 47.6307 | 3450
9th & 15th Floor
1 |  | 6BHK | 1567.0124 |  | 37.1358 | 3800 | 9th & 15th Floor
2 |  | 6BHK | 1567.0124 |  | 37.1358 | 3800
10th & 16th Floor
1 |  | 6BHK | 1370.3648 |  | 257.8409 | 3700 | 10th & 16th Floor
2 |  | 6BHK | 1370.3648 |  | 257.8409 | 3700
11th & 17th Floor
1 |  | 6BHK | 1354.4341 |  | 37.1358 | 3450 | 11th & 17th Floor
2 |  | 6BHK | 1354.4341 |  | 37.1358 | 3450
Fire check Between 17th & 18th Floor
18th & 24th Floor
1 |  | 6BHK | 2042.1461 |  | 37.1358 | 4930 | 18th & 24th Floor
2 |  | 6BHK | 2042.1461 |  | 37.1358 | 4930
19th, 22nd, 25th & 28th Floor
1 |  | 6BHK | 1659.6366 |  | 383.1769 | 4765 | 19th, 22nd, 25th & 28th Floor
2 |  | 6BHK | 1659.6366 |  | 383.1769 | 4765
20th, 23rd & 26th Floor
1 |  | 6BHK | 1716.1476 |  | 0 | 4100 | 20th, 23rd & 26th Floor |  |  |  | 2.3891
2 |  | 6BHK | 1716.1476 |  | 0 | 4100
21st & 27th Floor
1 |  | 6BHK | 2042.1461 |  | 47.6307 | 4930 | 21st & 27th Floor |  |  |  | 4882.3693
2 |  | 6BHK | 2042.1461 |  | 47.6307 | 4930 |  |  |  |  | 2.3908
29th Floor
1 |  | 4BHK | 2542.1608 |  | 0 | 4067.4573 | 29th Floor |  |  |  | 199.3362 | 2409.2335
2 |  | 4BHK | 2542.1608 |  | 0 | 4067.4573
30th Floor (Part Refuge Area @ Midlanding)
1 |  | 4BHK | 2570.0126 |  | 0 | 4112.0202 | 30th Floor (Part Refuge Area @ Midlanding) |  |  |  | 29th to 32nd floor loading 60%
2 |  | 4BHK | 2570.0126 |  | 0 | 4112.0202
31st Floor
1 |  | 4BHK | 2464.2563 |  | 520.7085 | 4072.9873 | 31st Floor
2 |  | 4BHK | 2464.2563 |  | 520.7085 | 4072.9873
32nd Floor
1 |  | 4BHK | 2542.1608 |  | 0 | 4067.4573 | 32nd Floor
2 |  | 4BHK | 2542.1608 |  | 0 | 4830.1055
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | Floor
Building No.2 (EWS)
Ground Floor For Parking
1st To 4th Floor For Residential
1 |  | 1RK | 408.7306 |  | 0 | 592.6594 | 1st To 4th Floor For Residential
2 |  | 1RK | 373.1879 |  | 0 | 541.1224
3 |  | 1RK | 373.1879 |  | 0 | 541.1224
4 |  | 1RK | 408.7306 |  | 0 | 592.6594
Remarks:
1.Building No.1 - All work completed. Please provide OC. Building No.2 - Construction work is in the process at the time of visit.(Internal photo was not allowed). 2. We considered Saleable area of commercial & 29th to 32nd Floor in Building No. 1 & Building no.2 as per our calculation. We considered Saleable area of Building no.1 Flats as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + F.B Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We mentioned area details of Building No.2 (EWS) in report because it is registered on RERA site. 8. Please provide revised approved Floor plan of Building No.1. 9. We have given construction percentage as per the proposed no of floors. 10. We have updated approved floor plan of 29th to 32nd floor in Building No. 1 & CC (on 02/04/2024). 11. Recommended Rates / Other charges of the Property have been revised on 02/04/2024. 12. Construction work goes beyond approved plan and CC permission for Building No. 2. Please provide revised Approved plans & CC . 8. On Site, we meet Mr.Premji Patel - 9820649838.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Mohite |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | One Akshar
Layout :
Google Map :
Wing B
Wing A
Bldg No. 1
Bldg No. 2
Building 1
Building 1

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 29
Particulars | total floor | 29
plinth | 10 | 10 | 100%
slab | 30 | 4 | 13.33% |  | Parking |  | Rate
Bricks | 29 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 29 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 29 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 29 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 29 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5.3333 | 0 | 0 | 0 | 0 | 0
RCC | 5.3333 | 4 |  | Recommended |  | 30 | 4 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 15.33% | 34% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
Date | Checked By | Description
20/03/2020. | Pratiksha | Given Rate As per Market inquire & ref Mis
2024-04-02 | Sachin | Flat No 3202 loading changed

## 32nd Floor
| Floor No | 3201 & 3202
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.15 | 1.75 | 3.7625 | Deck | 11.1 | 0.75 | 8.325 |  |  | 0
|  | 2.35 | 3.65 | 8.5775 | Deck | 21.55 | 0.75 | 16.1625 |  |  | 0
|  | 6.35 | 1.2 | 7.62 |  |  |  | 0 |  |  | 0
|  | 5.45 | 5.85 | 31.8825 | CB |  |  | 0 |  |  | 0
| kitch | 5.45 | 4.05 | 22.0725 | CB |  |  | 0 |  |  | 0
|  | 3.75 | 2.35 | 8.8125 | FB |  |  | 0 |  |  | 0
|  | 3.2 | 1.3 | 4.16 |  |  |  | 0 |  |  | 0
|  | 2.6 | 0.75 | 1.95 |  |  |  | 0 |  |  | 0
| Bed1 | 4.25 | 4.65 | 19.7625 | CB |  |  | 0 |  |  | 0
|  | 2.4 | 3.35 | 8.04 | FB |  |  | 0 |  |  | 0
|  | 1.65 | 3.05 | 5.0325 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.95 | 4.55 | 17.9725 | CB |  |  | 0 |  |  | 0
|  | 1.5 | 3.05 | 4.575 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 | 4.25 | 5.85 | 24.8625 | CB |  |  | 0 |  |  | 0
|  | 1.2 | 1.2 | 1.44 | FB |  |  | 0 |  |  | 0
|  | 3.05 | 1.5 | 4.575 |  |  |  | 0 |  |  | 0
| Bed4 | 3.95 | 3.95 | 15.6025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.65 | 1.5 | 3.975 | DB |  |  | 0 |  |  | 0
| toilet3 | 1.5 | 1.8 | 2.7 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 5.65 | 1.2 | 6.78 |  |  |  | 0 |  |  | 0
| Service quarter | 2.6 | 1.95 | 5.07 |  |  |  | 0 |  |  | 0
| passage3 | 2.05 | 1.2 | 2.46 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 2278.5773 | 211.685 |  |  | 263.5834 | 24.4875 |  | 0 | 0
|  |  | 2542.1608 | 236.1725

## 31st Floor
| Floor No | 3101 & 3102
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.15 | 1.75 | 3.7625 | Balcony | 11.5 | 1.5 | 17.25 | 21.5 | 2.25 | 48.375
|  | 2.35 | 3.65 | 8.5775 |  |  |  | 0 |  |  | 0
|  | 6.35 | 1.2 | 7.62 |  |  |  | 0 |  |  | 0
|  | 5.45 | 5.85 | 31.8825 | CB |  |  | 0 |  |  | 0
| kitch | 5.45 | 4.05 | 22.0725 | CB |  |  | 0 |  |  | 0
|  | 3.75 | 2.35 | 8.8125 | FB |  |  | 0 |  |  | 0
|  | 3.2 | 1.3 | 4.16 |  |  |  | 0 |  |  | 0
|  | 2.6 | 0.75 | 1.95 |  |  |  | 0 |  |  | 0
| Bed1 | 4.25 | 4.65 | 19.7625 | CB |  |  | 0 |  |  | 0
|  | 2.4 | 3.35 | 8.04 | FB |  |  | 0 |  |  | 0
|  | 1.65 | 3.05 | 5.0325 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.95 | 4.55 | 17.9725 | CB |  |  | 0 |  |  | 0
|  | 1.5 | 3.05 | 4.575 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 | 4.25 | 5.85 | 24.8625 | CB |  |  | 0 |  |  | 0
|  | 1.2 | 1.2 | 1.44 | FB |  |  | 0 |  |  | 0
|  | 3.05 | 1.5 | 4.575 |  |  |  | 0 |  |  | 0
| Bed4 | 3.95 | 3.95 | 15.6025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.65 | 1.5 | 3.975 | DB |  |  | 0 |  |  | 0
| toilet3 | 1.5 | 1.8 | 2.7 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 5.65 | 1.2 | 6.78 |  |  |  | 0 |  |  | 0
| Service quarter | 2.6 | 1.95 | 5.07 |  |  |  | 0 |  |  | 0
| passage3 | 2.05 | 1.2 | 2.46 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 2278.5773 | 211.685 |  |  | 185.679 | 17.25 |  | 520.7085 | 48.375
|  |  | 2464.2563 | 228.935

## 30th Floor
| Floor No | 3001 & 3002
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.15 | 1.75 | 3.7625 | Deck | 3.1 | 0.75 | 2.325 |  |  | 0
|  | 2.35 | 3.65 | 8.5775 | Deck | 5.5 | 0.75 | 4.125 |  |  | 0
|  | 6.35 | 1.2 | 7.62 | Bal | 2.9 | 1.5 | 4.35 |  |  | 0
|  | 5.45 | 5.85 | 31.8825 | Bal | 21.7 | 0.75 | 16.275 |  |  | 0
| kitch | 5.45 | 4.05 | 22.0725 | CB |  |  | 0 |  |  | 0
|  | 3.75 | 2.35 | 8.8125 | FB |  |  | 0 |  |  | 0
|  | 3.2 | 1.3 | 4.16 |  |  |  | 0 |  |  | 0
|  | 2.6 | 0.75 | 1.95 |  |  |  | 0 |  |  | 0
| Bed1 | 4.25 | 4.65 | 19.7625 | CB |  |  | 0 |  |  | 0
|  | 2.4 | 3.35 | 8.04 | FB |  |  | 0 |  |  | 0
|  | 1.65 | 3.05 | 5.0325 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.95 | 4.55 | 17.9725 | CB |  |  | 0 |  |  | 0
|  | 1.5 | 3.05 | 4.575 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 | 4.25 | 5.85 | 24.8625 | CB |  |  | 0 |  |  | 0
|  | 1.2 | 1.2 | 1.44 | FB |  |  | 0 |  |  | 0
|  | 3.05 | 1.5 | 4.575 |  |  |  | 0 |  |  | 0
| Bed4 | 3.95 | 3.95 | 15.6025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.65 | 1.5 | 3.975 | DB |  |  | 0 |  |  | 0
| toilet3 | 1.5 | 1.8 | 2.7 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 5.65 | 1.2 | 6.78 |  |  |  | 0 |  |  | 0
| Service quarter | 2.6 | 1.95 | 5.07 |  |  |  | 0 |  |  | 0
| passage3 | 2.05 | 1.2 | 2.46 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 2278.5773 | 211.685 |  |  | 291.4353 | 27.075 |  | 0 | 0
|  |  | 2570.0126 | 238.76

## 29th Floor
| Floor No | 2901 & 2902
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.15 | 1.75 | 3.7625 | Deck | 11.1 | 0.75 | 8.325 |  |  | 0
|  | 2.35 | 3.65 | 8.5775 | Deck | 21.55 | 0.75 | 16.1625 |  |  | 0
|  | 6.35 | 1.2 | 7.62 |  |  |  | 0 |  |  | 0
|  | 5.45 | 5.85 | 31.8825 | CB |  |  | 0 |  |  | 0
| kitch | 5.45 | 4.05 | 22.0725 | CB |  |  | 0 |  |  | 0
|  | 3.75 | 2.35 | 8.8125 | FB |  |  | 0 |  |  | 0
|  | 3.2 | 1.3 | 4.16 |  |  |  | 0 |  |  | 0
|  | 2.6 | 0.75 | 1.95 |  |  |  | 0 |  |  | 0
| Bed1 | 4.25 | 4.65 | 19.7625 | CB |  |  | 0 |  |  | 0
|  | 2.4 | 3.35 | 8.04 | FB |  |  | 0 |  |  | 0
|  | 1.65 | 3.05 | 5.0325 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.95 | 4.55 | 17.9725 | CB |  |  | 0 |  |  | 0
|  | 1.5 | 3.05 | 4.575 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 | 4.25 | 5.85 | 24.8625 | CB |  |  | 0 |  |  | 0
|  | 1.2 | 1.2 | 1.44 | FB |  |  | 0 |  |  | 0
|  | 3.05 | 1.5 | 4.575 |  |  |  | 0 |  |  | 0
| Bed4 | 3.95 | 3.95 | 15.6025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.65 | 1.5 | 3.975 | DB |  |  | 0 |  |  | 0
| toilet3 | 1.5 | 1.8 | 2.7 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 5.65 | 1.2 | 6.78 |  |  |  | 0 |  |  | 0
| Service quarter | 2.6 | 1.95 | 5.07 |  |  |  | 0 |  |  | 0
| passage3 | 2.05 | 1.2 | 2.46 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 2278.5773 | 211.685 |  |  | 263.5834 | 24.4875 |  | 0 | 0
|  |  | 2542.1608 | 236.1725