## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | Anukarati Homes Pvt Ltd
Name of the builder company |  |  |  | Anukarati Homes Pvt Ltd | [5 empty] | Previous builder | Ajan Homes Private Limited
Name of the Project (As per Builder) |  |  |  | Dadasaheb Phalke | [5 empty] | Present Builder | Anukarati Homes Pvt Ltd
Present Name of the Project (As per Rera) |  |  |  | Chitrapatjanak Dadasaheb Phalke Township - Phase 1
Previous Name of the Project (As per Rera) |  |  |  | Construction Work of 10080 EWS under PMAY Scheme, 522 EWS Houses and 24 Commercial Shops of Sector 1
Provided Contact Details ( Name & Contact No.) |  |  |  | 8691025107
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr.Aakash Gaikwad 7030081234
Name / No of the Building |  |  |  | Building A Building B (Wing B1 & B2) Building C
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plan, Cost Sheet, Fire Noc
RERA No. |  |  |  | P52000047538
Project location details |  | Dadasaheb Phalke, Survey No.103/2, 104/1, 104/2 & 105/1/B, near Namarata Acharya School, Neral - Badlapur Road, Shelu, Shelu, Shelu West, Karjat, Raigad - 410101.
Survey No |  | 103/2, 104/1, 104/2 & 105/1/B
Locality |  | Shelu
Road |  | Neral - Badlapur Road |  | Locality/Village |  | Shelu
City |  | Shelu West |  | District |  | Raigad
Taluka |  | Karjat |  | Pin Code |  | 410101
Nearby Landmark |  | Namarata Acharya School |  | Distance from city centre: |  | 0.9 KM from Shelu Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 15.80 Wide Neral Badlapur Road |  |  | Neral - Badlapur Road
West | NA | Other Plot |  |  | Open Land
North | NA | Other Plot |  |  | Namarata Acharya School
South | NA | 15.0 M. Wide Internal Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.060461,73.312948
Location Link |  | https://goo.gl/maps/uvsiYMSjHqNT5veUA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 16815.67
Permissible FSI |  |  |  | 2.1
Permissible TDR/Paid FSI |  |  |  | 0.012355
Total FSI availaible for the project |  |  |  | 2.1124
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 35520.66
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | EE/BP/PMAYA/A/MHADA/14/2025 |  |  | Dated | 2025-01-07
Approved Floor plan No. |  | EE/BP/PMAYA/A/MHADA/14/2025 |  |  | Dated | 2025-01-07
Approved Floor plan No. (Building C) |  | EE/BP/PMAYA/A/MHADA/14/2025 |  |  | Dated | 2025-01-07
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/944/2023 |  |  | Dated | 2023-12-07
Building A = G + 1st to 16th Floor Building B (B1 & B2 Wing) = G + 1st to 16th Floor
Commencement-CC No Valid Up to: (Building C) |  | EE/BP/PMAY/A/MHADA/149/2024 |  |  | Dated | 2024-02-22
This C C is issued for work upto plinth level only and the work shall be started w.e.f 22 FEB 2024
Fire Noc No Valid Up to: |  | MFS/51/2022/419 |  |  | Dated | 2022-05-19
Building A = G + 1st to 16th Floor (Height = 49.60 Mtrs) Building B (B1 & B2 Wing) = G + 1st to 16th Floor (Height = 49.90 Mtrs) Building C = Gr + 1st to 16th Floor (Height = 49.60 Mtrs)
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/MIS/233663/2021 |  |  | Dated | 2022-06-18
|  | Survey No. 100/1A Building A = G + 1st to 16th Floor (Height = 49.60 Mtrs) Wing B1 & B2 = G + 1st to 16th Floor (Height = 49.90 Mtrs) Building C = Gr + 1st to 16th Floor (Height = 49.60 Mtrs) | [5 empty] | Wing B1 & B2
O. Certificate No.: |  | EE/BP/PMAY/A/MHADA/68/2025 Approved upto : Bldg No.A & B1 = Gr/St + 1st to 16th Floor 396 EWS tenements & 12 Conv. Shops |  |  | Dated | 2025-03-04
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 35520.66
Approved no of units |  |  | Flats - 792, Shops - 24
Approved no of Floors |  |  | Building A = Gr + 1st to 16th Floor Building B (Wing B1 & B2) = Gr + 1st to 16th Floor Building C = Gr + 1st to 16th Floor
Proposed no of Floors |  |  | Building A = Gr + 1st to 16th Floor
Building B (Wing B1 & B2) = Gr + 1st to 16th Floor
|  |  | Building C = Gr + 1st to 16th Floor |  |  |  |  | https://cdptownship.com/
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | KONE Lifts, Club House, Multipurpose Hall, Fire Fighting Facility, Power Backup (Lift & Common Areas), Convenience Store, Children's Play Area, Landscape Garden etc. |  |  |  |  | All work Completed. Possession granted to the Building.
Violations Observed if any : |  |  | NA |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc |  |  |  |  | Completed |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | Piling Work in process | 4
Construction details: |  | Building A = Gr + 1st to 16th Floor | [5 empty] | Excavation in process | 8
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation Completed | 16
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Footing in Process | 4
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing Completed | 8
Excavation |  | 16 | 100% | 100% |  | 100% |  | Basement 1 | 0
Plinth |  | 16 | 100% |  |  |  |  | Basement 2 | 0
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Basement 3 | 0
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 4 | 0
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Plinth in process | 12
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% |  |  |  |  | Plinth completed | 16
Flooring & Fitting | Flooring & Fitting | 16 | 100% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 15 Floor, Painting upto 15 Floor, Finishing upto 11 Floor Completed | , Flooring upto 15 Floor, Painting upto 15 Floor, Finishing upto 11 Floor
Painting & Wooden |  | 16 | 100% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Building Common Amenities | Building Common Amenities | 16 | 100% |  |  |  |  | Completed | Completed
Possession |  | 16 | 100% |  |  |  |  | Piling Work in process | 4
Construction details: |  | Building B (Wing B1) = Gr + 1st to 16th Floor | [5 empty] | Excavation in process | 8
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation Completed | 16
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 15 Floor, Painting upto 15 Floor, Finishing upto 11 Floor Completed | [5 empty] | Footing in Process | 4
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing Completed | 8
Excavation |  | 16 | 100% | 92.5% |  | 94.69% |  | Basement 1 | 0
Plinth |  | 16 | 100% |  |  |  |  | Basement 2 | 0
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Basement 3 | 0
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 4 | 0
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Plinth in process | 12
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% |  |  |  |  | Plinth completed | 16
Flooring & Fitting | Flooring & Fitting | 15 | 93.75% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 14 Floor, External Plaster upto 14 Floor, Flooring upto 7 Floor, Painting upto 7 Floor Completed | , Internal Plaster upto 14 Floor, External Plaster upto 14 Floor, Flooring upto 7 Floor, Painting upto 7 Floor
Painting & Wooden |  | 15 | 93.75% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork
Building Common Amenities | Building Common Amenities | 11 | 68.75% |  |  |  |  | Completed | Completed
Possession |  | 0 | 0% |  |  |  |  | Piling Work in process | 4
Construction details: |  | Building B (Wing B2) = Gr + 1st to 16th Floor | [5 empty] | Excavation in process | 8
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation Completed | 16
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 14 Floor, External Plaster upto 14 Floor, Flooring upto 7 Floor, Painting upto 7 Floor Completed | [5 empty] | Footing in Process | 4
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing Completed | 8
Excavation |  | 16 | 100% | 79.38% |  | 90.94% |  | Basement 1 | 0
Plinth |  | 16 | 100% |  |  |  |  | Basement 2 | 0
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Basement 3 | 0
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 4 | 0
Internal Plaster | Brickwork & Internal Plaster | 14 | 87.5% |  |  |  |  | Plinth in process | 12
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 87.5% |  |  |  |  | Plinth completed | 16
Flooring & Fitting | Flooring & Fitting | 7 | 43.75% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 12 Floor, External Plaster upto 11.2 Floor Completed | , Internal Plaster upto 12 Floor, External Plaster upto 11.2 Floor
Painting & Wooden |  | 7 | 43.75% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Completed | Completed
Possession |  | 0 | 0% |  |  |  |  | Piling Work in process | 4
Construction details: |  | Building C = Gr + 1st to 16th Floor | [5 empty] | Excavation in process | 8
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation Completed | 16
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 12 Floor, External Plaster upto 11.2 Floor Completed | [5 empty] | Footing in Process | 4
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing Completed | 8
Excavation |  | 16 | 100% | 70.12% |  | 87.25% |  | Basement 1 | 0
Plinth |  | 16 | 100% |  |  |  |  | Basement 2 | 0 |  | 2023-07-14 | Rushikesh
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Basement 3 | 0
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 4 | 0
Internal Plaster | Brickwork & Internal Plaster | 12 | 75% |  |  |  |  | Plinth in process | 12
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11.2 | 70% |  |  |  |  | Plinth completed | 16
Flooring & Fitting | Flooring & Fitting | 0 | 0%
Painting & Wooden |  | 0 | 0%
Building Common Amenities | Building Common Amenities | 0 | 0%
Possession |  | 0 | 0%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3200
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges | [9 empty] | 1L charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges |  |  |  |  | 100000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2560
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building B | Wing B1 | 12 |  | 1692.9404 |  | 2624.0576
| Wing B2 | 12 |  | 1692.9404 |  | 2624.0576
Total |  | 24 |  | 3385.8808 |  | 5248.1152 |  |  | 386793.1648
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building A |  | 267 |  | 85644.8424 |  | 128467.2636
Building B | Wing B1 | 129 |  | 41378.9688 |  | 62305.2612
| Wing B2 | 129 |  | 41378.9688 |  | 62305.2612
Building C |  | 267 |  | 85644.8424 |  | 128467.2636 |  |  | plan on RERA BUT no Numbring & Some not on RERA so AREA NOT DRAFT PLEASE CHECK
Total |  | 792 |  | 254047.6224 |  | 381545.0496
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor |  | 10.764
55%
Building Type EWS
Building B
Wing B1
Ground Floor For Part Commercial, Part Residential, Meter Room & Creche
1 |  | Shop | 138.8717 | 0 | 215.2512 | Ground Floor For Part Commercial, Part Residential, Meter Room & Creche
2 |  | Shop | 161.2985 | 0 | 250.0127
3 |  | Shop | 123.0648 | 0 | 190.7505
4 |  | Shop | 123.0648 | 0 | 190.7505
5 |  | Shop | 161.2985 | 0 | 250.0127
6 |  | Shop | 138.8717 | 0 | 215.2512
7 |  | Shop | 138.8717 | 0 | 215.2512
8 |  | Shop | 161.2985 | 0 | 250.0127
9 |  | Shop | 123.0648 | 0 | 190.7505
10 |  | Shop | 123.0648 | 0 | 190.7505 |  |  | 10.764
11 |  | Shop | 161.2985 | 0 | 250.0127
12 |  | Shop | 138.8717 | 0 | 215.2512
Wing B2
Ground Floor For Part Commercial, Part Residential, Meter Room & Society Office
1 |  | Shop | 138.8717 | 0 | 215.2512 | Ground Floor For Part Commercial, Part Residential, Meter Room & Society Office
2 |  | Shop | 161.2985 | 0 | 250.0127
3 |  | Shop | 123.0648 | 0 | 190.7505
4 |  | Shop | 123.0648 | 0 | 190.7505
5 |  | Shop | 161.2985 | 0 | 250.0127
6 |  | Shop | 138.8717 | 0 | 215.2512
7 |  | Shop | 138.8717 | 0 | 215.2512
8 |  | Shop | 161.2985 | 0 | 250.0127
9 |  | Shop | 123.0648 | 0 | 190.7505
10 |  | Shop | 123.0648 | 0 | 190.7505 |  |  | 10.764
11 |  | Shop | 161.2985 | 0 | 250.0127
12 |  | Shop | 138.8717 | 0 | 215.2512
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 50% |  |  | 28.856
Building Type EWS
Building A
Ground Floor For Residential & Society Office
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | Ground Floor For Residential & Society Office
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
9 |  | 1BHK | 320.7672 | 0 | 481.1508
10 |  | 1BHK | 320.7672 | 0 | 481.1508
11 |  | 1BHK | 320.7672 | 0 | 481.1508 |  |  | 28.896
12 |  | 1BHK | 320.7672 | 0 | 481.1508
13 |  | 1BHK | 320.7672 | 0 | 481.1508
14 |  | 1BHK | 320.7672 | 0 | 481.1508
15 |  | 1BHK | 320.7672 | 0 | 481.1508
16 |  | Society Office
1st to 6th, 8th to 11th, 13th to 16th Floor For Residential
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 1st to 6th, 8th to 11th, 13th to 16th Floor For Residential
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
9 |  | 1BHK | 320.7672 | 0 | 481.1508
10 |  | 1BHK | 320.7672 | 0 | 481.1508
11 |  | 1BHK | 320.7672 | 0 | 481.1508 |  |  | 28.896
12 |  | 1BHK | 320.7672 | 0 | 481.1508
13 |  | 1BHK | 320.7672 | 0 | 481.1508
14 |  | 1BHK | 320.7672 | 0 | 481.1508
15 |  | 1BHK | 320.7672 | 0 | 481.1508
16 |  | 1BHK | 320.7672 | 0 | 481.1508
7th & 12th Floor (Part Refuge Area)
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 7th & 12th Floor (Part Refuge Area)
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
9 |  | 1BHK | 320.7672 | 0 | 481.1508
10 |  | 1BHK | 320.7672 | 0 | 481.1508
11 |  | 1BHK | 320.7672 | 0 | 481.1508
12 |  | 1BHK | 320.7672 | 0 | 481.1508
13 |  | 1BHK | 320.7672 | 0 | 481.1508
14 |  | 1BHK | 320.7672 | 0 | 481.1508
15 |  | Refuge Area
16
Building B
Wing B1
Ground Floor for Part Residential, Part Commercial, Meter room & Creche
1 |  | Commercial Area |  |  |  | Ground Floor for Part Residential, Part Commercial, Meter room & Creche
2
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | Creche
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | Commercial Area
8
1st Floor For Residential
1 |  | 1BHK | 320.7672 | 118.404 | 540.3528 | 1st Floor For Residential
2 |  | 1BHK | 320.7672 | 118.404 | 540.3528
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 118.404 | 540.3528
8 |  | 1BHK | 320.7672 | 118.404 | 540.3528
2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
7th & 12th Floor For Residential (Part Refuge Area)
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 7th & 12th Floor For Residential (Part Refuge Area)
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | Refuge Area
Wing B2
Ground Floor for Part Residential, Part Commercial, Meter room & Society Office
1 |  | Commercial Area |  |  |  | Ground Floor for Part Residential, Part Commercial, Meter room & Society Office
2
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | Society Office
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | Commercial Area
8
1st Floor For Residential
1 |  | 1BHK | 320.7672 | 118.404 | 540.3528 | 1st Floor For Residential
2 |  | 1BHK | 320.7672 | 118.404 | 540.3528
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 118.404 | 540.3528
8 |  | 1BHK | 320.7672 | 118.404 | 540.3528
2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
7th & 12th Floor For Residential (Part Refuge Area)
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 7th & 12th Floor For Residential (Part Refuge Area)
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | Refuge Area
Building C
Ground Floor For Residential, Society Office, Creche & Meter Room
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | Ground Floor For Residential, Society Office, Creche & Meter Room
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508 |  |  | Validity of CC is expired on 29/09/2023. Please provide latest CC.
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
9 |  | 1BHK | 320.7672 | 0 | 481.1508
10 |  | 1BHK | 320.7672 | 0 | 481.1508
11 |  | 1BHK | 320.7672 | 0 | 481.1508
12 |  | 1BHK | 320.7672 | 0 | 481.1508
13 |  | 1BHK | 320.7672 | 0 | 481.1508
14 |  | 1BHK | 320.7672 | 0 | 481.1508
15 |  | 1BHK | 320.7672 | 0 | 481.1508
1st to 6th, 8th to 11th, 13th to 16th Floor For Residential
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 1st to 6th, 8th to 11th, 13th to 16th Floor For Residential
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
9 |  | 1BHK | 320.7672 | 0 | 481.1508
10 |  | 1BHK | 320.7672 | 0 | 481.1508
11 |  | 1BHK | 320.7672 | 0 | 481.1508
12 |  | 1BHK | 320.7672 | 0 | 481.1508
13 |  | 1BHK | 320.7672 | 0 | 481.1508
14 |  | 1BHK | 320.7672 | 0 | 481.1508
15 |  | 1BHK | 320.7672 | 0 | 481.1508
16 |  | 1BHK | 320.7672 | 0 | 481.1508
7th & 12th Floor (Part Refuge Area)
1 |  | 1BHK | 320.7672 | 0 | 481.1508 | 7th & 12th Floor (Part Refuge Area)
2 |  | 1BHK | 320.7672 | 0 | 481.1508
3 |  | 1BHK | 320.7672 | 0 | 481.1508
4 |  | 1BHK | 320.7672 | 0 | 481.1508
5 |  | 1BHK | 320.7672 | 0 | 481.1508
6 |  | 1BHK | 320.7672 | 0 | 481.1508
7 |  | 1BHK | 320.7672 | 0 | 481.1508
8 |  | 1BHK | 320.7672 | 0 | 481.1508
9 |  | 1BHK | 320.7672 | 0 | 481.1508
10 |  | 1BHK | 320.7672 | 0 | 481.1508
11 |  | 1BHK | 320.7672 | 0 | 481.1508
12 |  | 1BHK | 320.7672 | 0 | 481.1508
13 |  | Refuge Area
14
15 |  | 1BHK | 320.7672 | 0 | 481.1508
16 |  | 1BHK | 320.7672 | 0 | 481.1508
Remarks:
1 | Building A = All work Completed. OC Received. Building B (Wing B1) = OC Received but finishing work is in process. Building B (Wing B2) & Building C = Construction work is in process at the time of visit.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We considered Saleable area of Commercial as per Builder area Sheet.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | We have added Building C on 05/12/2024
11 | We have updated approved Fire Noc on 05/12/2024
12 | Construction work of Building C is beyond CC permission, Please check for Revised CC for Building C
13 | We have received EC dtd 18/06/2022 & CC dtd. 09/06/2022 1. Environment Clearance Certificate (EC), consists of survey no. 100/1A. 2. CC consist of Survey no. 100/1A, 103/2, 104/2 & 105/1/B, 3. As per the revised approved Plans dtd. 25/01/2024, consist of survey No. 103/2, 104/1, 104/2, 105/1/B.
14 | With reference to the above remark, Provided EC dtd. 18/06/2022 are amended for FSI-36356.831 m2, Non-FSI-5013.022 m2, and Total BUA-41369.853 m2 (Plan approval-EE/BP/PMAY/A/MHADA/307/2022, dated 09.06.2022), which is mentioned on page no. 05 of 09, SEIAA Condition No. 04. Therefore we have updated EC in our report. Page no. 05 of 09, SEIAA Condition No. 04, attached below. | [6 empty] | As per the telephonic conversation with bank officials sannjay on 28/12/2024.
15 | We have updated revised approved floor plans (On 16/04/2025).
16 | We have updated OC for Building A & Building B1. (On 16/04/2025).
16 | As per approved floor plans dtd. 25/01/2024 & rera, project consists of Sr.No. 103/2, 104/1, 104/2 & 105/1/B. As per revised approved floor plans dtd.07/01/2025 project consists of Sr.No. 100/1A, 103/2, 104/1, 104/2 & 105/1/B.
17 | In Building No.B (Wing B1 & B2), shop numbering is not given. So we considered from left to right.
18 | As per revised approved floor plans dtd.07/01/2025 Survey No. 100/1A is added. We have considered previous survey nos for the project because the Survey No. 100/1A is not mentioned on RERA site. Please check for legal Title from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Dadasaheb Phalke
Remark No. : 14
Layout :
Google Map :
Formulas:
Shelu = [Shelu, row above]
Building - B1
Building - B2
Building A
Building B Wing B2
Wing A
Wing B1
Wing B2
Building A
Building C
Building B (Wing B1)
Building B (Wing B2)
N
N
Chitrapatjanak Dadasaheb Phalke Township - Phase 1
Bldg B1
Bldg B2
Bldg C
Building B Wing B2
Wing A
Wing B1
Wing B2
Bldg A
Bldg B (Wing B1)
Bldg B (Wing B2)
Bldg C
Bldg C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted