## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | M/s.Giriraj Realtors
Name of the builder company |  |  |  | M/s.Giriraj Realtors
Name of the Project |  |  |  | Sarvoday Greens
Contact Details ( Name & Contact No.) |  |  |  | 9923001101
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Vishal 9324480570
Name / No of the Building |  |  |  | Building No.1
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700026551
Project location details |  | Sarvoday Greens, CTS No. 89/2/1, 90/3, 90/4, 110/1, 110/1/2, 110/2, 110/1/6, 110/1/7, 107/1, 107/2, near Amrutvani Complex, Sonale Bhadwad Road, Temghar, Bhiwandi, Bhiwandi, Thane.
CTS No |  | 89/2/1, 90/3, 90/4, 110/1, 110/1/2, 110/2, 110/1/6, 110/1/7, 107/1, 107/2
Road |  | Sonale Bhadwad Road |  | Locality/Village |  | Temghar
City |  | Bhiwandi |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421302
Nearby Landmark |  | Amrutvani Complex |  | Distance from city centre: |  | 4.1 KM from Bhiwandi Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Krishnai wani complex
West | NA | NA |  |  | Open
North | NA | NA |  |  | Amrutvani Complex D Type
South | NA | NA |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.283 |  | Longitude |  | 73.0733
Location Link |  | https://goo.gl/maps/BvCnZGwMpW2CZgwU8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10163.96
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10163.96
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | B.P.No./39/2019-2020/NRV/2506 |  |  | Dated | 20/08/2019.
Approved Floor plan No. |  | B.P.No./39/2019-2020/NRV/2506 |  |  | Dated | 20/08/2019.
Commencement Certificate No. |  | B.P.K/68/2021-2022/J.K.N.R.V/3008 |  |  | Dated | 2021-10-19
Valid Up to: Gr + 1st to 15th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5711.42
Approved no of units |  |  | Flats - 116
Approved no of Floors |  |  | Building No.1 = Gr + 1st to 15th Floor
Proposed no of Floors |  |  | Building No.1 = Gr + 1st to 15th Floor
Expected Completion |  |  | Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Nothing
Construction details: |  | Building No.1 = Gr + 1st to 15th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 100% |  | 100% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 15 | 100% |  |  |  |  | Plinth in process | 11.25
Possession |  | 15 | 100% |  |  |  |  | Plinth completed | 15
Wheather the construction is as per approved Building plan : |  |  |  |  | Yes
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5800
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 2,00,000/-
Distressed valuation of the Property |  |  |  |  | 4640
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 116 |  | 47710.3967 |  | 71565.595
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) |  | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.1 | [11 empty] | B
Ground Floor for Parking
1st to 7th, 9th to 12th, 13th Floor | [9 empty] | ,.., |  | 1st to | 13
101,..,1301 |  | 1BHK | 395.0388 | 0 | 592.5582 | 1st to 7th, 9th to 12th, 13th Floor |  |  |  | 101,..,1301 | 1 | 101 | 1301
102,..,1302 |  | 1BHK | 401.9923 | 0 | 602.9885 |  |  |  |  | 102,..,1302 | 2 | 102 | 1302
103,..,1303 |  | 1BHK | 366.4711 | 0 | 549.7067 |  |  |  |  | 103,..,1303 | 3 | 103 | 1303
104,..,1304 |  | 1BHK | 411.723 | 0 | 617.5845 |  |  |  |  | 104,..,1304 | 4 | 104 | 1304
105,..,1305 |  | 1BHK | 424.1016 | 0 | 636.1524 |  |  | 5706.1798 |  | 105,..,1305 | 5 | 105 | 1305
106,..,1306 |  | 2BHK | 543.7542 | 0 | 815.6313 |  |  | 5762.4073 |  | 106,..,1306 | 6 | 106 | 1306
107,..,1307 |  | 1BHK | 388.0422 | 0 | 582.0633 |  |  |  |  | 107,..,1307 | 7 | 107 | 1307
108,..,1308 |  | 1BHK | 384.2317 | 0 | 576.3476 |  |  |  |  | 108,..,1308 | 8 | 108 | 1308
109,..,1309 |  | 1BHK | 384.2317 | 0 | 576.3476 |  |  |  |  | 109,..,1309 | 9 | 109 | 1309
8th Floor | [11 empty] | 8
801 |  | 1BHK | 395.0388 | 0 | 592.5582 | 8th Floor |  |  |  | 801 | 1 | 801
802 |  | 1BHK | 401.9923 | 0 | 602.9885 |  |  |  |  | 802 | 2 | 802
803 |  | 1BHK | 366.4711 | 0 | 549.7067 |  |  |  |  | 803 | 3 | 803
804 |  | 1BHK | 411.723 | 0 | 617.5845 |  |  |  |  | 804 | 4 | 804
805 |  | 1BHK | 424.1016 | 0 | 636.1524 |  |  |  |  | 805 | 5 | 805
806 |  | 2BHK | 543.7542 | 0 | 815.6313 |  |  |  |  | 806 | 6 | 806
807 |  | 1BHK | 388.0422 | 0 | 582.0633 |  |  |  |  | 807 | 7 | 807
808 |  | Refuge Area | [7 empty] | 808 | 8 | 808
809 |  | 1BHK | 384.2317 | 0 | 576.3476 |  |  |  |  | 809 | 9 | 809
Remarks:
1. All work completed. Please provide OC. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Car parking is subjected to authentic documentation. 8. We have update latest approved C.C taken from RERA site. (on 16/06/2022). 8. On Site, we meet Mr. Chetan - 8291401555 & Jayant Patil : 9892377815.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Mangesh Bapardekar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sarvoday Greens
Google Map :
Bldg No. 1
Bldg No. 1

## C%
Construction details: Building No. = | [6 empty] | Plinth work completed
Ground | 1 |  | Podium | 3 | Floors | 42 | All work Completed. Wait For OC.
Stage of construction: | Plinth work completed | [5 empty] | All work Completed. Provide OC.
Type of Work | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth | 10 | 100% | 10% |  | 30%
RCC Slab | 0 | 0% |  |  |  |  | Excavation in process | 1% | 2%
Brick | 0 | 0% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster | 0 | 0% |  |  |  |  | Footing in Process | 4% | 8%
Flooring | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
|  |  | 10% |  | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted