## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/07/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | B K Groups
Name of the builder company |  |  |  | B K Groups
Name of the Project |  |  |  | Varsha Heights
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Rehan Bardi 9323830693
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rehan Bardi : 9702461430/9324034861/8976923333
Name / No of the Building |  |  |  | Building Type - A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51700050218
Project location details |  | Varsha Heights, Survey No.75, H. No. 1, near Sukh Vastu Building, Internal Road, Jay Malhar Nagar, Devrung, Ambivli West, Bhiwandi, Thane - 421305.
Survey No |  | 75, H. No. 1
Locality |  | Jay Malhar Nagar
Road |  | Internal Road |  | Locality/Village |  | Devrung
City |  | Ambivli West |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421305
Nearby Landmark |  | Sukh Vastu Building |  | Distance from city centre: |  | 6 KM from Ambivli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road / Water Body
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Sukh Vastu Building
South | NA | NA |  |  | Sai Ram Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.276104,73.146538
Location Link |  | https://goo.gl/maps/ntkuiQCBwKkxYk3r7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1901.04
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.3049
Total FSI availaible for the project |  |  |  | 2.4049
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4571.9
Total number of Buildings |  |  |  | 3 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Layout Approval No |  | BS/Rekhankan/BP/Mj.Devrung/Taluka-Bhiwandi/SSTN/2996 |  |  | Dated | 2022-12-21
Approved Floor plan No. |  | BS/Rekhankan/BP/Mj.Devrung/Taluka-Bhiwandi/SSTN/2996 |  |  | Dated | 2022-12-21
Commencement-CC No Valid Up to: |  | BP/Mj.Devrung/Taluka.Bhiwandi/S.N. 75/1/SSTN/2996 |  |  | Dated | 2022-12-21
Building Type A = Gr. + 1st to 5th Floor Building Type B = Gr. + 1st to 5th Floor Building Type C = Gr/Stilt + 1st to 5th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4571.9
Approved no of units |  |  | Flats - 80, Shops - 14
Approved no of Floors |  |  | Building Type A = Gr. + 1st to 5th Floor Building Type B = Gr. + 1st to 5th Floor Building Type C = Gr/Stilt + 1st to 5th Floor
Proposed no of Floors |  |  | Building Type A = Gr. + 1st to 5th Floor
Building Type A = Gr. + 1st to 5th Floor
Building Type B = Gr. + 1st to 5th Floor
Building Type C = Gr/Stilt + 1st to 5th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Badminton Courts, Kids' Play Areas / Sand Pits, Yoga Areas, Jogging / Cycle Track, Normal Park / Central Green, Indoor Games
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building Type A = Gr. + 1st to 5th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 57.5% |  | 80% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 5
Construction details: |  | Building Type B = Gr. + 1st to 5th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 2 Floor Completed | , Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 92% |  | 95% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 40% |  |  |  |  | Plinth in process | 3.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 5
Construction details: |  | Building Type C = Gr/Stilt + 1st to 5th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 10% |  | 45% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 5
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4500 |  |  |  | Visitor 4K
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000 |  |  |  | builder 4k
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Other Charges |  |  |  |  | 15000 |  |  |  | mis 4300
Legal Charges |  |  |  |  | 10000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 150000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3600
Commercial Area Details : Shops
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building Type A |  | 6 |  | 1142.491 |  | 1770.861
Building Type B |  | 8 |  | 979.9546 |  | 1518.9296
Total |  | 14 |  | 2122.4455 |  | 3289.7906
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building Type A |  | 30 |  | 12054.6036 |  | 17479.1752
Building Type B |  | 35 |  | 15904.3482 |  | 23061.3049
Building Type C |  | 15 |  | 6070.3578 |  | 8802.0188
Total |  | 80 |  | 34029.3096 |  | 49342.4989
Grand Total |  | 94 |  | 36151.7551 |  | 52632.2895
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building Type A | [7 empty] | 10.764
Ground Floor For Commercial, Lobby & Parking
1 |  | Shop | 217.8634 | 0 | 337.6882 | Ground Floor For Commercial, Lobby & Parking |  | 18.59
2 |  | Shop | 149.4043 | 0 | 231.5767
3 |  | Shop | 163.0746 | 0 | 252.7656 |  |  | 15.167
4 |  | Shop | 224.1065 | 0 | 347.365
5 |  | Shop | 211.7279 | 0 | 328.1782 |  |  | 18.3425
6 |  | Shop | 176.3143 | 0 | 273.2872
Building Type B
Ground Floor For Commercial, Lobby & Parking
1 |  | Shop | 143.3765 | 0 | 222.2335 | Ground Floor For Commercial, Lobby & Parking |  | 13.255
2 |  | Shop | 93.7544 | 0 | 145.3194 |  |  | 8.6925
3 |  | Shop | 109.4699 | 0 | 169.6783
4 |  | Shop | 143.3765 | 0 | 222.2335
5 |  | Shop | 143.3765 | 0 | 222.2335
6 |  | Shop | 109.4699 | 0 | 169.6783
7 |  | Shop | 93.7544 | 0 | 145.3194
8 |  | Shop | 143.3765 | 0 | 222.2335
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Building Type A
1st, 2nd, 3rd, 4th & 5th Floor For Residential
1 |  | 1BHK | 316.031 | 0 | 458.245 | 1st, 2nd, 3rd, 4th & 5th Floor For Residential |  | 28.5795 |  |  | 1832980.032
2 |  | 1BHK | 398.268 | 0 | 577.4886 |  |  | 36.69 |  |  | 2309954.4
3 |  | 1BHK | 430.2371 | 0 | 623.8438 | [5 empty] | 2495375.064
4 |  | 2BHK | 543.582 | 0 | 788.1939 |  |  | 50.4325 |  |  | 3152775.6
5 |  | 1BHK | 303.0066 | 0 | 439.3596 | [5 empty] | 1757438.28
6 |  | 1BHK | 419.796 | 0 | 608.7042 | [5 empty] | 2434816.8
Building Type B | [10 empty] | 0
1st, 2nd, 3rd, 4th & 5th Floor For Residential | [10 empty] | 0
1 |  | 2BHK | 508.8143 | 0 | 737.7807 | 1st, 2nd, 3rd, 4th & 5th Floor For Residential |  | 47.4625 |  |  | 2951122.824
2 |  | 1BHK | 379.2157 | 0 | 549.8628 |  |  | 35.4915 | 33.9615 |  | 2199451.176
3 |  | 1BHK | 427.3308 | 0 | 619.6297 |  |  | 37.87 | 39.7 | 1.83 | 2478518.64
4 |  | 2BHK | 520.2241 | 0 | 754.325 |  |  |  | 47.8925 |  | 3017299.896
5 |  | 2BHK | 520.2241 | 0 | 754.325 | [5 empty] | 3017299.896
6 |  | 1BHK | 395.3617 | 0 | 573.2745 | [5 empty] | 2293097.976
7 |  | 1BHK | 429.6989 | 0 | 623.0634 |  |  |  | 39.4875 |  | 2492253.504
Building Type C | [10 empty] | 0
Ground Floor For Society Office, Driver Room, Lobby & Parking | [10 empty] | 0
1st, 2nd, 3rd, 4th & 5th Floor For Residential
1 |  | 1BHK | 376.4171 | 0 | 545.8048 | 1st, 2nd, 3rd, 4th & 5th Floor For Residential |  | 33.927
2 |  | 1BHK | 376.4171 | 0 | 545.8048
3 |  | 2BHK | 461.2374 | 0 | 668.7942
Remarks:
* | Wing A = Construction work is in process at the time of Visit. Wing B = Finishing & Cleaning work pending. Tenanat has occupied the flat. Wing C = Construction work increased as compared to last visit. Wing C = Work is same as last visit (08/08/2024).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Varsha Heights
Layout :
Google Map :
Formulas:
Devrung = [Devrung, row above]
Building -A
Building-c
Building -B
A Wing
B Wing
C Wing
A Wing
A Wing
B Wing
C Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted