## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 29/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-11
Name of the builder group |  |  |  | M/s. Regency Nirman Ltd
Name of the builder company |  |  |  | M/s. Regency Nirman Ltd
Name of the Project |  |  |  | Regency Luxuria Phase I & II
Contact Details ( Name & Contact No.) |  |  |  | Mr. Devendra Parab - 9107171060
Contact Details (Site Person Name & Contact No.) |  |  |  | Miss. Arati - 9107171020 |  |  |  | Miss. Gita - 9107171060 & Miss. Manita - 9107171010.
Name / No of the Building |  |  |  | Building No. 3 (Ruby) Building No. 4 (Emerald)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | Phase I - P51700031251 Phase II - P51700053314
Project location details |  | Regency Luxuria Phase I & II, Survey No.54/1, 54/2, 53, 52/16, 60/1C, 59/2(pt), near Goyal Villa, Regency Anantam Rd., Sonarpada, Golavli, Dombivli East, Kalyan, Thane - 421302. | [5 empty] | New S No 52 H No 16(Pt) New S No. 53, New S No 54 H No 1 & 2, New S No 60 H. No 1(pt)/1C, , S No 59 H NO 2B
Survey No |  | 54/1, 54/2, 53, 52/16, 60/1C, 59/2(pt)
Locality |  | Sonarpada
Road |  | Regency Anantam Rd. |  | Locality/Village |  | Golavli
City |  | Dombivli East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421302
Nearby Landmark |  | Goyal Villa |  | Distance from city centre: |  | 3.7 KM from Thakurli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Shree Sai Gajanan CHS LTD
North | NA | NA |  |  | Open Land
South | NA | NA |  |  | Open Land
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.204912,73.115124
Location Link |  | https://goo.gl/maps/BVVZkwS5ytK7PJxP8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 27933.02
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.5925
Total FSI availaible for the project |  |  |  | 4.6925
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 131076.2
Total number of Buildings |  |  |  | 2 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation (KDMC)
Layout Approval No |  | KDMC/TPD/BP/27Village/2020-21/16/198 |  |  | Dated | 2023-09-11
Approved Floor plan No. |  | KDMC/TPD/BP/27Village/2020-21/16/198 |  |  | Dated | 2023-09-11
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/27Village/2020-21/16/198 |  |  | Dated | 2023-09-11
Building No. 3 = G/St + 3P + 1st to 30th Floor (24777.37 sqm) Building No. 4 = G/St + 3P + 1st to 30th Floor (31014.07 sqm)
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 55791.44
Approved no of units |  |  | Flats - 480
Approved no of Floors |  |  | Building No. 3 = G/St + 3P + 1st to 30th Floor Building No. 4 = G/St + 3P + 1st to 30th Floor
Proposed no of Floors |  |  | Building No. 3 = G/St + 3P + 1st to 30th Floor
Building No. 4 = G/St + 3P + 1st to 30th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 3 = G/St + 3P + 1st to 30th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 26 Floor, Flooring upto 16 Floor Completed | , External Plaster upto 26 Floor, Flooring upto 16 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 30 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 26 Floor, Flooring upto 16 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 79% |  | 92% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 34 | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 26 | 86.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 16 | 53.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building No. 4 = G/St + 3P + 1st to 30th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 15 Floor Completed | , Flooring upto 22 Floor, Painting upto 15 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 30 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 15 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 84.83% |  | 93.67% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 34 | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 30 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 73.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 8200 |  |  | 7000 to 7500 | Rushikesh | 2023-03-20 | IGR | This found from old sent mail by sachin 17/08/2023
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate (From 2nd Floor) |  |  |  |  | 30 |  |  | 7500 to 8200 | Bhargav | 2025-08-29 | verbal | Building 4 Flat 402
Infrastructure Charges |  |  |  |  | 120000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges |  |  |  |  | 100000
Recommended rate of Parking |  |  |  |  | 500000
Distressed valuation of the Property |  |  |  |  | 6560
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 3 |  | 240 |  | 202361.0472 |  | 303541.5708 |  |  | visitor | market
Building No. 4 |  | 240 |  | 260451.126 |  | 390676.689 |  |  | visitor | market
Total |  | 480 |  | 462812.1732 |  | 694218.2598 |  |  | visitor | market
Building details Floor Wise | [8 empty] | 8500 | 7000
Details of Flats in Building | [8 empty] | 5630000
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Balcony Area + FB Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No. 3 (Ruby)
Ground Floor for Parking
1st & 2nd Podium Floor for Parking
3rd Podium (Eco Deck) Floor for Parking
1st to 3rd, 5th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor for Residential
1 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414 | 60.073
2 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414
3 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
4 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
5 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
6 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
7 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414
8 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414
4th, 8th, 13th, 18th, 23rd & 28th Floor ( Part Refuge Area @ Midlanding)
1 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414 | 60.073
2 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414
3 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
4 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
5 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
6 |  | 2BHK | 719.8963 | 128.8182 | 848.7145 | 0 | 1273.0717
7 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414
8 |  | 2BHK | 708.8094 | 128.8182 | 837.6276 | 0 | 1256.4414
Building No. 4 (Emerald)
Ground Floor for Parking
1st & 2nd Podium Floor for Parking
3rd Podium (Eco Deck) Floor for Parking
1st to 3rd, 5th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor for Residential
1 |  | 2BHK | 754.4488 | 125.5351 | 879.9839 | 0 | 1319.9759
2 |  | 3BHK | 1078.1222 | 153.4408 | 1231.5631 | 0 | 1847.3446
3 |  | 3BHK | 1139.0465 | 153.4408 | 1292.4873 | 0 | 1938.7309
4 |  | 2BHK | 811.2827 | 125.5351 | 936.8178 | 0 | 1405.2267
5 |  | 2BHK | 811.2827 | 125.5351 | 936.8178 | 0 | 1405.2267
6 |  | 3BHK | 1139.0465 | 153.4408 | 1292.4873 | 0 | 1938.7309
7 |  | 3BHK | 1078.1222 | 153.4408 | 1231.5631 | 0 | 1847.3446
8 |  | 2BHK | 754.4488 | 125.5351 | 879.9839 | 0 | 1319.9759
4th, 8th, 13th, 18th, 23rd & 28th Floor ( Part Refuge Area @ Midlanding) | [8 empty] | 0 |  | 0
1 |  | 2BHK | 754.4488 | 125.5351 | 879.9839 | 0 | 1319.9759 | 62.9275 | 6511880.934 | 6511943.8615 | 6159887.37
2 |  | 3BHK | 1078.1222 | 153.4408 | 1231.5631 | 0 | 1847.3446 | 83.6595 | 9113566.644 | 9113650.3035 | 8620941.42
3 |  | 3BHK | 1139.0465 | 153.4408 | 1292.4873 | 0 | 1938.7309 |  | 9564406.02 |  | 9047411.1
4 |  | 2BHK | 811.2827 | 125.5351 | 936.8178 | 0 | 1405.2267 |  | 6932451.942 |  | 6557724.81
5 |  | 2BHK | 811.2827 | 125.5351 | 936.8178 | 0 | 1405.2267 |  | 6932451.942 |  | 6557724.81
6 |  | 3BHK | 1139.0465 | 153.4408 | 1292.4873 | 0 | 1938.7309 | 11605.5299 | 9564406.02 |  | 9047411.1
7 |  | 3BHK | 1078.1222 | 153.4408 | 1231.5631 | 0 | 1847.3446 | 10149.7036 | 9113566.644 |  | 8620941.42
8 |  | 2BHK | 754.4488 | 125.5351 | 879.9839 | 0 | 1319.9759 |  | 6511880.934 |  | 6159887.37
Ground Floor | [8 empty] | 0
1 |  | 2 |  | 0 | #REF! | Ground Floor |  |  | #REF!
2 |  |  |  | 0 | #REF! | Ground Floor |  |  | #REF!
3 |  |  |  | 0 | #REF! | Ground Floor |  |  | #REF!
4 |  |  |  | 0 | #REF! | Ground Floor |  |  | #REF!
2nd Floor | [8 empty] | 0
201 |  |  |  | 0 | #REF! | 2nd Floor |  |  | #REF!
202 |  |  |  | 0 | #REF! | 2nd Floor |  |  | #REF!
203 |  |  |  | 0 | #REF! | 2nd Floor |  |  | #REF!
204 |  |  |  | 0 | #REF! | 2nd Floor |  |  | #REF!
205 |  |  |  | 0 | #REF! | 2nd Floor |  |  | #REF!
2nd to 5th Floor | [8 empty] | 0
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor |  |  | #REF!
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor |  |  | #REF!
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor |  |  | #REF!
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor |  |  | #REF!
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor |  |  | #REF!
2nd & 5th Floor | [8 empty] | 0
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  | #REF!
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  | #REF!
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  | #REF!
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  | #REF!
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  | #REF!
Remarks:
* | Building No.3 & 4 = Construction work is in process at the time of Visit. (Internal photo was not allowed.)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + F.B Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised plans & CC of Building No. 3 & 4 (on 30/04/2024).
* | Recommended Rates / Other charges of the Property have been revised on 20/06/2024 & 29/08/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Krishna Kambali |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Regency Luxuria Phase I & II
Layout :
Google Map :
Formulas:
Golavli = [Golavli, row above]
Building No. 4
3rd Podium
Building No. 3
Building No. 4
N
Ruby
Emrald
Note on H129: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted