## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-12
Name of the builder group |  |  |  | Mr.Devidas Anant Waingankar
Name of the builder company |  |  |  | M/s.Shree DA Developers
Name of the Project |  |  |  | Shree Sai Kabadi Waingankar Complex (SSKW)
Contact Details ( Name & Contact No.) |  |  |  | Mr. Sagar - 99677048842
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Sagar - 99677048842
Name / No of the Building |  |  |  | Wing A, B & C
Docouments Provided |  |  |  | Refer data
RERA No. |  |  |  | P51700010661
Project location details |  | Shree Sai Kabadi Waingankar Complex (SSKW), Survey No.217 (Pt), near Krishna Petroleum, Mumbai Nashik Highway , Vasind, Vasind, Shahapur, Thane.
Survey No |  | 217 (Pt)
Road |  | Mumbai Nashik Highway |  | Locality |  | Vasind
City |  | Vasind |  | District |  | Thane
Taluka |  | Shahapur |  | Pin Code |  | 421601
Nearby Landmark |  | Krishna Petroleum |  | Distance from city centre: |  | 1.7Km from Vashind Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Krishna Petroleum
West | NA | NA |  |  | Road
North | NA | NA |  |  | Road
South | NA | NA |  |  | Mumbai - Agra National Highway
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.415785,73.2751328
Location Link |  | https://goo.gl/maps/g4r1MsS9GEzeukFT6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2138.2
Permissible FSI |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  | NA
Total FSI availaible for the project |  |  |  | NA
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 1603.65
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  | Dated | NA
Approved Floor plan No. |  | NA |  |  | Dated | NA
Commencement Certificate No. |  | BS/Rekhankan/BP/Mouje.Khativali/Tal.Shahapur/ssthane/403 |  |  | Dated | 2012-03-01
Valid Up to: Wing - A, B & C = G/St + 1st to 3rd Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 1603.65
Approved no of units |  |  | NA
Approved no of Floors |  |  | Wing A, B & C = G/St + 1st to 3rd Floor
Proposed no of Floors |  |  | Wing A & B = G/St + 1st to 3rd Floor Wing C = Basement + Stilt + 1st to 3rd Floor
Wing C = Basement + Stilt + 1st to 3rd Floor
Expected Completion |  |  | As per RERA - 31/03/2024
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A & B = G/St + 1st to 3rd Floor Wing C = Basement + Stilt + 1st to 3rd Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 3
Stage of construction: |  | Construction work completed upto 3rd Floor (Except Lift & Electric Work) | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 93.33% |  | 95% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% |  |  |  |  | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 66.67% |  |  |  |  | Plinth in process | 2.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Construction details: |  | Wing C = Basement + Stilt + 1st to 3rd Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 3
Stage of construction: |  | Construction work completed upto 3rd Floor (Except Lift & Electric Work) | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 93.33% |  | 95% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% |  |  |  |  | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 66.67% |  |  |  |  | Plinth in process | 2.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4000
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Infrastructure cost including meter deposit |  |  |  |  | 95,000/-
24 Month maintenance charges |  |  |  |  | 28,000/-
Paging Charges |  |  |  |  | 1500/-
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 3200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
6 |  |  |  | 0 | 0 | Ground Floor
7 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
206 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301,..,1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 301,..,1501 | 301 | 1501
302,..,1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 302,..,1502 | 302 | 1502
303,..,1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 303,..,1503 | 303 | 1503
304,..,1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 304,..,1504 | 304 | 1504
305,..,1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 305,..,1505 | 305 | 1505
306,..,1506 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 306,..,1506 | 306 | 1506
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 201 to 501 | 201 | 501
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 202 to 502 | 202 | 502
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 203 to 503 | 203 | 503
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 204 to 504 | 204 | 504
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 205 to 505 | 205 | 505
206 to 506 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 206 to 506 | 206 | 506
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 201 & 501 | 201 | 501
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 202 & 502 | 202 | 502
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 203 & 503 | 203 | 503
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 204 & 504 | 204 | 504
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 205 & 505 | 205 | 505
206 & 506 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 206 & 506 | 206 | 506
Remarks:
1. Wing A, B, C = Construction work was same as last visit 11/03/2023. 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4. As per the agreement (Index II), Wing A, Flat no. 101(2BHK) has Carpet Area of 519 Sq.ft & Terrace of 94 Sq.ft valued at Rs. 50,00,000/-. As per the conversion with the builder, he is quoting Rs. 50,00,000/- inclusive of other charges for 2BHK Flats as he is selling those flats as premium flats in the project. 5. As per the agreement (Index II), Wing A, Flat no. 102(2BHK) has Carpet Area of 412 Sq.ft & Terrace of 78 Sq.ft valued at Rs. 40,00,000/-. As per the conversion with the builder, he is quoting Rs. 40,00,000/- inclusive of other charges for 2BHK Flats as he is selling those flats as premium flats in the project. 6. As per RERA, completion period of project Shree Sai Kabadi Waingankar Complex (SSKW) is expired on 31/03/2024 but still project is under construction. 8. Since the project has received first CC on 01/03/2012, but still project is not yet completed. 9. As checked on RERA portal on date 14/07/2025, we have observed that above project "Shree Sai Kabadi Waingankar Complex (SSKW)" is kept under abeyance. Please check from your end 4. Some flats are occupied by tenants. 5. On Site, we meet Mr.Steven(Security) - 9921117353. | [8 empty] | Work is same as last visit (11/03/2023).
1 | Construction work is in process at the time of Visit (labour found). All work completed. OC received.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr........(........).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shree Sai Kabadi Waingankar Complex (SSKW)
Google Map :
Wing A
Wing A
Wing B
Wing C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted