## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s.Transcon Triumph Phase 2 Private Limited
Name of the builder company |  |  |  | M/s.Transcon Triumph Phase 2 Private Limited
Name of the Project |  |  |  | Transcon Triumph Tower 4
Contact Details ( Name & Contact No.) |  |  |  | 2266128128
Name / No of the Building |  |  |  | Tower No.4
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800034924
Project location details |  | Transcon Triumph Tower 4, CTS No.695, 702, 704, 704/1 to 79, 705(pt), 705/2, 720/A/5, 720/84 to 160, 725, 725/7 to 70, 728, 729, 730, 731, 731/1, 732(pt), 732/1(pt) to 15(pt), 737/8/1 & 737/8/2(pt), near Oberoi Springs, Veera Desai Road, Veera Desai Industrial Estate, Oshiwara, Jogeshwari West, Andheri, Mumbai - 400047.
CTS No |  | 695, 702, 704, 704/1 to 79, 705(pt), 705/2, 720/A/5, 720/84 to 160, 725, 725/7 to 70, 728, 729, 730, 731, 731/1, 732(pt), 732/1(pt) to 15(pt), 737/8/1 & 737/8/2(pt)
Locality |  | Veera Desai Industrial Estate
Road |  | Veera Desai Road |  | Village |  | Oshiwara
City |  | Jogeshwari West |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400047
Nearby Landmark |  | Oberoi Springs |  | Distance from city centre: |  | 2.3KM from Jogeshwari Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Kadam Heights
West | NA | NA |  |  | Tower 3
North | NA | NA |  |  | Tower 1
South | NA | NA |  |  | Satyadev Plaza
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.1379335,72.8348443
Location Link |  | https://maps.app.goo.gl/GZ4BFfnJrtVPenV38
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 21745.34
Permissible FSI |  |  |  | 2.2
Permissible TDR/Paid FSI |  |  |  | 1.0166
Total FSI availaible for the project |  |  |  | 3.2166
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 69945.83
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority
Layout Approval No |  | SRA/DDTP/633/KW/PL/AP |  |  | Dated | 2022-03-31
Approved Floor plan No. |  | SRA/DDTP/633/KW/PL/AP |  |  | Dated | 2024-06-18
Commencement-CC No Valid Up to: |  | SRA/DDTP/633/KW/PL/AP |  |  | Dated | 2022-04-08
The plinth CC (Inculding Service Basement) is granted for Tower no.4 is Sale Building as per approved amended plan dated 31/03/2022.
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) For Tower 4 |  |  | 15548.53
Approved no of units |  |  | Flats = 186
Approved no of Floors |  |  | Tower No.4 = LG Floor + P1 to P5 + P6 (Eco-Deck Floor) + 7th to 35th Floor
Proposed no of Floors |  |  | Tower No.4 = LG Floor + UG Floor (1st Floor) + 2nd to 5th Podium + 6th (eco-Bal) + 7th to 38th Floor
Expected Completion |  |  | As per RERA - 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3.Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower No.4 = LG Floor + UG Floor (1st Floor) + 2nd to 5th Podium + 6th (eco-Bal) + 7th to 38th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 17.25 Floor, External Plaster upto 14.95 Floor Completed | , RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 17.25 Floor, External Plaster upto 14.95 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 38 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 17.25 Floor, External Plaster upto 14.95 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 46.49% |  | 70.72% |  | Excavation in process | 19
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 24 | 61.54% |  |  |  |  | Footing in Process | 9.5
Brickwork | Brickwork & Internal Plaster | 23 | 60.53% |  |  |  |  | Footing Completed | 19
Internal Plaster | Brickwork & Internal Plaster | 17.25 | 45.39% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14.95 | 39.34% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 28.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Construction details: Part II |  | Tower No.4 = LG Floor + UG Floor (1st Floor) + 2nd to 5th Podium + 6th (eco-Bal) + 7th to 38th Floor | [5 empty] | Excavation Completed, Footing work Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 38 | Excavation | , Footing work Completed
Stage of construction: |  | Excavation Completed, Footing work Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 5% |  | 32.5% |  | Excavation in process | 19
Plinth |  | 19 | 50% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 9.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 19
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 28.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Progress % |  | 25.75% |  | Disbursement % |  | 51.61%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  | 20000 to 25000 | Gaurav | Cost sheet | 2022-10-18
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 26400 |  |  | 25000 to 26400 & Parking 12L by aakash mote on 28/04/2025 LTV 66.75 Case 3401 & 3402 jodi flat
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Infra & Development Charges |  |  |  |  | 500000
Water, Electricity, Gas Charges |  |  |  |  | 100000
Society Formation Charges
Advance Maintenance Charges |  |  |  |  | 180000
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 21120
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 186 |  | 146016.4048 |  | 233626.2477
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Tower 4
(Lower Ground) Floor for Stack Parking
1st Podium Floor for Parking
2nd Podium Floor floor for Residential
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 2nd Podium Floor floor for Residential |  | 19349.853
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | Entrance Lobby (Triple Height)
6
3rd Podium Floor for Residential & Badminton Court
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 3rd Podium Floor for Residential & Badminton Court
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | Badminton Court
6
4th Podium Floor
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 4th Podium Floor
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | Badminton Court Below
6
5th Podium Floor for Residential & Health Spa
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 5th Podium Floor for Residential & Health Spa
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415 |  |  |  | 38575000
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | Entrance Lobby & Health Spa
6
6th Podium (Eco-Deck) Floor for Residential & Café
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 6th Podium (Eco-Deck) Floor for Residential & Café
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | Entrance Lobby & Café
6
7th Floor for Residential
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 7th Floor for Residential |  |  | 24827.8936
2 |  | 3 | 957.7134 | 0 | 1532.3415 |  |  |  | 18337.9487
3 |  | 3 | 957.7134 | 0 | 1532.3415 |  |  |  | 18337.9487
4 |  | 2 | 708.9843 | 0 | 1134.3749 |  |  |  | 24771.352
5 |  | 2 | 644.2254 | 0 | 1030.7606 |  |  |  | 27261.4212
6 |  | 2 | 644.2254 | 0 | 1030.7606 |  |  |  | 27261.4212
9th to 14th, 16th to 21st, 23rd to 28th Floor
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 9th to 14th, 16th to 21st, 23rd to 28th Floor
2 |  | 3 | 957.7134 | 0 | 1532.3415 |  |  |  | 26702.2858
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749 |  |  | 1196.8 | 24810.7402 | 31590622.792
5 |  | 2 | 644.2254 | 0 | 1030.7606
6 |  | 2 | 644.2254 | 0 | 1030.7606
8th, 15th, 22nd & 29th Floor
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 8th, 15th, 22nd & 29th Floor
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | Refuge Area
6
30th to 35th Floor
1 |  | 2 | 707.3697 | 0 | 1131.7915 | 30th to 35th Floor |  | 70333112.6784 | 71893112.6784 | 75493112.6784 | 78538112.6784
2 |  | 3 | 957.7134 | 0 | 1532.3415
3 |  | 3 | 957.7134 | 0 | 1532.3415
4 |  | 2 | 708.9843 | 0 | 1134.3749
5 |  | 2 | 687.9407 | 0 | 1100.7051
6 |  | 2 | 687.9407 | 0 | 1100.7051 |  |  |  |  | 6
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated latest approved floor plans (On 21/04/2025).
* | Provided layout plan is not legible. Please provide legible approved layout plan & Revised approved CC (dtd. 18/06/2024).
* | Recommended Rates/Other Charges of the Property have been revised on 28/04/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Transcon Triumph Tower 4
Google Map :
Part 1
Part 2
Tower 4

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted