## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | Kapstone Constructions Private Limited
Name of the builder company |  |  |  | Kapstone Constructions Private Limited
Name of the Project |  |  |  | Rustomjee La Vie Wing A, B & C
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Santosh - 9820995007
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Prathmesh
Name / No of the Building |  |  |  | Sub Plot 8A Wing A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | Wing A = P51700050803 Wing B = P51700053110 Wing C = P51700053109
Project location details |  | Rustomjee La Vie Wing A, B & C, Survey No.12, 13, 14pt, 15, 16pt, 17pt, 18pt, 19pt, 20, 21pt, 30pt, 35 to 38, 41, 42, 43, 44, 44, 45pt, 46pt, 47pt, 48, 49, 50, 51, 53pt, 54, 55, 84pt, 327, 328, 329, 345, 383, 386pt, 423, 424 & Others, near Lodha Crown, RG Road, Laxmi Nagar, Majiwade, Thane West, Thane, Thane - 400601.
Survey No |  | 12, 13, 14pt, 15, 16pt, 17pt, 18pt, 19pt, 20, 21pt, 30pt, 35 to 38, 41, 42, 43, 44, 44, 45pt, 46pt, 47pt, 48, 49, 50, 51, 53pt, 54, 55, 84pt, 327, 328, 329, 345, 383, 386pt, 423, 424 & Others
Locality |  | Laxmi Nagar
Road |  | RG Road |  | Locality/Village |  | Majiwade
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400601
Nearby Landmark |  | Lodha Crown |  | Distance from city centre: |  | 4.40 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | 45.00 M. Wide D.P. Road |  |  | RG Road/Pipelin
West | NA | Other Plot |  |  | Lodha Crown
North | NA | Other Plot |  |  | Open Plot
South | NA | 20.00 M. Wide Service Road |  |  | RG Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.210904,72.990706
Location Link |  | https://maps.app.goo.gl/kZkaaAzt8k5kmfsh7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 441626.81
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.44655
Total FSI availaible for the project |  |  |  | 1.4466
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 638836.19
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation (TMC)
Layout Approval No For Wing A, B & C |  | S05/0022/10 TMCB/TDD/0006/(P/T)/ 2023/AutoDCR |  |  | Dated | 2023-09-15
Layout Approval No |  | VP/S05/0022/10/TMC/TD-DP/ TPS/4294/23 |  |  | Dated | 2023-02-14
Approved Floor plan No. For Wing A |  | VP/S05/0022/10/TMC/TD-DP/ TPS/4294/23 |  |  | Dated | 2023-02-14
Commencement-CC No For Wing A Valid Up to: |  | VP/S05/0022/10/TMC/TDD/4294/23 |  |  | Dated | 2023-02-14
A Wing = 3B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 40th Floor
Wing B & C
Approved Floor plan No. For Wing B & C |  | S05/0022/10 TMCB/TDD/0006/(P/T)/ 2023/AutoDCR |  |  | Dated | 2023-09-15
Commencement-CC No For Wing B & C Valid Up to: |  | VP/S05/0022/10/TMC/TDD/4294/23 |  |  | Dated | 2023-09-15
Wing B = 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 53rd Floor Wing C = 4B + G + 1st to 23rd + Service Floor + Recreational Floor + 24th to 54th Floor
Fire NOC Valid Up to: |  | TMC/CFO/42142 |  |  | Dated | 2021-03-18
Wing A, B & C Basement + 1st to 45th Floor (150.08Mt Height)
Environmental Clearance Valid Up to: |  | SIA/MH/MIS/81646/2017 |  |  | Dated | 2023-02-23
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 121558.39
Approved no of units |  |  | Flats - 1367
Approved no of Floors |  |  | A Wing = 3B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor Wing B = 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 53rd Floor Wing C = 4B + G + 1st to 23rd + Service Floor + Recreational Floor + 24th to 54th Floor
Proposed no of Floors |  |  | A Wing = 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor
Wing B = 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor
Wing C = 4B + G + 1st to 23rd + Service Floor + Recreational Floor + 24th to 55th Floor
Expected Completion |  |  | As per RERA - Wing A = 31/12/2028 Wing B & C = 28/02/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Medical Facilities, Letter Box, High Speed Elevators, Foosball, Escalators, Changing Room, Beach Volley Ball Court, Pergola, Multipurpose Hall, Manicured Garden, Senior Citizen Siteout, Solar Lighting, Security Cabin,Intercom, Banquet Hall, Amphitheater, Indoor Games, Gymnasium etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  |  |  | Photo provided by the bank on 11/09/2024
Construction details: |  | A Wing = 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab Completed | , RCC upto 5 Slab
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 55 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 13.75
Excavation |  | 55 | 100% | 13.57% |  | 47.68% |  | Excavation in process | 27.5
Plinth |  | 55 | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 5 | 8.929% |  |  |  |  | Footing in Process | 9.1667
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 18.3333
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 27.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 36.6667
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 45.8333
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Construction details: |  | Wing B = 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 55 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 13.75
Excavation |  | 55 | 100% | 10.71% |  | 45.54% |  | Excavation in process | 27.5
Plinth |  | 55 | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 1 | 1.786% |  |  |  |  | Footing in Process | 9.1667
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 18.3333
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 27.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 36.6667
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 45.8333
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Construction details: |  | Wing C = 4B + G + 1st to 23rd + Service Floor + Recreational Floor + 24th to 55th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 55 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 13.75
Excavation |  | 55 | 100% | 10.71% |  | 45.54% |  | Excavation in process | 27.5
Plinth |  | 55 | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 1 | 1.786% |  |  |  |  | Footing in Process | 9.1667
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 18.3333
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 27.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 36.6667
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 45.8333
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 14000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Infrastructure Charges |  |  |  |  | 700000 |  |  | 1387301
Registration Charges |  |  |  |  | 50000
Society Formation Charges |  |  |  |  | 50000
Gas Connection Charges
Electric water connections & piped gas connection charges |  |  |  |  | 150000 |  |  | 173895
Society Formation Charges
24 Months Maintenance Charges |  |  |  |  | 350000 |  |  | 649808
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 11200 |  |  |  |  | rate 14000 sanjay verbal CAse C wing 2305
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 529 |  | 374321.4288 |  | 580198.2146
Wing B |  | 520 |  | 297863.9429 |  | 461689.1115
Wing C |  | 318 |  | 275463.8797 |  | 426969.0135
Total |  | 1367 |  | 947649.2514 |  | 1468856.3397
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Sub Plot No. 8A
Wing A
1st to 3rd Basement Floor For Parking
Ground Floor For Entrance Lobby, Panel Room & Double Height Parking
1st Floor For Drivers Room, Society Office, BMS Room & ELV Room | [10 empty] | cost Sheet
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd, 24th, 26th to 29th, 31st to 34th, 36th to 39th, 41st to 44th, 46th to 49th & 51st to 54th Floor For Residential | [8 empty] | Inspection | official site | 13307.0883
1 |  | 2BHK | 711.2448 | 0 | 1102.4294 | 2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd, 24th, 26th to 29th, 31st to 34th, 36th to 39th, 41st to 44th, 46th to 49th & 51st to 54th Floor For Residential |  | 53.5358 | 11610.7211 | 12309.8002 | 14108.3053
2 |  | 2BHK | 728.1415 | 0 | 1128.6194 |  |  |  |  | 12279.0874
3 |  | 2BHK | 693.5474 | 0 | 1074.9985 |  |  |  |  | 12699.2263
4 |  | 2BHK | 730.5365 | 0 | 1132.3316 |  |  | 10.764 |  | 12429.3713
5 |  | 2BHK | 670.8528 | 0 | 1039.8219 |  |  | https://www.rustomjeelaviemajiwada.co.in/
6 |  | 2BHK | 670.8528 | 0 | 1039.8219
7 |  | 2BHK | 733.4697 | 0 | 1136.8781 |  |  |  |  | 11368.7807
8 |  | 2BHK | 693.5474 | 0 | 1074.9985 |  |  |  |  | 272850.7373
9 |  | 2BHK | 731.4246 | 0 | 1133.7081
10 |  | 2BHK | 670.8528 | 0 | 1039.8219
7th, 12th, 17th, 30th, 35th, 40th, 45th, 50th, 55th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th, 12th, 17th, 30th, 35th, 40th, 45th, 50th, 55th Floor (Part Refuge Area)
2 |  | 3BHK | 916.9152 | 0 | 1421.2186 |  |  | 74.6628
3 |  | 2BHK | 693.5474 | 0 | 1074.9985
4 |  | 2BHK | 730.5365 | 0 | 1132.3316
5 |  | 2BHK | 670.8528 | 0 | 1039.8219
6 |  | 2BHK | 683.366 | 0 | 1059.2173
7 |  | 2BHK | 733.4697 | 0 | 1136.8781
8 |  | 2BHK | 708.4286 | 0 | 1098.0644
9 |  | 2BHK | 731.4246 | 0 | 1133.7081
10 |  | 2BHK | 670.8528 | 0 | 1039.8219
22nd & 25th Floor
1 |  | Refuge Area |  |  |  | 22nd & 25th Floor
2 |  | 3BHK | 897.244 | 0 | 1390.7282
3 |  | 2BHK | 693.5474 | 0 | 1074.9985
4 |  | 2BHK | 730.5365 | 0 | 1132.3316
5 |  | 2BHK | 670.8528 | 0 | 1039.8219
6 |  | 2BHK | 670.8528 | 0 | 1039.8219
7 |  | 2BHK | 733.4697 | 0 | 1136.8781
8 |  | 2BHK | 693.5474 | 0 | 1074.9985
9 |  | 2BHK | 731.4246 | 0 | 1133.7081
10 |  | 2BHK | 670.8528 | 0 | 1039.8219
Wing B
1st to 4th Basement Floor For Parking
Ground Floor for Commercial, Entrance Lobby, Society Office, Panel Room & Parking
1st to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential | [7 empty] | 18
1 |  | 2BHK | 560.8071 | 0 | 869.251 | 1st to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential
2 |  | 2BHK | 583.9201 | 0 | 905.0761
3 |  | 2BHK | 558.1941 | 0 | 865.2009
4 |  | 2BHK | 583.9201 | 0 | 905.0761
5 |  | 2BHK | 560.8071 | 0 | 869.251
6 |  | 2BHK | 560.8071 | 0 | 869.251
7 |  | 2BHK | 575.1205 | 0 | 891.4368
8 |  | 2BHK | 558.1941 | 0 | 865.2009
9 |  | 2BHK | 581.9826 | 0 | 902.073
10 |  | 2BHK | 560.8071 | 0 | 869.251
7th, 12th, 17th, 30th, 35th, 40th, 45th & 50th Floor (Part Refuge Area) | [7 empty] | 8
1 |  | 2BHK | 560.8071 | 0 | 869.251 | 7th, 12th, 17th, 30th, 35th, 40th, 45th & 50th Floor (Part Refuge Area)
2 |  | 2BHK | 612.9829 | 0 | 950.1235
3 |  | 2BHK | 558.1941 | 0 | 865.2009
4 |  | 3BHK | 728.8439 | 0 | 1129.708
5
6 |  | 2BHK | 589.8699 | 0 | 914.2983
7 |  | 2BHK | 579.4799 | 0 | 898.1939
8 |  | 2BHK | 587.2569 | 0 | 910.2482
9 |  | 2BHK | 581.9826 | 0 | 902.073
10 |  | 2BHK | 560.8071 | 0 | 869.251
22nd & 25th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 2BHK | 560.8071 | 0 | 869.251 | 22nd & 25th Floor (Part Refuge Area)
2 |  | 2BHK | 583.9201 | 0 | 905.0761
3 |  | 2BHK | 558.1941 | 0 | 865.2009
4 |  | 3BHK | 728.8439 | 0 | 1129.708
5
6 |  | 2BHK | 560.8071 | 0 | 869.251
7 |  | 2BHK | 579.4799 | 0 | 898.1939
8 |  | 2BHK | 558.1941 | 0 | 865.2009
9 |  | 2BHK | 581.9826 | 0 | 902.073
10 |  | 2BHK | 560.8071 | 0 | 869.251
Service Floor & Recreational Floor (For Fitness Centre, Conference) is in between 22nd & 23rd Floors
23rd, 24th, 26th to 29th, 31st to 34th, 36th to 39th, 41st to 44th, 46th to 49th, 51st to 53rd Floor | [7 empty] | 25
1 |  | 2BHK | 560.8071 | 0 | 869.251 | 23rd, 24th, 26th to 29th, 31st to 34th, 36th to 39th, 41st to 44th, 46th to 49th, 51st to 53rd Floor
2 |  | 2BHK | 583.9201 | 0 | 905.0761
3 |  | 2BHK | 558.1941 | 0 | 865.2009
4 |  | 2BHK | 583.9201 | 0 | 905.0761
5 |  | 2BHK | 560.8071 | 0 | 869.251
6 |  | 2BHK | 560.8071 | 0 | 869.251
7 |  | 2BHK | 575.1205 | 0 | 891.4368
8 |  | 2BHK | 558.1941 | 0 | 865.2009
9 |  | 2BHK | 581.9826 | 0 | 902.073
10 |  | 2BHK | 560.8071 | 0 | 869.251
Wing C
1st to 4th Basement Floor For Parking
Ground Floor For Etrance Lobby, Meter Room, Panel Room & Parking
1st Floor For Society Office
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor For Residential | [7 empty] | 18
1 |  | 3BHK | 900.1745 | 0 | 1395.2704 | 2nd to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor For Residential
2 |  | 3BHK | 838.1023 | 0 | 1299.0585
3 |  | 3BHK | 893.7161 | 0 | 1385.2599
4 |  | 3BHK | 893.7161 | 0 | 1385.2599
5 |  | 3BHK | 838.1023 | 0 | 1299.0585
6 |  | 3BHK | 882.4058 | 0 | 1367.729
8th, 13th, 18th, 31st, 36th, 41st, 46th & 51st Floor (Part Refuge Area) | [7 empty] | 8
1 |  | 3BHK | 900.1745 | 0 | 1395.2704 | 8th, 13th, 18th, 31st, 36th, 41st, 46th & 51st Floor (Part Refuge Area)
2 |  | 2BHK | 662.3154 | 0 | 1026.5888
3 |  | 2BHK | 741.1902 | 0 | 1148.8448
4 |  | 3BHK | 922.7789 | 0 | 1430.3073
5 |  | 3BHK | 867.1651 | 0 | 1344.1058
6 |  | 3BHK | 911.4686 | 0 | 1412.7763
23rd & 26th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 3BHK | 900.1745 | 0 | 1395.2704 | 23rd & 26th Floor (Part Refuge Area)
2 |  | 2BHK | 662.3154 | 0 | 1026.5888
3 |  | 2BHK | 741.1902 | 0 | 1148.8448
4 |  | 3BHK | 893.7161 | 0 | 1385.2599
5 |  | 3BHK | 838.1023 | 0 | 1299.0585
6 |  | 3BHK | 882.4058 | 0 | 1367.729
Service Floor & Recreational Floor (For Multipurpose Hall & Swimming Pool) is in between 23rd & 24th Floors
24th, 25th, 27th to 30th, 32nd to 35th, 37th to 40th, 42nd to 45th, 47th to 50th & 52nd to 54th Floor | [7 empty] | 25
1 |  | 3BHK | 900.1745 | 0 | 1395.2704 | 24th, 25th, 27th to 30th, 32nd to 35th, 37th to 40th, 42nd to 45th, 47th to 50th & 52nd to 54th Floor
2 |  | 3BHK | 838.1023 | 0 | 1299.0585
3 |  | 3BHK | 893.7161 | 0 | 1385.2599
4 |  | 3BHK | 893.7161 | 0 | 1385.2599
5 |  | 3BHK | 838.1023 | 0 | 1299.0585
6 |  | 3BHK | 882.4058 | 0 | 1367.729
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan. | [6 empty] | Wing A = Net carpet + Balcony + Chajja Area
* | We considered Gross carpet area = Net carpet + Balcony + Utility Area + Chajja Area. | [6 empty] | Wing B & C = Net carpet + Balcony + Utility Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved plans and CC for Wing B & C (on 21/10/2024).
* | We have not drafted Wing B commercial shop area because shop numbering is not mentioned on approved plans.
* | Please Check for Environmental Clearance. | [6 empty] | EC drafted in RBL report not for plot 8A
* | Please provide approved plans for Wing A.
* | Recommended Rates/Other Charges of the Property have been revised on 28/10/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Rustomjee La Vie Wing A, B & C
Layout :
Google Map :
Formulas:
Majiwade = [Majiwade, row above]
Photo provided by the bank on 11/09/2024
Wing C
Wing B
Wing A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted