## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | Sai Balaji Enterprises |  |  |  |  | ss life spaces firm
Name of the builder company |  |  |  | Sai Balaji Enterprises
Name of the Project |  |  |  | Balaji Govind
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Manish Telramani 9136695258
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Suraj 8356002318
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P51700032267
Project location details |  | Balaji Govind, Survey No.30, H.No.2(Pt), 3A, 3B, 4, 5 & 6, near Balaji Gopal, Internal Road, Kanchangaon, Kanchangaon, Thakurli East, Kalyan, Thane - 421201.
Survey No |  | 30, H.No.2(Pt), 3A, 3B, 4, 5 & 6
Locality |  | Kanchangaon
Road |  | Internal Road |  | Locality/Village |  | Kanchangaon
City |  | Thakurli East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Nearby Landmark |  | Balaji Gopal |  | Distance from city centre: |  | 2.6KM from Thakurli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 24.00 M. WD D.P Road |  |  | Internal Road
West | NA | Other Plot |  |  | Open Plot
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.2213093,73.1103424
Location Link |  | https://goo.gl/maps/57Af2gDfGbrgwcde8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2372.75
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 4.0611
Total FSI availaible for the project |  |  |  | 5.1611
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12246
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation (KDMC)
Layout Approval No |  | KDMC/TPD/BP/DOM/2021-22/42/257 |  |  | Dated | 2022-09-08
Approved Floor plan No. |  | KDMC/TPD/BP/DOM/2021-22/42/257 |  |  | Dated | 2022-09-08
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/DOM/2021-22/42/257 |  |  | Dated | 2022-09-08
|  | Wing A = Gr + 1st to 14th Floor Wing B = Gr + 1st to 14th Floor + 15th(Pt) Floor | [5 empty] | a wing gr + st on cc
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 12246
Approved no of units |  |  | Flats - 210, Shops - 7
Approved no of Floors |  |  | Wing A = Gr + 1st to 14th Floor Wing B = Gr + 1st to 14th Floor + 15th(Pt) Floor |  |  |  |  | B Wing = G + 1st to 14th Floor + 15th Floor
Proposed no of Floors |  |  | Wing A = Gr + 1st to 14th Floor
Wing B = Gr + 1st to 14th Floor + 15th(Pt) Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Kids Play Area, Garden, CCTV surveillance, Gymnasium, Video Door Phone, Gazebo, Lift, etc. |  |  |  |  | https://bellamaisonrealty.com/Property_for_sale.php?projectname=Balaji%20Govind
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 11 Floor, Painting upto 7 Floor Completed | , Flooring upto 11 Floor, Painting upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 11 Floor, Painting upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 85.36% |  | 93.93% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 78.57% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing B = Gr + 1st to 14th Floor + 15th(Pt) Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 13 Floor Completed | , External Plaster upto 13 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 13 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 73.67% |  | 89.33% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 86.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6600 |  |  | Rate 6600 OC 2.5L Park 3L Bhargav verbal 30/01/2025
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Other Charges |  |  |  |  | 250000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 5280
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 7 |  | 1375.2086 |  | 2754
Total |  | 7 |  | 1375.2086 |  | 2754
Residential Area Details : | [8 empty] | cost sheet | visitor | market
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 6000 | 6000 | 6300-7100
Wing A |  | 112 |  | 56054.9939 |  | 81602
Wing B |  | 98 |  | 41655.313 |  | 59598
Total |  | 210 |  | 97710.3069 |  | 141200 |  |  | 143954 | 99085.5155
Grand Total |  | 217 |  | 99085.5155 |  | 143954
Building Details Floor Wise
Details of Residential & Commercial in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Wing A | [8 empty] | 10.764
Ground Floor For Commercial, Meter Room, Driver Room & Parking | [7 empty] | 203.2243 | 18.4 | 2.0004
1 |  | Shop | 200.9639 | 0 | 402 | Ground Floor For Commercial, Meter Room, Driver Room & Parking |  |  |  | 2.0015
2 |  | Shop | 172.8698 | 0 | 346 |  |  |  |  | 2.0047
3 |  | Shop | 200.5333 | 0 | 402 |  |  |  |  | 2.0036
4 |  | Shop | 200.641 | 0 | 402 |  |  |  |  | 2.0056
5 |  | Shop | 226.3669 | 0 | 454 |  |  |  |  | 2.0015
6 |  | Shop | 172.8698 | 0 | 346 |  |  |  |  | 2.0004
7 |  | Shop | 200.9639 | 0 | 402
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor |  | 1.5 | 42.208 | 42.208 |  | 2688066.81
Wing A | [7 empty] | 61.8047 | 8.2875 | 53.5172
1st Floor For Residential | [9 empty] | 1.4522 | 44.51 |  | 42.208
1 |  | 2 | 530.9074 | 0 | 771 | 1st Floor For Residential |  | 1.4522 | 42.208 | 1.4265 | 34.058
2 |  | 1 | 407.2828 | 0 | 581 |  |  | 1.4265 |  | 1.4238 | 24.4135
3 |  | 1 | 408.0579 | 0 | 581 |  |  | 1.4238 | 1.5463 | 2.1904 |  |  | 7.42
4 |  | 2 | 531.8761 | 342.5794 | 1165 |  |  | 2.1904 | 42.484 | 1.7058 | 34.1965 |  | 2.66
5 |  | 2 | 532.3067 | 113.4439 | 908 |  |  | 1.7058 |  | 1.4501 | 1.26
6 |  | 2 | 531.6824 | 0 | 771 |  |  | 1.4501 |  | 1.4522
7 |  | 2 | 530.9074 | 0 | 771 |  |  | 1.4522 |  | 1.4522 | 1.6982
8 |  | 2 | 530.9074 | 0 | 771 |  |  | 1.4522 |  | #DIV/0! | 1.6988
2nd to 7th, 9th to 12th &14th Floor | [9 empty] | 1.4522 | 1.6988
1 |  | 2 | 530.9074 | 0 | 771 | 2nd to 7th, 9th to 12th &14th Floor |  | 1.4522 |  | 1.4265
2 |  | 1 | 407.2828 | 0 | 581 |  |  | 1.4265 |  | 1.4238
3 |  | 1 | 408.0579 | 0 | 581 |  |  | 1.4238 |  | 1.4552
4 |  | 2 | 531.8761 | 0 | 774 |  |  | 1.4552 |  | 1.4484
5 |  | 2 | 532.3067 | 0 | 771 |  |  | 1.4484 |  | 1.4501
6 |  | 2 | 531.6824 | 0 | 771 |  |  | 1.4501 |  | 1.4522
7 |  | 2 | 530.9074 | 0 | 771 |  |  | 1.4522 |  | 1.4522
8 |  | 2 | 530.9074 | 0 | 771 |  |  |  |  | #DIV/0!
8th & 13th Floor (Part Refuge Area) | [9 empty] | 1.4522
1 |  | 2 | 530.9074 | 0 | 771 | 8th & 13th Floor (Part Refuge Area) |  |  |  | 1.4265
2 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4238
3 |  | 1 | 408.0579 | 0 | 581 |  |  |  |  | 1.4552
4 |  | 2 | 531.8761 | 0 | 774 |  |  |  |  | 1.4484
- |  | Refuge Area
5 |  | 2 | 532.3067 | 0 | 771 |  |  |  |  | 1.4501
6 |  | 2 | 531.6824 | 0 | 771 |  |  |  |  | 1.4522
7 |  | 2 | 530.9074 | 0 | 771 |  |  |  |  | 1.4522
8 |  | 2 | 530.9074 | 0 | 771 |  |  | 10 |  | #REF!
Wing B | [9 empty] | #DIV/0!
Ground Floor For Meter Room & Parking | [7 empty] | 11 |  | #DIV/0!
1st to 7th, 9th to 12th &14th Floor | [7 empty] | 6301.2048 | 1.4265 | 1.4265
1 |  | 1 | 407.2828 | 0 | 581 | 1st to 7th, 9th to 12th &14th Floor |  | 24.051 | 1.4522 | 1.4522
2 |  | 2 | 530.9074 | 0 | 771 |  |  | 1.4265 |  | 1.4265
3 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4265
4 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4265 | 679.69
5 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4238
6 |  | 1 | 408.0579 | 0 | 581 |  |  |  |  | 1.4265
7 |  | 1 | 407.2828 | 0 | 581 |  |  | 2 |  | #DIV/0!
8th & 13th Floor ( Part Refuge Area) | [9 empty] | 1.4265
1 |  | 1 | 407.2828 | 0 | 581 | 8th & 13th Floor ( Part Refuge Area) |  |  |  | 1.4522
2 |  | 2 | 530.9074 | 0 | 771 |  |  |  |  | 1.4265
3 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4265
4 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4265
5 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | 1.4238
6 |  | 1 | 408.0579 | 0 | 581 |  |  |  |  | 1.4265
7 |  | 1 | 407.2828 | 0 | 581 |  |  |  |  | #DIV/0!
15th Floor For Society Office, Fitness Center & Part Terrace Area | [9 empty] | #REF!
Remarks: | [9 empty] | #DIV/0!
* | Construction work is in process at the time of Visit. | [8 empty] | #DIV/0!
* | We considered Saleable area of Flat as per Builder area Sheet. | [8 empty] | #DIV/0!
* | We considered Saleable area of Commercial as per Builder area Sheet. | [8 empty] | #DIV/0!
* | We considered Carpet area as per Approved Plan. | [8 empty] | #DIV/0!
* | We considered Gross carpet area = Net carpet + Encl Balcony + Open Balcony Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates / Other charges of the Property have been revised on 30/01/2025.
* | As per the revised approved plan dated 08/09/2022, the approved structure of Wing A is reduced to Gr + 1st to 14th Floor (earlier it was Wing A = Gr + 1st to 15th Floor)
* | We have updated revised approved plans & CC on 05/04/2025
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Balaji Govind
Layout Plan :
Google Map :
Formulas:
Kanchangaon = [Kanchangaon, row above]
WING A
WING B
Wing A
Wing B
Wing A
Wing A
Wing A
Wing B
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted