## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | Haware Engineers And Builders Private Limited
Name of the builder company |  |  |  | Haware Engineers And Builders Private Limited
Name of the Project |  |  |  | Haware Elinor
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Ashish : 8454892018
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Padmakar : 9867874046
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | NA | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area, Cost sheet | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000049131 |  |  |  | #N/A |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Haware Elinor, Plot No.14, Sector -16E, near Springdale Apartment, Internal Road, Roadpali, Kalamboli, Kharghar, Panvel, Raigad - 410218. | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 14, Sector -16E | [9 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Roadpali | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Kalamboli | [5 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kharghar |  | District |  | Raigad | [5 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410218 | [8 empty] | Mahad | Daund
Nearby Landmark |  | Springdale Apartment |  | Distance from city centre: |  | 5.5 KM from Kharghar Railway Station | [8 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [10 empty] | Mangaon | Ambegaon
[15 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [10 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [10 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [10 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Plot No. 13A |  |  | Rangai
West | NA | 6.00M Winde Road |  |  | Springdale Apartment
North | NA | Plot No. 9A |  |  | Internal Road
South | NA | 15.00M Wide Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.043560, 73.098805
Location Link |  | https://maps.app.goo.gl/MZ5gp58qST9yJTxX6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1449.31
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.8684
Total FSI availaible for the project |  |  |  | 3.3684
Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 4881.813
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | PMP/NRV/10404/3019/2023 |  |  | Dated | 2023-10-18
Approved Floor plan No. |  | PMP/NRV/10404/3019/2023 |  |  | Dated | 2023-10-18
Commencement-CC No |  | PMC/TP/Kalamboli/16E/14/21-23/ 10404/3019/2023 |  |  | Dated | 2023-10-18
Valid Up to: |  | Gr + 1st to 14th Floor (Residential Units = 81, Commercial Units = 09)
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4881.813
Approved no of units |  |  | Flats - 81, Shops - 09
Approved no of Floors |  |  | Gr + 1st to 6th Floor
Proposed no of Floors |  |  | Gr + 1st to 19th Floor
Expected Completion |  |  | As per RERA - 10/11/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Stack Car Parking, Roof Top Garden, Gazeboo Lounge, Kids Play Area, Senior Citizen Area
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 14 Floor, Internal Plaster upto 14 Floor, External Plaster upto 14 Floor, Flooring upto 11 Floor, Painting upto 7 Floor Completed | , RCC upto 17 Slab, Brickwork upto 14 Floor, Internal Plaster upto 14 Floor, External Plaster upto 14 Floor, Flooring upto 11 Floor, Painting upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 14 Floor, Internal Plaster upto 14 Floor, External Plaster upto 14 Floor, Flooring upto 11 Floor, Painting upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 70.05% |  | 84.45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 17 | 85% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 14 | 73.68% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 14 | 73.68% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 73.68% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 57.89% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 36.84% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7300 |  |  | 7000 to 7300 | 2024-02-20 | smith
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 13000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Water, MSEB, Development Charges |  |  |  |  | 300000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 5840
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 9 |  | 1748.46 |  | 3530
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 81 |  | 35124.0084 |  | 59105
Grand Total |  | 90 |  | 36872.4684 |  | 62635
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
50%
Ground Floor for Commercial & Parking Area | [10 empty] | 10.764
1 |  | Shop | 182.8804 | 0 | 370 | Ground Floor for Commercial & Parking Area |  | 2.0232
2 |  | Shop | 190.8457 | 0 | 384 |  |  | 2.0121
3 |  | Shop | 230.3496 | 0 | 464 |  |  | 2.0143
4 |  | Shop | 174.1615 | 0 | 354 |  |  | 2.0326
5 |  | Shop | 170.5556 | 0 | 346 |  |  | 2.0287
6 |  | Shop | 181.6877 | 0 | 366 |  |  | 2.0144
7 |  | Shop | 229.0762 | 0 | 460
8 |  | Shop | 206.023 | 0 | 416
9 |  | Shop | 182.8804 | 0 | 370
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
50%
1st Floor Residential & Society Office
1 |  | 2BHK | 536.2625 | 69.4278 | 1022 | 1st Floor Residential & Society Office |  | 48.1475
2 |  | 1BHK | 387.7193 | 0 | 818 |  |  | 35.0055
3 |  | 2BHK | 536.2625 | 70.2889 | 1022 |  |  | 10.764
4 |  | 1BHK | 384.7054 | 0 | 643
5 |  | Society Office
6 |  | 1BHK | 371.7886 | 0 | 643
2nd to 7th Floor
1 |  | 2BHK | 536.2625 | 0 | 895 | 2nd to 7th Floor |  | 1.669
2 |  | 1BHK | 387.7193 | 0 | 648 |  |  | 1.6713
3 |  | 2BHK | 536.2625 | 0 | 895 |  |  | 1.669
4 |  | 1BHK | 384.7054 | 0 | 643 |  |  | 1.6714
5 |  | 1BHK | 371.7886 | 0 | 621 |  |  | 1.6703
6 |  | 1BHK | 371.7886 | 0 | 621 |  |  | 1.6703
8th, 10th & 12th Floor (Refuge Balcony At Mindlanding of Stairecase)
1 |  | 2BHK | 536.2625 | 0 | 895 | 8th, 10th & 12th Floor (Refuge Balcony At Mindlanding of Stairecase) |  | 1.669
2 |  | 1BHK | 387.7193 | 0 | 648 |  |  | 1.6713
3 |  | 2BHK | 536.2625 | 0 | 895 |  |  | 1.669
4 |  | 1BHK | 384.7054 | 0 | 643 |  |  | 1.6714
5 |  | 1BHK | 371.7886 | 0 | 621 |  |  | 1.6703
6 |  | 1BHK | 371.7886 | 0 | 621 |  |  | 1.6703
9th, 11th & 13th Floor
1 |  | 2BHK | 536.2625 | 0 | 895 | 9th, 11th & 13th Floor |  | 1.669
2 |  | 1BHK | 387.7193 | 0 | 648 |  |  | 1.6713
3 |  | 2BHK | 536.2625 | 0 | 895 |  |  | 1.669
4 |  | 1BHK | 384.7054 | 0 | 643 |  |  | 1.6714
5 |  | 1BHK | 371.7886 | 0 | 621 |  |  | 1.6703
6 |  | 1BHK | 371.7886 | 0 | 621 |  |  | 1.6703
14th Floor
1 |  | 2BHK | 536.2625 | 0 | 895 | 14th Floor
2 |  | 1BHK | 387.7193 | 0 | 648 | 14th Floor
3 |  | 2BHK | 536.2625 | 0 | 895 | 14th Floor
4 |  | 1BHK | 384.7054 | 0 | 643 | 14th Floor
5 |  | Terrace Area |  |  |  | 14th Floor
6 | [5 empty] | 14th Floor
Remarks:
* | Construction work is in process at the time of Visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Chajja
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Hindu cremation is located on the west side of the project.
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated revised approved plans (On 29/02/2024).
* | We have updated revised approved CC from RERA site on 18/01/2024.
* | Recommended Rates/Other Charges of the Property have been revised on 20/02/2024.
* | Construction stage is reduced due to revision in proposed structure of project.
* | Construction work goes beyond CC permission. Please provide revised approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Haware Elinor
Layout :
Google Map :
Formulas:
Kalamboli = [Kalamboli, row above]
Hindu cremation
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC