## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | Shubham Realty
Name of the builder company |  |  |  | Shubham Realty
Name of the Project |  |  |  | Jijai Tulsi
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Vinay Kalantare 9833892787
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Santosh : 9321482979
Name / No of the Building |  |  |  | Wing A (Aaradhya) & Wing B (Durva)
Name / No of the Existing Building
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000050705
Project location details |  | Jijai Tulsi, Survey No.105/4, 105/5 & 106/1, near Jijai Angan, Ghot Road, Ghot, Taloja Majkur, Taloja East, Panvel, Raigad - 410208.
Survey No |  | 105/4, 105/5 & 106/1
Locality |  | Ghot
Road |  | Ghot Road |  | Locality/Village |  | Taloja Majkur
City |  | Taloja East |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Jijai Angan |  | Distance from city centre: |  | 4.4KM from Taloja Panchnand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Internal Road/ Jijai Angan
West | NA | Other Plot |  |  | QA Riverfront
North | NA | S.No.105 H.No.6, 7 & 8 |  |  | Open Plot
South | NA | Internal Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.084050,73.109680
Location Link |  | https://goo.gl/maps/voAD4KkV9x34wVD79
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6340
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.4599
Total FSI availaible for the project |  |  |  | 2.5599
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 16230.032
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation (PMC)
Layout Approval No |  | PMP/NRV/16488/J.K.2011/2022 |  |  | Dated | 2022-06-30
Approved Floor plan No. |  | PMP/NRV/16488/J.K.2011/2022 |  |  | Dated | 2022-06-30
Commencement-CC No Valid Up to: |  | PMC/TP/Taloje Majkur/ 105/4, 105/5 & 106/1 / 21-22/16488/2011/2022 |  |  | Dated | 2022-06-30
Wing A & B = G + 17th Upper Floor
|  | CARPC/RP/2024/APL/00013 |  |  | Dated | 2024-05-09
The renewal of bldg permission is granted upto period, dtd 29/06/2024 with the previous bldg permission CC PMC/TP/Taloje Majkur/ 105/4, 105/5 & 106/1 / 21-22/16488/2011/2022 conditions are remain same.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 16230.032
Approved no of units |  |  | Flats - 266
Approved no of Floors |  |  | A Wing (Aaradhya) = G + 1st to 17th Floor B Wing (Durva) = G + 1st to 17th Floor
Proposed no of Floors |  |  | A & B Wing = G + 1st to 17th Floor
B Wing = G + 1st to 17th Floor
Expected Completion |  |  | As per RERA - 30/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Landscape Garden, Paved Compound, Gymnasium, Clubhouse, Jogging Track, Mandir, Kids Play Area, Seating Area, Play Area, Badminton Court, Multipurpose Play Area, Gazebo, Swimming Pool etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = G + 1st to 17th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 17 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.25
Excavation |  | 17 | 100% | 12.22% |  | 46.67% |  | Excavation in process | 8.5
Plinth |  | 17 | 100% |  |  |  |  | Excavation Completed | 17
RCC (Including podiums) |  | 1 | 5.556% |  |  |  |  | Footing in Process | 4.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 8.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 17
Construction details: |  | B Wing = G + 1st to 17th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 17 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.25
Excavation |  | 17 | 100% | 14.44% |  | 48.33% |  | Excavation in process | 8.5
Plinth |  | 17 | 100% |  |  |  |  | Excavation Completed | 17
RCC (Including podiums) |  | 2 | 11.11% |  |  |  |  | Footing in Process | 4.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 8.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 17
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  | Rate 5000 by smith verbal on 18/03/2025
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5200 |  |  | 5000 to 5200 by smith on 19/07/2025
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges + Advance Maintenance Charges |  |  |  |  | 150000
Club Charges + Society Formation Charges |  |  |  |  | 150000
Other Charges |  |  |  |  | 80000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 100000
Advance Maintenance Charges |  |  |  |  | 40000
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 4160
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A (Aaradhya) |  | 133 |  | 61169.6377 |  | 102600
Wing B (Durva) |  | 133 |  | 61169.6377 |  | 102600
Total |  | 266 |  | 122339.2753 |  | 205200
Grand Total |  | 266 |  | 122339.2753 |  | 205200
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
45%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Wing A (Aaradhya)
Ground Floor For Parking & Meter Room | [8 empty] | 10.764
1st Floor For Podium Parking & Amenities
2nd Floor For Podium Parking, Society Office & Amenities
3rd to 7th, 9th to 12th & 14th to 16th Floor For Residential
1 |  | 1 | 419.4903 | 0 | 680 | 3rd to 7th, 9th to 12th & 14th to 16th Floor For Residential |  |  | 680 | 1.621
2 |  | 1 | 425.8777 | 0 | 720 |  |  |  | 720 | 1.6906
3 |  | 2 | 602.7571 | 0 | 1015 |  |  |  | 1015 | 1.6839
4 |  | 1 | 415.5442 | 0 | 705 |  |  |  | 705 | 1.6966
5 |  | 1 | 415.5442 | 0 | 705 |  |  |  | 705 | 1.6966
6 |  | 1 | 415.5442 | 0 | 705 |  |  |  | 705 | 1.6966
7 |  | 2 | 602.7571 | 0 | 1015 |  |  |  | 1015 | 1.6839
8 |  | 1 | 425.8777 | 0 | 720 |  |  |  | 720 | 1.6906
9 |  | 1 | 419.4903 | 0 | 680 |  |  |  | 680 | 1.621
8th & 13th Floor (Part Refuge Area)
1 |  | 1 | 419.4903 | 0 | 680 | 8th & 13th Floor (Part Refuge Area)
- |  | Refuge Area
2 |  | 2 | 602.7571 | 0 | 1015
3 |  | 1 | 415.5442 | 0 | 705
4 |  | 1 | 415.5442 | 0 | 705
5 |  | 1 | 415.5442 | 0 | 705
6 |  | 2 | 602.7571 | 0 | 1015
7 |  | 1 | 425.8777 | 0 | 720
8 |  | 1 | 419.4903 | 0 | 680
17th Floor
1 |  | 1 | 419.4903 | 0 | 680 | 17th Floor |  |  | 1.621
2 |  | 1 | 425.8777 | 0 | 720 |  |  |  | 1.6906
3 |  | 1 | 480.9086 | 123.786 | 880 |  |  |  | 1.8299
4 |  | 1 | 415.5442 | 0 | 705 |  |  |  | 1.6966
5 |  | 1 | 415.5442 | 0 | 705 |  |  |  | 1.6966
6 |  | 1 | 415.5442 | 0 | 705 |  |  |  | 1.6966
7 |  | 2 | 602.7571 | 0 | 1015 |  |  |  | 1.6839
8 |  | 1 | 425.8777 | 0 | 720 |  |  |  | 1.6906
9 |  | 1 | 419.4903 | 0 | 680 |  |  |  | 1.621
Wing B (Durva)
Ground Floor For Parking & Meter Room
1st Floor For Podium Parking & Amenities
2nd Floor For Podium Parking, Society Office & Amenities
3rd to 7th, 9th to 12th & 14th to 16th Floor For Residential
1 |  | 1 | 419.4903 | 0 | 680 | 3rd to 7th, 9th to 12th & 14th to 16th Floor For Residential
2 |  | 1 | 425.8777 | 0 | 720
3 |  | 2 | 602.7571 | 0 | 1015
4 |  | 1 | 415.5442 | 0 | 705
5 |  | 1 | 415.5442 | 0 | 705
6 |  | 1 | 415.5442 | 0 | 705
7 |  | 2 | 602.7571 | 0 | 1015
8 |  | 1 | 425.8777 | 0 | 720
9 |  | 1 | 419.4903 | 0 | 680
8th & 13th Floor (Part Refuge Area)
1 |  | 1 | 419.4903 | 0 | 680 | 8th & 13th Floor (Part Refuge Area)
2 |  | 1 | 425.8777 | 0 | 720
3 |  | 2 | 602.7571 | 0 | 1015
4 |  | 1 | 415.5442 | 0 | 705
5 |  | 1 | 415.5442 | 0 | 705
6 |  | 1 | 415.5442 | 0 | 705
7 |  | 2 | 602.7571 | 0 | 1015
- |  | Refuge Area
8 |  | 1 | 419.4903 | 0 | 680
17th Floor
1 |  | 1 | 419.4903 | 0 | 680 | 17th Floor
2 |  | 1 | 425.8777 | 0 | 720
3 |  | 2 | 602.7571 | 0 | 1015
4 |  | 1 | 415.5442 | 0 | 705
5 |  | 1 | 415.5442 | 0 | 705
6 |  | 1 | 415.5442 | 0 | 705
7 |  | 1 | 480.9086 | 123.786 | 880
8 |  | 1 | 425.8777 | 0 | 720
9 |  | 1 | 419.4903 | 0 | 680
Ground Floor
1 |  |  |  | 0 | #REF! | Ground Floor
2 |  |  |  | 0 | #REF! | Ground Floor
3 |  |  |  | 0 | #REF! | Ground Floor
4 |  |  |  | 0 | #REF! | Ground Floor
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
Remarks:
* | Wing A & B = Construction work is in process at the time of visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 18/03/2025 & 19/07/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area. | [9 empty] | Sunil Peravi
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Jijai Tulsi
Layout :
Google Map :
Formulas:
Taloja Majkur = [Taloja Majkur, row above]
Wing A
Wing B
Wing A
Wing A
Wing B
Wing A
Wing A
Wing B
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D57: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted