## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [8 empty] | Sale Plan , EC, Fire NOC & Metro NOC
Valuation Report
Date: |  |  |  | 14/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-10 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Crescent Group | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Crescent Shelters | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Crescent WTC (Western Trade Center) | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Miss. Afrin 9820165155
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Wasim 9321055565 |  |  |  | Miss. Afrin 9820165155
Name / No of the Building As per layout |  |  |  | Building A1
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, EC, Fire NOC & Sale Plan | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA Name & No. |  |  |  | One Crescent (B Building) P51700053224 | [12 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Crescent WTC (Western Trade Center), CTS No (As per appoved CC).4152, 4153, 4351, 4316, 4352, 4354 to 4360, 4404, 4405, 4406, 4452, 4453, near Westin Darvesh Horizon, Penkarpada Road, Penkarpada, Mira, Mira Road East, Thane, Thane - 401107. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No (As per appoved CC) |  | 4152, 4153, 4351, 4316, 4352, 4354 to 4360, 4404, 4405, 4406, 4452, 4453 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Penkarpada | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Penkarpada Road |  | Locality/Village |  | Mira | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Mira Road East |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Thane |  | Pin Code |  | 401107 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Westin Darvesh Horizon |  | Distance from city centre: |  | 3.0 KM from Mira Road Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 60.00M Wide DP Road (National Highway) |  |  | Hotel Ajit Palace/Service Road
West | NA | RG Area |  |  | Open Plot
North | NA | 18.30M Wide Penkarpada Road |  |  | Penkarpada Road
South | NA | Other Plot |  |  | Darvesh Horizon
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.262500,72.873000
Location Link |  | https://maps.app.goo.gl/Nh9JJEnRFC9N6Sqj6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7630.09
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.3682
Total FSI availaible for the project |  |  |  | 3.4682
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 26462.87
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mira-Bhayandar Municipal Corporation | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | MBMCB/7008/2024/APL/0004/AutoDCR |  |  | Dated | 2024-03-19 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | MBMCB/7008/2024/APL/0004/AutoDCR |  |  | Dated | 2024-03-19 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MBMCB/7008/2024/APL/0004/AutoDCR |  |  | Dated | 2024-03-19 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Building A1 =1B + Gr +1st + P2 to P5 + 6th to 23rd Floor + Recreational Floor | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Building A1 =1B + Gr +1st + P2 to P5 + 6th to 23rd Floor + Recreational Floor |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/INFRA2/441658/2023 |  |  | Dated | 2024-02-02 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | C.T.S No.4152, 4153, 4351, 4316, 4352, 4354 to 4360, 4404, 4405, 4406, 4452, 4453 Commercial Building No.1 = 1B + Gr +1st + P2 to P5 + 6th to 22nd Floor + Recreational Floor Proposed BUA - 71431.95 Sq.M | [15 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Fire Noc No Valid Up to: |  | MBMC/FIRE/1981/2023-24 |  |  | Dated | 2024-03-12 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
|  | Building No.1 = 1B + Gr +1st + P2 to P5 + 6th to 22nd Floor + Recreational Floor 93.35Mtrs | [15 empty] | Bhiwandi Nizampur City Municipal Corporation
Airport Noc No Valid Up to: |  | C.T.S No.4152, 4153, 4351, 4316, 4352, 4354 to 4360, 4404, 4405, 4406, 4452, 4453 Commercial Building No.1 = 1B + Gr +1st + P2 to P5 + 6th to 22nd Floor + Recreational Floor Proposed BUA - 71431.95 Sq.M |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved Builtup Area of Building A1 (Sq.Mt) |  |  | 23487.8 |  |  |  |  | 24749.48
Approved no of units |  |  | Offices - 410 |  |  |  |  | Shops -,
Approved no of Floors |  |  | Building A1 =1B + Gr +1st + P2 to P5 + 6th to 23rd Floor + 24th (Recreational Floor)
Proposed no of Floors |  |  | Building A1 =1B + Gr +1st + P2 to P5 + 6th to 23rd Floor + 24th (Recreational Floor)
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | High Speed Elevators, Visitor Management Service, Parking, Grand Sky Atrium, Dedicated Recreational Avenues etc. |  |  |  |  | https://www.crescentwtc.in/
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building A1 =1B + Gr +1st + P2 to P5 + 6th to 23rd Floor + 24th (Recreational Floor) | [5 empty] | Excavation, Plinth Completed, RCC upto 16 Slab, Brickwork upto 6 Floor Completed | , RCC upto 16 Slab, Brickwork upto 6 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 24 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 16 Slab, Brickwork upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 37.48% |  | 65.45% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 16 | 64% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 6 | 25% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. | [16 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 18000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 15000 |  |  |  |  | 11612.9032 | [6 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 500000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 14400 | [12 empty] | 1000000
Commercial Area Details : (Office)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop
Building A1 |  | 410 |  | 170510.1559 |  | 264290.7417 |  | 410
Total |  | 410 |  | 170510.1559 |  | 264290.7417
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Grand Total |  | 410 |  | 170510.1559 |  | 264290.7417
Building details Floor Wise
Details of Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | AP Area | Gross Carpet area | Attached Terrace area | Saleable area Loading : |  |  |  | 10.764
55%
Building A1
Basement Floor For Parking | [7 empty] | 10.764
Ground Floor For Commercial, Entrance Lobby
1 |  | Shop (Duplex) | 144.3913 | 0 | 144.3913 | 0 | 223.8065 |  | 2020.0799
2 |  | Shop (Duplex) | 470.5053 | 0 | 470.5053 | 0 | 729.2832 |  | 1916.3149
3 |  | Shop (Duplex) | 399.984 | 0 | 399.984 | 0 | 619.9752 |  | 1928.8012
4 |  | Shop (Duplex) | 402.548 | 0 | 402.548 | 0 | 623.9494 |  | 2549.884
5 |  | Shop (Duplex) | 465.087 | 0 | 465.087 | 0 | 720.8849 |  | 519.0401 |  | 7.33
6 |  | Shop (Duplex) |  | 0 | 0 | 69.6431 | 107.9468 | 3.98 | 71.2577
1st Floor For Commercial
1 |  | Shop |  | 0 | 0 | 0 | 0 |  | 2251.6135
2 |  | Shop |  | 0 | 0 | 0 | 0 |  | 1929.7699
3 |  | Shop |  | 0 | 0 | 0 | 0 |  | 1927.1866
4 |  | Shop |  | 0 | 0 | 0 | 0 |  | 2738.4692
ST |  | Shop |  | 0 | 0 | 0 | 0 |  | 69.6431
1st Floor (Duplex with Ground Floor)
2nd Floor For Amenity Space & Parking
3rd & 4th For Parking
5th For Parking & Part Refuge Area | [7 empty] | 15
6th to 9th, 11th to 14th, 16th to 19th & 21st to 23rd Floor | [7 empty] | 54.9105
1 |  | Office | 594.711 | 0 | 594.711 | 0 | 921.8021 | 54.9105
2 |  | Office | 631.9544 | 0 | 631.9544 | 0 | 979.5294
3 |  | Office | 339.2813 | 0 | 339.2813 | 0 | 525.886
4 |  | Office | 283.2008 | 0 | 283.2008 | 0 | 438.9613
5 |  | Office | 296.1176 | 0 | 296.1176 | 0 | 458.9823 | 29.7789
6 |  | Office | 309.0344 | 0 | 309.0344 | 0 | 479.0034 |  | 1.275
7 |  | Office | 321.9512 | 0 | 321.9512 | 0 | 499.0244
8 |  | Office | 334.7604 | 0 | 334.7604 | 0 | 518.8786
9 |  | Office | 347.6772 | 0 | 347.6772 | 0 | 538.8997
10 |  | Office | 866.3944 | 0 | 866.3944 | 0 | 1342.9113 | 37.0035
11 |  | Office | 395.8999 | 0 | 395.8999 | 0 | 613.6449 | 35.3835
12 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
13 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
14 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
15 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812 | 42.8505
16 |  | Office | 470.0639 | 0 | 470.0639 | 0 | 728.599
17 |  | Office | 504.9392 | 0 | 504.9392 | 0 | 782.6558
18 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
19 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
20 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927 | 29.3464
21 |  | Office | 315.6005 | 0 | 315.6005 | 0 | 489.1807
22 |  | Office | 333.0382 | 0 | 333.0382 | 0 | 516.2091
23 |  | Office | 596.3256 | 0 | 596.3256 | 0 | 924.3047
10th Floor For Part Refuge Area, Society Office & Drivers Room
1 |  | Society Office & Drivers Room |  |  |  |  | -
2 |  | Refuge Area |  |  |  |  | -
3 |  | Office | 339.2813 | 0 | 339.2813 | 0 | 525.886
4 |  | Office | 283.2008 | 0 | 283.2008 | 0 | 438.9613 | 20502.9463
5 |  | Office | 296.1176 | 0 | 296.1176 | 0 | 458.9823
6 |  | Office | 309.0344 | 0 | 309.0344 | 0 | 479.0034
7 |  | Office | 321.9512 | 0 | 321.9512 | 0 | 499.0244 |  | 14528.3471
8 |  | Office | 334.7604 | 0 | 334.7604 | 0 | 518.8786
9 |  | Office | 347.6772 | 0 | 347.6772 | 0 | 538.8997
10 |  | Office | 866.3944 | 0 | 866.3944 | 0 | 1342.9113
11 |  | Office | 395.8999 | 0 | 395.8999 | 0 | 613.6449
12 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
13 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
14 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
15 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
16 |  | Office | 470.0639 | 0 | 470.0639 | 0 | 728.599
17 |  | Office | 504.9392 | 0 | 504.9392 | 0 | 782.6558
18 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
19 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
20 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
21 |  | Office | 315.6005 | 0 | 315.6005 | 0 | 489.1807
22 |  | Office | 333.0382 | 0 | 333.0382 | 0 | 516.2091
23 |  | Office | 596.3256 | 0 | 596.3256 | 0 | 924.3047
15th & 20th Floor (Part Refuge Area)
1 |  | Office | 467.5882 | 0 | 467.5882 | 0 | 724.7616
2 |  | Refuge Area |  |  |  |  | -
3 |  | Office | 339.2813 | 0 | 339.2813 | 0 | 525.886
4 |  | Office | 283.2008 | 0 | 283.2008 | 0 | 438.9613
5 |  | Office | 296.1176 | 0 | 296.1176 | 0 | 458.9823
6 |  | Office | 309.0344 | 0 | 309.0344 | 0 | 479.0034
7 |  | Office | 321.9512 | 0 | 321.9512 | 0 | 499.0244
8 |  | Office | 334.7604 | 0 | 334.7604 | 0 | 518.8786
9 |  | Office | 347.6772 | 0 | 347.6772 | 0 | 538.8997
10 |  | Office | 866.3944 | 0 | 866.3944 | 0 | 1342.9113
11 |  | Office | 395.8999 | 0 | 395.8999 | 0 | 613.6449
12 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
13 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
14 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
15 |  | Office | 397.7298 | 0 | 397.7298 | 0 | 616.4812
16 |  | Office | 470.0639 | 0 | 470.0639 | 0 | 728.599
17 |  | Office | 504.9392 | 0 | 504.9392 | 0 | 782.6558
18 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
19 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
20 |  | Office | 364.469 | 0 | 364.469 | 0 | 564.927
21 |  | Office | 315.6005 | 0 | 315.6005 | 0 | 489.1807
22 |  | Office | 333.0382 | 0 | 333.0382 | 0 | 516.2091
23 |  | Office | 596.3256 | 0 | 596.3256 | 0 | 924.3047
24th Floor For Recreational Floor
1st Floor For Commercial
1 |  | Shop | 209.18 | 0 | 209.18 | 0 | 324.229
2 |  | Shop | 179.28 | 0 | 179.28 | 0 | 277.884
3 |  | Shop | 179.04 | 0 | 179.04 | 0 | 277.512
4 |  | Shop | 254.41 | 0 | 254.41 | 0 | 394.3355
ST |  | Shop | 6.47 | 0 | 6.47 | 0 | 10.0285
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Ground Floor For Commercial, Entrance Lobby
1st Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) | [6 empty] | Office and shops numbers were not mentioned in approved plan hence we have taken Office numbering from sale plan.
* | Car parking is subjected to authentic documentation.
* | In the approved floor plan shop & office numbering is not mentioned, Therefore we have not drafted area for shops (i.e. Ground floor)
* | We have considered office numbering from the sale plan provided by bank officles, which is attached below.
* | Legal address is not mentioned in the approved plans. we are relesing the report on the bank officers' request by mail.
* | We have considered Survey No from approved CC & RERA site.
* | As per RERA site, in the project Crescent WTC (Western Trade Center) Consists of Building (One Crescent - B Building), But in the approved plan Building A1 & A2 is mentioned. | [6 empty] | We have considered Survey No from RERA with the reference of approved CC, approved plans & Title Certificate.
* | Provide sale plan for Ground Floor.
* | Metro line is passing on the east side of the project.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ranjan Sharma |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Crescent WTC (Western Trade Center)
Layout :
Sale Plan:
Google Map :
Formulas:
Mira = [Mira, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on C61: SACHIN: Height from AMSL
Note on D64: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F96: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H219: SACHIN: Give loading of 50% for A Category
Building A1
Building A2
N
Metro Line
Crescent WTC (Western Trade Center)

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate