## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | Sathe Schemes
Name of the builder company |  |  |  | Sathe Schemes
Name of the Project |  |  |  | Equinox
Provided Contact Details (Name & Contact No.) |  |  |  | 8483990487
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Milind Mokal 7774948881 |  |  |  | Miss.Kalyani : 8149490487
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | NA | [6 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, Sale Plans, Cost Sheet. | [6 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000052525 |  |  |  | #N/A |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Equinox, Plot No.20/1, near Vishal Complex, Internal Rd, Chinchpada, Pen, Pen, Pen, Raigad - 402107. | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 20/1 | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Chinchpada | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Rd |  | Locality/Village |  | Pen |  |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Pen |  | District |  | Raigad |  |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Pen |  | Pin Code |  | 402107 | [7 empty] | Mahad | Daund
Nearby Landmark |  | Vishal Complex |  | Distance from city centre: |  | 750M from Pen Railway Station | [7 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [9 empty] | Mangaon | Ambegaon
[14 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [9 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [9 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [9 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 20M Wide DP Road |  |  | Road
West | NA | ADJ 20/3 Open Space |  |  | Open Plot/K.E.S SCHOOL
North | NA | 9M Wide DP Road |  |  | Internal Rd/ Building
South | NA | ADJ FP On 20/2 |  |  | Shri Vasanti Steel Pen
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.738976,73.090657
Location Link |  | https://maps.app.goo.gl/qZuJEC3onHxuDTfQA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2868.02
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.3041
Total FSI availaible for the project |  |  |  | 3.4041
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 9763.104
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Pen Municipal Council
Layout Approval No |  | PNP/K4/B.V3396BP/310 |  |  | Dated | 2023-04-26
Approved Floor plan No. |  | PNP/K4/B.V3396BP/310 |  |  | Dated | 2023-04-26
Commencement-CC No Valid Up to: |  | PNP/K4/BV/BP/3396/2022-2023/310/2023 |  |  | Dated | 2023-04-26
Gr/Stilt + 1st to 15th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9763.104
Approved no of units |  |  | Flats - 62, Shops - 20, Commercial Unit - 02
Approved no of Floors |  |  | Gr/Stilt + 1st to 15th Floor
Proposed no of Floors |  |  | Gr/Stilt + 1st to 15th Floor
Expected Completion |  |  | As per RERA - 31/05/2030
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Kids Play Area, Gym, Etc..
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/Stilt + 1st to 15th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 7 Floor, Internal Plaster upto 5 Floor, External Plaster upto 1 Floor Completed | , Brickwork upto 7 Floor, Internal Plaster upto 5 Floor, External Plaster upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 7 Floor, Internal Plaster upto 5 Floor, External Plaster upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 56.67% |  | 79.33% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 7 | 46.67% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 33.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 6.667% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | 0 | [5 empty] | #DIV/0!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 0 | #DIV/0! | Work not yet Started.0
Stage of construction: |  | #DIV/0! | [5 empty] | #DIV/0!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0
Excavation |  | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! |  | Excavation in process | 0
Plinth |  | 20 | #DIV/0! |  |  |  |  | Excavation Completed | 0
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0
Brickwork | Brickwork & Internal Plaster | 0 | #DIV/0! |  |  |  |  | Footing Completed | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | #DIV/0! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #DIV/0! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #DIV/0! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #DIV/0! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #DIV/0! |  |  |  |  | Plinth in process | 0
Possession |  | 0 | #DIV/0! |  |  |  |  | Plinth completed | 0
Construction details: |  | 0 | [5 empty] | #DIV/0!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 0 | #DIV/0! | Work not yet Started.
Stage of construction: |  | #DIV/0! | [5 empty] | #DIV/0!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0
Excavation |  | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! |  | Excavation in process | 0
Plinth |  | 0 | #DIV/0! |  |  |  |  | Excavation Completed | 0
RCC (Including podiums) |  | 1 | 100% |  |  |  |  | Footing in Process | 0
Brickwork | Brickwork & Internal Plaster | 0 | #DIV/0! |  |  |  |  | Footing Completed | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | #DIV/0! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #DIV/0! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #DIV/0! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #DIV/0! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #DIV/0! |  |  |  |  | Plinth in process | 0
Possession |  | 0 | #DIV/0! |  |  |  |  | Plinth completed | 0
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4200 |  |  | 5500 to 6000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 9000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 7000
Floor Rise Rate from 6th Floor Per Sq. Ft
Development Charges |  |  |  |  | 100000
Club Charges |  |  |  |  | 100000
Gas Connection Charges
Society Formation + M.S.E.B Charges |  |  |  |  | 50000
Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 3360
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 20 |  | 10877.8831 |  | 16316.8247
Commercial Unit |  | 2 |  | 3129.45 |  | 4694.175
Total |  | 22 |  | 14007.3331 |  | 21010.9997
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 62 |  | 73305.5471 |  | 111116.5729
Total |  | 62 |  | 73305.5471 |  | 111116.5729
Grand Total |  | 84 |  | 87312.8803 |  | 132127.5726
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft Area/ Mezzanine area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Ground Floor For Commercial & Parking | [7 empty] | 10.764
1 |  | Shop | 174.7858 | 87.3929 | 262.1787 | 0 | 393.2681
2 |  | Shop | 351.2724 | 175.6362 | 526.9086 | 0 | 790.3628
3 |  | Shop | 541.2462 | 270.6177 | 811.8639 | 0 | 1217.7959
4 |  | Shop | 545.0997 | 272.5445 | 817.6442 | 0 | 1226.4663
5 |  | Shop | 584.5605 | 292.2749 | 876.8354 | 0 | 1315.2532
6 |  | Shop | 630.1891 | 315.0946 | 945.2837 | 0 | 1417.9256 | 58.1134
7 |  | Shop | 580.5456 | 290.2728 | 870.8184 | 0 | 1306.2275
8 |  | Shop | 401.5941 | 132.5156 | 534.1097 | 0 | 801.1645
9 |  | Shop | 267.4962 | 88.2648 | 355.761 | 0 | 533.6414
10 |  | Shop | 137.2302 | 46.3605 | 183.5908 | 0 | 275.3862
11 |  | Shop | 310.7352 | 102.5379 | 413.273 | 0 | 619.9095
12 |  | Shop | 264.8375 | 87.3929 | 352.2304 | 0 | 528.3456 | 24.5992
13 |  | Shop | 347.548 | 173.774 | 521.322 | 0 | 781.9831 | 32.2901
14 |  | Shop | 313.9321 | 103.5927 | 417.5248 | 0 | 626.2872 | 29.169
15 |  | Shop | 313.9321 | 103.5927 | 417.5248 | 0 | 626.2872
16 |  | Shop | 301.1875 | 99.384 | 400.5715 | 0 | 600.8572
17 |  | Shop | 306.4403 | 101.117 | 407.5573 | 0 | 611.336
18 |  | Shop | 334.9219 | 167.4555 | 502.3774 | 0 | 753.5661
19 |  | Shop | 420.8401 | 210.4147 | 631.2548 | 0 | 946.8822
20 |  | Shop | 419.5054 | 209.7473 | 629.2527 | 0 | 943.879
1st Floor + 2nd Floor((Mezzanine Floor) For Commercial Units & Parking | [7 empty] | 10.764
1 |  | Unit Duplex With Mezzanine Floor | 1156.1289 | 432.7128 | 1588.8417 | 0 | 2383.2626
2 |  | Unit Duplex With Mezzanine Floor | 1111.2323 | 429.376 | 1540.6083 | 0 | 2310.9124
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
3rd Floor For Residential & Amenities | [8 empty] | 10.764
1 |  | Driver Rest Room/Indoore Game Hall/Gymnasium |  |  |  |  | 0
2 |  | 3BHK | 1008.393 | 61.1126 | 1069.5057 | 1293.4291 | 1927.6158 | 87.302 | 93.682 | 6.38
3 |  | 3BHK | 1039.2857 | 93.2432 | 1132.5289 | 51.8179 | 1750.6112
4 |  | 2BHK | 620.1571 | 61.893 | 682.0501 | 126.3263 | 1086.2383 | 57.665
5 |  | 3BHK | 1041.4601 | 60.2784 | 1101.7385 | 1283.2841 | 1973.4287
6 |  | Screening Room/Society Office |  |  |  |  | 0
4th Floor | [8 empty] | 4200
1 |  | 3BHK | 805.9868 | 152.5958 | 958.5826 | 0 | 1437.874 |  | 6039070.6194 | 4482.7586
2 |  | 3BHK | 1022.6446 | 187.003 | 1209.6476 | 0 | 1814.4713 |  | 7620779.6028
3 |  | 3BHK | 1039.2857 | 145.061 | 1184.3468 | 0 | 1776.5202 | 4.814 | 7461384.6762
4 |  | 2BHK | 620.1571 | 213.7031 | 833.8602 | 0 | 1250.7903 |  | 5253319.071
5 |  | 2BHK | 788.8182 | 273.9976 | 1062.8158 | 0 | 1594.2237 |  | 6695739.7416
5th Floor
1 |  | 3BHK | 805.9868 | 152.5958 | 958.5826 | 0 | 1437.874
2 |  | 3BHK | 1022.6446 | 187.003 | 1209.6476 | 0 | 1814.4713
3 |  | 3BHK | 1039.2857 | 145.061 | 1184.3468 | 0 | 1776.5202
4 |  | 2BHK | 620.1571 | 213.7031 | 833.8602 | 0 | 1250.7903
5 |  | 2BHK | 788.8182 | 273.9976 | 1062.8158 | 0 | 1594.2237
6th, 7th, 9th to 12th, & 14th Floor
1 |  | 3BHK | 805.9868 | 127.9732 | 933.96 | 0 | 1400.94
2 |  | 3BHK | 1022.6446 | 187.003 | 1209.6476 | 0 | 1814.4713
3 |  | 3BHK | 1039.2857 | 145.061 | 1184.3468 | 0 | 1776.5202
4 |  | 3BHK | 1493.8064 | 490.3755 | 1984.1819 | 0 | 2976.2729
5 |  | 2BHK | 573.7212 | 182.2776 | 755.9988 | 0 | 1133.9982
8th & 13th Floor(Part Refuge Area)
1 |  | 3BHK | 805.9868 | 127.9732 | 933.96 | 0 | 1400.94
2 |  | 3BHK | 1022.6446 | 187.003 | 1209.6476 | 0 | 1814.4713
3 |  | 2BHK | 870.2048 | 120.4384 | 990.6432 | 0 | 1485.9648
4 |  | 3BHK | 1493.8064 | 490.3755 | 1984.1819 | 0 | 2976.2729
5 |  | 2BHK | 573.7212 | 182.2776 | 755.9988 | 0 | 1133.9982
15th Floor
1 |  | 3BHK | 1561.3505 | 208.0412 | 1769.3917 | 367.1062 | 2745.8641
2 |  | 3BHK | 962.1832 | 93.2432 | 1055.4263 | 119.7172 | 1642.9981
3 |  | 3BHK | 1558.1643 | 212.4275 | 1770.5919 | 989.8305 | 2903.3455
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Weather Shed Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh Patil |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Equinox
Layout :
Google Map :
Formulas:
Pen = [Pen, row above]
N
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC