## Table 1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  | 13/07/2025
CPC Name: |  |  | Axis Goregaon
Date Of Property Visit |  |  | 2025-07-08
Name of the builder group |  |  | M/s.Nano Homes
Name of the builder company |  |  | M/s.Nano Homes
Name of the Project |  |  | Pavan Vihar Complex Building No. 2
Contact Details ( Name & Contact No.) |  |  | NA
Name / No of the Building |  |  | Wing A, B, C & D
Docouments Provided |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  | P99000007247
Project location details |  | Pavan Vihar Complex Building No. 2, GUT no.19/A & 20, H no.1, 3 & 4, Boisar Road,Nagzari, Palghar
GUT no |  | 19/A & 20 | H no | 1, 3 & 4 | Locality | Nagzari
Road | Boisar Road |  | District | Palghar
City | Palghar |  | Pin Code | 401501
Near by Landmark |  | Bharat Petroleum petrol pump | Distance from city centre: |  | 21 Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  | Yes
Class of locality |  |  | Middle Class
Nature of land with topographical condtion |  |  | Plane
Nature of the locality |  |  | Developing
Quality of infrastructure in vicinity |  |  | Good
Boundaries |  | East | West | South |  | North
As per deed |  | NA | NA | NA |  | NA
At site |  | Open Area | Bharat Petroleum petrol pump | Open Area |  | Boisar Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.782919, 72.85202
Location Link |  | https://goo.gl/maps/CHtgX9a5ZW8EvGqf9?coh=178572&entry=tt
Approval details:
Approved usage of the Property: |  |  | Commercial & Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  | 12381
Permissible FSI |  |  | 0.9
Permissible TDR/Paid FSI |  |  | 0.2
Total FSI availaible for the project |  |  | 1.1
Total Approved Builtup area of the project in Sq. Mt. |  |  | 13571.5
Total number of Buildings |  |  | 01 Building (04 wings)
Approval Detail : Plan approval
Layout Approval No | SD/BP/M.NAGZARI/T.PALGHAR/G.K.19/ NR-PALGHAR/119 |  |  | Dated | 06/02/2016.
Approved Floor plan No. | SD/BP/M.NAGZARI/T.PALGHAR/G.K.19/ NR-PALGHAR/119 |  |  | Dated | 06/02/2016.
Commencement Certificate No. | SD/BP/M.NAGZARI/T.PALGHAR/G.K.19/ NR-PALGHAR/119 Valid Up to: G + 4th Floor |  |  | Dated | 06/02/2016.
O. Certificate No.: | NA |  |  | Dated | NA
Commencement date of construction |  | 06/02/2016. | Expected Completion |  | 30/04/2022.
Building wise Construction details
Approved area of the building in Sq.Mt |  | 13571.48 | Approved no of units |  | Flats = 68 Shop = 19
Approved no of Floors | G + 4th Floor (4 wings-A,B,C,D) |  | No of floors at site : See Construction details
Quality of construction: Good |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Wing A to D = G + 1st to 4th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Floors |  | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 93.75% |  | 96.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% |  |  |  |  | Plinth in process | 3
Possession |  | 1 | 25% |  |  |  |  | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : | : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  | 2800
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) |  |  |  | 4500
Club House Charges |  |  |  | 50000/-
Maintainance |  |  |  | 9840/-
Society charges |  |  |  | 50000/-
Recommended rate of Parking |  |  |  | 100000/-
Development charges Per Sq. Ft. |  |  |  | NA
Distressed valuation of the Property |  |  |  | 2240
Building details Floor Wise
Details of Flats in Building
Unit No. As per Approved Plan | Unit No. As per Builder Area Sheet | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No. 2
A-Wing (Type -C1b)
Ground Floor is For Parking & Residential
1 |  | 1RK | 210 | 0 | 345 | Ground Floor
2 |  | 1RK | 263 | 0 | 430
3 |  | 1RK | 210 | 0 | 345
1st To 4th Floor
1 |  | 1RK | 245 | 0 | 400 | 1st To 4th Floor |  | 3250
2 |  | 1RK | 297 | 0 | 490
3 |  | 1BHK | 369 | 0 | 605
4 |  | 1RK | 245 | 0 | 400 |  |  | 1818.1818
B-Wing (Type -A1)
Ground Floor is For
1 |  | Shop | 99 | 0 | 230 | Ground Floor
2 |  | Shop | 119 | 0 | 270
3 |  | Shop | 81 | 0 | 190 |  |  | 348
4 |  | Shop | 101 | 0 | 230 |  |  | 3735.6322
5 |  | Shop | 142 | 0 | 330
6 |  | Shop | 115 | 0 | 265
7 |  | M.P Room | 162 | 0 | 260
1st To 4th Floor
1 |  | 1RK | 247 | 0 | 430 | 1st To 4th Floor
2 |  | 1RK | 250 | 0 | 435
3 |  | 1RK | 316 | 0 | 550
4 |  | 1RK | 299 | 0 | 520
C-Wing (Type -A1a)
Ground Floor is For Commercial & parking
1 | 7 | Shop | 115 | 0 | 265 | Ground Floor
2 | 8 | Shop | 142 | 0 | 325
3 | 9 | Shop | 100 | 0 | 230
4 | 10 | Shop | 82 | 0 | 190
5 | 11 | Shop | 67 | 0 | 155
6 | 12 | Shop | 67 | 0 | 155
7 | 13 | Shop | 128 | 0 | 290
8 | 14 | Shop | 90 | 0 | 205
9 | 15 | Shop | 110 | 0 | 250
1st To 4th Floor
1 |  | 1RK | 299 | 0 | 520 | 1st To 4th Floor
2 |  | 1RK | 316 | 0 | 550
3 |  | 1RK | 250 | 0 | 435
4 |  | 1RK | 247 | 0 | 430
D-Wing (Type -C1a)
Ground Floor is For Commercial & parking
1 | 16 | Shop | 111 | 0 | 275 | Ground Floor
2 | 17 | Shop | 135 | 0 | 330
3 | 18 | Shop | 135 | 0 | 330
4 | 19 | Shop | 89 | 0 | 220
1st To 4th Floor
1 |  | 1RK | 210 | 0 | 445 | 1st To 4th Floor
2 |  | 1BHK | 303 | 0 | 670
3 |  | 1RK | 263 | 0 | 540
4 |  | 1RK | 210 | 0 | 445 |  | 1689.8876
Remarks: 1. Wing A to D = Lift work is pending. Some tenants have occupied the flats. 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. Car parking is subjected to authentic documentation. 7. As per RERA, completion period of project Pavan Vihar Complex Building No. 2 is expired on 30/04/2022 but still project work is pending. 8.As checked on RERA portal on date 13/07/2025, we have observed that above project " Pavan Vihar Complex Building No. 2 " is kept under abeyance. Please check from your end. 7. On Site, we meet Mr.Bijay - 7366808163.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pavan Vihar Complex Building No. 2
Google Map :
Wing A
Wing B
Wing C
Wing D
Wing A
Wing B
Wing C
Wing D
Wing D

## A%
|  |  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | total floor | 4 |  | 15 | 0 | 0 | 1 | 14
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 4 | 100% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 85% | 90% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B
|  |  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | total floor | 4 |  | 15 | 0 | 0 | 1 | 14
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 2 | 50% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 5 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 2.5 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 5 | 2.5
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 80% | 87.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C,D
|  |  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | total floor | 4 |  | 15 | 0 | 0 | 1 | 14
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0.5 | 12.5% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 1.25 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0.625 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 1.25 | 0.625
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 76.25% | 85.62% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%