## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | Adityaraj Builders & Promoters
Name of the builder company |  |  |  | Adityaraj Builders & Promoters
Name of the Project |  |  |  | Adishakti Chs Adityaraj Prime
Provided Contact Details ( Name & Contact No.) |  |  |  | Miss. Charudalta (9619888991)
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr Narshi Bhimane 9925485818 |  |  |  | Mr Narshi Bhimane 9925485818
Name / No of the Building |  |  |  | Adityaraj Prime
Name / No of the Existing Building |  |  |  | Building No. 81/Adishakti CHS.
Documents Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51800045695
Project location details |  | Adishakti Chs Adityaraj Prime, CTS No.356 (Pt), Existing Building Name - Adishakti CHS & No. 81, near 394 last busstop kannamwar nagar, Road No.1, Kannamwar Nagar, Hariyali, Vikhroli (East), Kurla, Mumbai - 400083.
CTS No |  | 356 (Pt), Existing Building Name - Adishakti CHS & No. 81
Locality |  | Kannamwar Nagar
Road |  | Road No.1 |  | Locality/Village |  | Hariyali
City |  | Vikhroli (East) |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400083
Nearby Landmark |  | 394 last busstop kannamwar nagar |  | Distance from city centre: |  | 1.9KM from Vikhroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot/ Uc Building
West | NA | NA |  |  | Bus Stop/Road No.1
North | NA | NA |  |  | Road No.1
South | NA | NA |  |  | Asmita College
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1204 |  | Longitude |  | 72.9386
Location Link |  | https://goo.gl/maps/Wzg3Wo7ko5dJKHPR9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1026.94
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 2.1685
Total FSI availaible for the project |  |  |  | 5.1685
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5307.78
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority. (MHADA)
Layout Approval No |  | MHADA-9/1069/2023 |  |  | Dated | 2023-07-17
Approved Floor plan No. |  | MHADA-9/1069/2023 |  |  | Dated | 2023-07-17
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-9/1069/2023/FCC/2/Amend |  |  | Dated | 2023-10-16
|  | This C.C. is further extended upto top of 22nd floor i.e. building comprising of Ground (pt) + Stilt (pt) + 1st part for office and part for residential + 2nd to 22nd upper floors (including O.H.T + L.M.R.) along with parking tower as per approved amended plan dtd. 17.07.2023. |  |  | Valid Upto Date | 2024-05-25
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5307.78
Approved no of units |  |  | Flats - 143, Shops - 06, Offices - 03
Approved no of Floors |  |  | Gr + 1st to 22nd Floor
Proposed no of Floors |  |  | Gr + 1st to 22nd Floor
B Wing = G + 1st to 20th Floor
C Wing = G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/03/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 21 Floor, Flooring upto 15 Floor, Painting upto 7 Floor Completed | , External Plaster upto 21 Floor, Flooring upto 15 Floor, Painting upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 21 Floor, Flooring upto 15 Floor, Painting upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 82.95% |  | 93.18% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11 |  | 20.02
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0 |  | 15.87
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 95.45% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 68.18% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 31.82% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | B Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 11500 |  |  |  | 11000 to 11300 | 2023-03-28 | Sanket | Verbal
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 23000 |  |  |  | 11500 | 2023-03-29
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 17000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 600000 |  |  | https://www.magicbricks.com/office-space-for-sale-in-kannamwar-nagar-mumbai-pppfs
Distressed valuation of the Property |  |  |  |  | 9200 |  |  | https://www.magicbricks.com/shops-for-sale-in-vikhroli-east-mumbai-pppfs
Commercial Area Details : | [7 empty] | https://housing.com/in/buy/projects/page/282475-chs-adityaraj-prime-by-adityaraj-group-in-vikhroli-east
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | https://www.magicbricks.com/adishakti-chs-adityaraj-prime-vikhroli-east-mumbai-pdpid-4d4235333630353435
Shop |  | 6 |  | 1821.9227 |  | 2915.0763 |  |  | Cost Sheet | Sheet | Magic Brick | Housing
Office |  | 3 |  | 2764.3838 |  | 4423.0141 |  |  | 19500 | 12903.2258 | 13610.1363 | 12214.2249
Total |  | 9 |  | 4586.3065 |  | 7338.0905 |  |  |  |  | 11948.6505 | 10942.4483
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 143 |  | 60022.304 |  | 93034.5711
Total
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor |  |  |  | Shop | Office
[5 empty] | 60% |  |  |  | 10.764 | 25757.2314 | 15468.7098
Ground Floor For Commercial & Society Office | [9 empty] | 20844.0299 | 15827.9782
1 |  | Shop | 466.1404 | 0 | 745.8246 | Ground Floor For Commercial & Society Office |  |  |  | 23300.6307 | 15648.344
2 |  | Shop | 184.4142 | 0 | 295.0628
3 |  | Shop | 293.8491 | 0 | 470.1586
4 |  | Shop | 245.2846 | 0 | 392.4554
5 |  | Shop | 272.4584 | 0 | 435.9334
6 |  | Shop | 359.7759 | 0 | 575.6415
1st Floor For Commercial & Residential
1 |  | Office | 853.4151 | 0 | 1365.4642 | 1st Floor For Commercial & Residential
2 |  | Office | 686.8705 | 0 | 1098.9928 |  |  | 2.42 | 2.4
3 |  | Office | 1224.0982 | 0 | 1958.5572
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
1st Floor For Commercial & Residential
6 |  | 1BHK | 370.2441 | 0 | 573.8784 | 1st Floor For Commercial & Residential |  | 7173480.4062 | 6312662.7575
7 |  | 1BHK | 369.7434 | 0 | 573.1023 |  |  | 7163778.375 | 6304124.97
2nd to 6th, 8th to 13th, 15th to 20th & 22nd Floor | [7 empty] | 0 | 0
1 |  | 2BHK | 512.9477 | 0 | 795.0689 | 2nd to 6th, 8th to 13th, 15th to 20th & 22nd Floor |  | 9938360.835 | 8745757.5348
2 |  | 1BHK | 383.333 | 0 | 594.1661 |  |  | 7427075.9063 | 6535826.7975 |  | 13480.4805
3 |  | 1BHK | 412.693 | 0 | 639.6741 |  |  | 7995926.4875 | 7036415.309
4 |  | 2BHK | 509.6388 | 0 | 789.9401 |  |  | 9874251.7965 | 8689341.5809
5 |  | 1BHK | 378.0855 | 0 | 586.0325 |  |  | 7325406.5625 | 6446357.775
6 |  | 1BHK | 370.2441 | 0 | 573.8784 |  |  | 7173480.4062 | 6312662.7575
7 |  | 1BHK | 369.7434 | 0 | 573.1023 |  |  | 7163778.375 | 6304124.97
7th & 14th Floor (Part Refuge Area)
1 |  | 2BHK | 512.9477 | 0 | 795.0689 | 7th & 14th Floor (Part Refuge Area)
2 |  | Refuge Area
3
4 |  | 2BHK | 509.6388 | 0 | 789.9401
5 |  | 1BHK | 378.0855 | 0 | 586.0325
6 |  | 1BHK | 370.2441 | 0 | 573.8784
7 |  | 1BHK | 369.7434 | 0 | 573.1023
21st Floor (Part Refuge Area & Fitness Center)
1 |  | 2BHK | 512.9477 | 0 | 795.0689 | 21st Floor (Part Refuge Area & Fitness Center)
2 |  | Refuge Area
3 |  | Fitness Center
4 |  | 2BHK | 509.6388 | 0 | 789.9401
5 |  | 1BHK | 378.0855 | 0 | 586.0325
6 |  | 1BHK | 370.2441 | 0 | 573.8784
7 |  | 1BHK | 369.7434 | 0 | 573.1023
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved floor plan & C.C (on 07/08/2023).
* | We have updated latest CC (On 20/10/2023).
* | Validity of CC is expired on 25/05/2024. Please provide latest approved CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Akash |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Adishakti Chs Adityaraj Prime
Layout :
Google Map :
Formulas:
Hariyali = [Hariyali, row above]
N
Adityaraj Prime

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted