## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | M/s. Runwal Residency Private Limited
Name of the builder company |  |  |  | M/s. Runwal Residency Private Limited
Name of the Project |  |  |  | Runwal Gardens Phase VIII
Contact Details ( Name & Contact No.) |  |  |  | Mr. Subhas -983540059/Mr. Kunal -99673393445
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Ankit 9137940152
Name / No of the Building |  |  |  | Phase 8 = Building No. 43, 44 & 45
Documents Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | Runwal Gardens - Phase 8 - Bldg No. 44 = P51700047512 Runwal Gardens Phase 8 Bldg No. 43 and 45 = P51700052441 |  |  |  | Building No. 43 & 45 is drafted & hide in yes bank apf file
Project location details |  | Runwal Gardens Phase VIII, Survey No.Runwal Gardens Phase 8 Bldg No. 44 Survey No.4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/9, 4/10, 4/11, 5/1, 5/2, 5/3, 5/4, 5/5, 5/6, 6/1, 6/2, 6/3, 7/1, 7/2A, 7/2B, 7/2C, 7/3A, 7/3B, 8/1, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7, 8/8, 8/9, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 10, 11, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10, 12/11, 12/12, 12/13, 12/14, 13, 14/1, 14/2A, 14/2B, 14/3, 14/4, 14/5, 15, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 17/10, 17/11, 18, 19, 22, 23/1, 23/2, 23/3, 23/10, 37/1, 37/2B, 37/2C, 37/2D, 37/3, 37/4, 37/21, 38/1, 38/2, 39/1, 39/2, 39/3, 40, 41/1A, 41/1B, 41/2, 41/3, 41/4, 44/1, 44/4,44/5A, 44/5B, 44/6A, 44/6B, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 44/13, 44/14, 44/15, 44/16, 44/17, 44/18, 44/19, 49, 50/1, 50/2, 50/3 at Village Gharivali Dist Thane and S. Nos. 44/1, 44/2, 44/3, 44/4, 44/5, 44/6, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/4, 45/5A, 45/5/B, 45/6, 46/1/2, 46/2A, 46/2B, 46/3, 47/2, 49, 50, 51, 52/1, 52/2, 53/1A, 53/1/B, 53/2/A, 53/2/B, 53/3/A, 53/3/B, 94/2, near Premiere colony ground, Kalyan - Shilphata Road, Usarghar, Nilaje, Kalyan, Thane - 421201.
Survey No |  | Runwal Gardens Phase 8 Bldg No. 44 Survey No.4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/9, 4/10, 4/11, 5/1, 5/2, 5/3, 5/4, 5/5, 5/6, 6/1, 6/2, 6/3, 7/1, 7/2A, 7/2B, 7/2C, 7/3A, 7/3B, 8/1, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7, 8/8, 8/9, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 10, 11, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10, 12/11, 12/12, 12/13, 12/14, 13, 14/1, 14/2A, 14/2B, 14/3, 14/4, 14/5, 15, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 17/10, 17/11, 18, 19, 22, 23/1, 23/2, 23/3, 23/10, 37/1, 37/2B, 37/2C, 37/2D, 37/3, 37/4, 37/21, 38/1, 38/2, 39/1, 39/2, 39/3, 40, 41/1A, 41/1B, 41/2, 41/3, 41/4, 44/1, 44/4,44/5A, 44/5B, 44/6A, 44/6B, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 44/13, 44/14, 44/15, 44/16, 44/17, 44/18, 44/19, 49, 50/1, 50/2, 50/3 at Village Gharivali Dist Thane and S. Nos. 44/1, 44/2, 44/3, 44/4, 44/5, 44/6, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/4, 45/5A, 45/5/B, 45/6, 46/1/2, 46/2A, 46/2B, 46/3, 47/2, 49, 50, 51, 52/1, 52/2, 53/1A, 53/1/B, 53/2/A, 53/2/B, 53/3/A, 53/3/B, 94/2
Road |  | Kalyan - Shilphata Road |  | Locality/Village |  | Usarghar
City |  | Nilaje |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Nearby Landmark |  | Premiere colony ground |  | Distance from city centre: |  | 4.1Km from Nilaje Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | 30.00 M. Wide Road |  |  | Kalyan Shilphata Road
West | NA | Other Plot |  |  | Runwal Residency
North | NA | Other Plot |  |  | Open Plot/Diva Manpada Road
South | NA | 24.00 M. Wide Road |  |  | Usarghar Betwade Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.184020,73.087538
Location Link |  | https://maps.app.goo.gl/aWG8h5GVAV1Gcvnq9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 533750
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.686
Total FSI availaible for the project |  |  |  | 1.686
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 899902.5
Total number of Buildings |  |  |  | 03 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mumbai Metropolitan Region Development Authority (MMRDA)
Layout Approval No. (Bldg No. 44) |  | SROT/Growth Center/2401/BP/ITP Usarghar-Gharivali-Sagaon 01/Site-A/Amended Layout & CC Phase 8/Vol-35/1332/2022 |  |  | Dated | 2022-10-17
Approved Floor plan No. |  | SROT/Growth Center/2401/BP/ITP Usarghar-Gharivali-Sagaon 01/Site-A/Amended Layout & CC Phase 8/Vol-35/1332/2022 |  |  | Dated | 2022-10-17
Commencement Certificate No. Valid Up to: |  | SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-01/Site-A/Amended Layout & CC Phase-8/Vol-35/1332/2022 |  |  | Dated | 2022-10-17
Building No. 43, 44 & 45 = Ground Podium + 1st to 6th Podium + Club House at 7th Podium floor + 8th floor + 9th to 36th floor (Residential floors)
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 234315.79
Approved no of units |  |  | Flats - 417
Approved no of Floors |  |  | Building No. 43, 44 & 45 = Gr + 1st to 36th Floor
Proposed no of Floors |  |  | Building No. 44 = Gr + 1st to 36th Floor
Building No. 43 = Gr + 1st to 36th Floor
Building No. 45 = Gr + 1st to 36th Floor
Expected Completion |  |  | As per RERA - 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 43 = Gr + 1st to 36th Floor Building No. 44 = Gr + 1st to 36th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 8 Slab Completed, Brickwork upto 7 Floor Completed, Internal Plaster upto 5.25 Floor Completed, External Plaster upto 4.55 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 36
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab Completed, Brickwork upto 7 Floor Completed, Internal Plaster upto 5.25 Floor Completed, External Plaster upto 4.55 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9
Excavation |  | 36 | 100% | 22.46% |  | 53.82% |  | Excavation in process | 18
Plinth |  | 36 | 100% |  |  |  |  | Excavation Completed | 36
RCC (Including podiums) |  | 8 | 21.62% |  |  |  |  | Footing in Process | 9
Brickwork | Brickwork & Internal Plaster | 7 | 19.44% |  |  |  |  | Footing Completed | 18
Internal Plaster | Brickwork & Internal Plaster | 5.25 | 14.58% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4.55 | 12.64% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 27
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 36
Construction details: |  | Building No. 44 = Gr + 1st to 36th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed, Brickwork upto 6 Floor Completed, Internal Plaster upto 4.5 Floor Completed, External Plaster upto 3.9 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 36
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed, Brickwork upto 6 Floor Completed, Internal Plaster upto 4.5 Floor Completed, External Plaster upto 3.9 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9
Excavation |  | 36 | 100% | 20.84% |  | 52.68% |  | Excavation in process | 18
Plinth |  | 36 | 100% |  |  |  |  | Excavation Completed | 36
RCC (Including podiums) |  | 7 | 18.92% |  |  |  |  | Footing in Process | 9
Brickwork | Brickwork & Internal Plaster | 6 | 16.67% |  |  |  |  | Footing Completed | 18
Internal Plaster | Brickwork & Internal Plaster | 4.5 | 12.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.9 | 10.83% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 27
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 36
Construction details: |  | Building No. 45 = Gr + 1st to 36th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 36
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9
Excavation |  | 36 | 100% | 14.32% |  | 48.24% |  | Excavation in process | 18
Plinth |  | 36 | 100% |  |  |  |  | Excavation Completed | 36
RCC (Including podiums) |  | 4 | 10.81% |  |  |  |  | Footing in Process | 9
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 18
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 27
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 36
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 8250 |  |  | 7500 to 7600 | 2024-05-03 | viraj
Recommended rate of the shop Per Sq. Ft. (on Saleable area)
Recommended rate of the Office Per Sq. Ft. (on Saleable area)
Floor Rise Rate Per Sq.ft
Development Charges
Other Charges |  |  |  |  | 500000 |  |  | OC n Building 45 2503 area changed by Smith on 16/07/2024
Legal Services Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000 |  |  | Rate 7600 to 8250 Bhargav building 44 Flat 701 index 2 19/12/2024
Distressed valuation of the Property |  |  |  |  | 6600
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 43
Building No. 44 |  | 118 |  | 142329.0675 |  | 227726.5079
Building No. 43 |  | 191 |  | 139058.2108 |  | 222493.1372
Building No. 45 |  | 108 |  | 123580.1385 |  | 197728.2216
Total |  | 417 |  | 404967.4167 |  | 647947.8668
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Phase 8
Building No.44
1st Podium Floor For Society Office, Fire Lobby, Children Play Room, Driver Room & Podium Parking
2nd Podium Floor For Residential, Fire Lobby & Podium Parking
1 |  | 3BHK | 1199.6343 | 0 | 1919.415 | 2nd Podium Floor For Residential, Fire Lobby & Podium Parking
2 |  | Parking
3
4 |  | 4BHK | 1454.2245 | 0 | 2326.7592
3rd to 6th Podium Floor
1 |  | 3BHK | 1199.6343 | 0 | 1919.415 | 3rd to 6th Podium Floor
2 |  | Parking
3
4 |  | 4BHK | 1454.2245 | 0 | 2326.7592
7th Podium Floor For Residential & Amenities
1 |  | 3BHK | 1199.6343 | 0 | 1919.415 | 7th Podium Floor For Residential & Amenities
2 |  | Amenities
3
4
8th Podium Floor For Residential (Part Refuge Area)
1 |  | 3BHK | 1199.6343 | 0 | 1919.415 | 8th Podium Floor For Residential (Part Refuge Area)
2 |  | Amenities Below
3
4
9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th, 30th Floor
1 |  | 3BHK | 1199.6343 | 0 | 1919.415 | 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th, 30th Floor
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 4BHK | 1454.2245 | 0 | 2326.7592
13th 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 3BHK | 1199.6343 | 0 | 1919.415 | 13th 18th, 23rd & 28th Floor (Part Refuge Area)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 4BHK | 1454.2245 | 0 | 2326.7592
31st Floor (Lower Duplex)
1 |  | 4BHK (Duplex With 32nd Floor) | 1962.5194 | 0 | 3140.031 | 31st Floor (Lower Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 6BHK (Duplex With 32nd Floor) | 2498.3083 | 0 | 3997.2932
32nd Floor (Upper Duplex)
1 |  | Duplex With 31st Floor |  |  |  | 32nd Floor (Upper Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | Duplex With 31st Floor
33rd Floor (Lower Duplex) (Part Refuge Area)
1 |  | 4BHK (Duplex With 34th Floor) | 1962.5194 | 0 | 3140.031 | 33rd Floor (Lower Duplex) (Part Refuge Area)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 6BHK (Duplex With 34th Floor) | 2498.3083 | 0 | 3997.2932
34th Floor (Upper Duplex)
1 |  | Duplex With 33rd Floor |  |  |  | 34th Floor (Upper Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | Duplex With 33rd Floor
35th Floor (Lower Duplex)
1 |  | 4BHK (Duplex With 36th Floor) | 1962.5194 | 0 | 3140.031 | 35th Floor (Lower Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 6BHK (Duplex With 36th Floor) | 2498.3083 | 0 | 3997.2932
36th Floor (Upper Duplex)
1 |  | Duplex With 35th Floor |  |  |  | 36th Floor (Upper Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | Duplex With 35th Floor
Building No.43
Ground Floor for Meter Room, Garbage Room, Electric/Pannel Room, Letter Box Room, Society Office & Parking
1st Podium Floor For Residential, Fire Lobby & Podium Parking
1 |  | Parking |  |  |  | 1st Podium Floor For Residential, Fire Lobby & Podium Parking
2 |  | 2BHK | 679.4035 | 0 | 1087.0456 |  |  |  | 60.6184
3 |  | 3BHK | 813.3413 | 0 | 1301.3461
4 |  | Double Height Entrance Lobby
5 |  | Parking
6
2nd to 6th Podium Floor
1 |  | Parking |  |  |  | 2nd to 6th Podium Floor
2 |  | 2BHK | 679.4035 | 0 | 1087.0456
3 |  | 3BHK | 813.3413 | 0 | 1301.3461
4 |  | 2BHK | 697.0874 | 0 | 1115.3398
5 |  | Parking
6
7th Podium Floor For Residential & Amenities
1 |  | Club House |  |  |  | 7th Podium Floor For Residential & Amenities
2 |  | 2BHK | 679.4035 | 0 | 1087.0456
3 |  | 3BHK | 813.3413 | 0 | 1301.3461
4 |  | 2BHK | 697.0874 | 0 | 1115.3398
5 |  | Double Height Entrance Lobby
6 |  | Club House
8th Podium Floor For Residential (Part Refuge Area)
1 |  | Club House Below |  |  |  | 8th Podium Floor For Residential (Part Refuge Area)
2 |  | 2BHK | 679.4035 | 0 | 1087.0456
3 |  | 3BHK | 813.3413 | 0 | 1301.3461
4 |  | 1BHK | 497.3076 | 0 | 795.6921
5 |  | Double Height Entrance Lobby Below
6 |  | Club House Below
9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd & 34th to 36th Floor
1 |  | 2BHK | 698.9173 | 0 | 1118.2677 | 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd & 34th to 36th Floor
2 |  | 2BHK | 679.4035 | 0 | 1087.0456
3 |  | 3BHK | 813.3413 | 0 | 1301.3461
4 |  | 2BHK | 697.0874 | 0 | 1115.3398
5 |  | 3BHK | 810.8656 | 0 | 1297.3849
6 |  | 2BHK | 708.7892 | 0 | 1134.0627
13th 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
1 |  | 2BHK | 698.9173 | 0 | 1118.2677 | 13th 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
2 |  | 2BHK | 679.4035 | 0 | 1087.0456
3 |  | 3BHK | 813.3413 | 0 | 1301.3461
4 |  | 1BHK | 497.3076 | 0 | 795.6921
5 |  | 3BHK | 810.8656 | 0 | 1297.3849
6 |  | 2BHK | 708.7892 | 0 | 1134.0627
Building No. 45
Ground Floor for Entrance Lobby, Meter Room, Garbage Room, Electric/Pannel Room & Parking
1st Floor For Society Office, Fire Lobby, Creche Area, Driver Room, Fitness centre & Podium Parking
2nd to 6th Podium Floor For Fire Lobby & Podium Parking
7th Podium Floor For Amenities Double Height
8th Podium Floor (Part Refuge Area)
9th to 12th, 14th to 17th, 19th to 22nd, 24th, 26th, 27th, 29th to 30th & 34th Floor
1 |  | 3BHK | 1164.8801 | 0 | 1863.8081 | 9th to 12th, 14th to 17th, 19th to 22nd, 24th, 26th, 27th, 29th to 30th & 34th Floor
2 |  | 3BHK | 958.4266 | 0 | 1533.4825
3 |  | 3BHK | 961.5481 | 0 | 1538.477
4 |  | 4BHK | 1415.1431 | 0 | 2264.2289
25th Floor
1 |  | 3BHK | 1164.8801 | 0 | 1863.8081 | 25th Floor
2 |  | 3BHK | 958.4266 | 0 | 1533.4825
3 |  | 3BHK | 1022.2571 | 0 | 1635.6113 |  |  | Building No. 45 Flat no. 2503 CA area changed as agreement index 2 area by smith on 16/07/2024
4 |  | 4BHK | 1415.1431 | 0 | 2264.2289
13th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
1 |  | 3BHK | 1171.0156 | 0 | 1873.6249 | 13th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
2 |  | 3BHK | 958.4266 | 0 | 1533.4825
3 |  | 3BHK | 961.5481 | 0 | 1538.477
4 |  | 3BHK | 1208.9048 | 0 | 1934.2477
31st Floor (Lower Duplex)
1 |  | 4BHK (Duplex With 32nd Floor) | 1935.2596 | 0 | 3096.4153 | 31st Floor (Lower Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 6BHK (Duplex With 32nd Floor) | 2423.7299 | 0 | 3877.9678
32nd Floor (Upper Duplex)
1 |  | Duplex With 31st Floor |  |  |  | 32nd Floor (Upper Duplex)
2 |  | 3BHK | 958.4266 | 0 | 1533.4825
3 |  | 3BHK | 961.5481 | 0 | 1538.477
4 |  | Duplex With 31st Floor
35th Floor (Lower Duplex)
1 |  | 4BHK (Duplex With 36th Floor) | 1962.5194 | 0 | 3140.031 | 35th Floor (Lower Duplex)
2 |  | 3BHK | 978.2592 | 0 | 1565.2148
3 |  | 3BHK | 982.2096 | 0 | 1571.5354
4 |  | 6BHK (Duplex With 36th Floor) | 2498.3083 | 0 | 3997.2932
36th Floor (Upper Duplex)
1 |  | Duplex With 35th Floor |  |  |  | 36th Floor (Upper Duplex)
2 |  | 3BHK | 958.4266 | 0 | 1533.4825
3 |  | 3BHK | 961.5481 | 0 | 1538.477
4 |  | Duplex With 35th Floor
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have received approved floor plans for buildings no. 43 to 45, but building no. 44 is registered in RERA, so we have considered an APF for building no. 44 only.
* | Constrution details are collected from Ms. Sonali - 9324908227
* | We have updated Building No. 43 & 45 (on 24/04/2024).
* | Recommended Rates/Other Charges of the Property have been revised on 03/05/2024, 16/07/2024 & 19/12/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided. | [8 empty] | Constrution details are collected from Ms. Sonali - 9324908227
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Gangaram |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Runwal Gardens Phase VIII
Layout :
Google Map :
Formulas:
Usarghar = [Usarghar, row above]
T/43
T/44
T/45
Building No 43, 44 & 45
45
44
43

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
2024-07-16 | Smith | 2024-07-16