## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 16/07/2025
CPC Name: |  |  |  |  | Axis Kalina
Date Of Property Visit |  |  |  |  | 2025-07-09
Name of the builder group |  |  |  |  | M/s. Ruparel Realty
Name of the builder company |  |  |  |  | M/s. Ruparel Infra & Realty Pvt Ltd.
Name of the Project (As per RERA) |  |  |  |  | Ruparel Optima Ph I
Name of the Project (As per Builder) |  |  |  |  | Ruparel Optima (Sale Building 1, 2 & 3)
Contact Details ( Name & Contact No.) |  |  |  |  | Mr.Aaditya(022-24391100)
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Ashok 8369099238 |  |  |  | Mr.Yash : 8928335745
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No. |  |  |  |  | P51800013701
Approved Layout Plan : |  | Sale bldg No.1-RS/STGOVT/0013/20060721/AP/S1 Dated: 29/08/2019. Sale bldg No.2-RS/STGOVT/0013/20060721/AP/S2 Dated: 29/08/2019. Sale bldg No.3-SRA/ENG/RS/STGOVT/0013/20060721/AP/S3 Dated:29/08/2019.
Project location details |  | CTS No.471 A, Village Kandivali, opp. Pooja Enclave, Near Oscar Hospital, Old Link Road, Kandivali West, Mumbai.
CTS No | 471 A |  |  | Plot No. |  | Locality | Kandivali West
Road | Old Link Road |  |  |  | District | Mumbai
City | Kandivali |  |  |  | Pin Code | 400 067.
Near by Landmark |  | Near Oscar Hospital, |  |  | Distance from city centre: |  | About 3 Km from Kandivali Railway Station.
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Slum |  | Slum |  | Slum |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.20201464, 72.8282365
Location Link |  | https://goo.gl/maps/unLVNz2JnMk5oiYL9
Approval details:
Approved usage of the Property: Residential & Commercial (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 21191.31
Permissible FSI |  |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 4
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 84765.24
Total number of Buildings |  |  |  |  | 7 Buildings
Approval Detail : Plan approval
Layout Approval No |  | Sale bldg No.1-RS/STGOVT/0013/20060721/AP/S1 Dated: 29/08/2019. Sale bldg No.2-RS/STGOVT/0013/20060721/AP/S2 Dated: 29/08/2019. Sale bldg No.3-SRA/ENG/RS/STGOVT/0013/20060721/AP/S3 Dated:29/08/2019.
Building plan approval No |  | Sale bldg No.1-RS/STGOVT/0013/20060721/AP/S1 Dated: 29/08/2019. Sale bldg No.2-RS/STGOVT/0013/20060721/AP/S2 Dated: 29/08/2019. Sale bldg No.3-SRA/ENG/RS/STGOVT/0013/20060721/AP/S3 Dated:29/08/2019.
C.certificate No |  | Sale bldg No.1-RS/STGOVT/0013/20060721/AP/S1 Dated: 02/06/2021.
Valid Upto : This CC is further extended upto 20th upper floors as per last approved amended plans.
C.certificate No |  | Sale bldg No.2-RS/STGOVT/0013/20060721/AP/S2 Dated: 02/06/2021
Valid Upto : This CC is further extended upto 22nd upper floors as per last approved amended plans.
C.certificate No |  | Sale bldg No.3-RS/STGOVT/0013/20060721/AP/S3 Dated:05/10/2020.
Valid Upto : This CC is further extended from 1st to 3rd & 4th to 7th part upper floors marked red hatched line as shown on plan.
Commencement date of construction |  |  | 02/01/2020. |  | Expected Completion |  | 2025-12-30
Building wise Construction details
Approved area of the building in Sq.Mt |  | 53266.14 |  |  | Approved no of units |  | Sale Shops = 25 Flats = 1507
Approved no of Floors |  | Sale bldg No.1 (A, B, C Wing) = G + 1st & 2nd Commercial Floor + Service Floor + 1st to 42nd Floor. Sale bldg No.2 (A, B, C Wing) = B + G + 1st to 42nd Floor. Sale bldg No.3 = B + G + 1st commercial + 1st to 41st Floor
Quality of construction: Good |  |  |  | Projected life: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Sale Building 1 (A Wing) = G + 1st & 2nd Commercial Floor + Service Floor + 1st to 42nd Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 40 Slab, Brickwork upto 38 Floor, Internal Plaster upto 37 Floor, External Plaster upto 37 Floor, Flooring upto 35 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 2 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 40 Slab, Brickwork upto 38 Floor, Internal Plaster upto 37 Floor, External Plaster upto 37 Floor, Flooring upto 35 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 76.09% |  | 89.17% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 40 | 88.89% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 38 | 90.48% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 37 | 88.1% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 37 | 88.1% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 35 | 83.33% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Sale Building 1 (B Wing) = G + 1st & 2nd Commercial Floor + Service Floor + 1st to 42nd Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 37 Floor, Internal Plaster upto 37 Floor, External Plaster upto 37 Floor, Flooring upto 24 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 2 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 37 Floor, Internal Plaster upto 37 Floor, External Plaster upto 37 Floor, Flooring upto 24 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 72.4% |  | 87.07% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 39 | 86.67% | [5 empty] | Footing in Process | 10.5 |  |  | 38
Brickwork | Brickwork & Internal Plaster | 37 | 88.1% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 37 | 88.1% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 37 | 88.1% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 24 | 57.14% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Sale Building 1 (B Wing - Flat no.3 & 4) = G + 1st & 2nd Commercial Floor + Service Floor + 1st to 42nd Floor (Part 2) | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 22 Floor, Internal Plaster upto 16 Floor, External Plaster upto 17 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 2 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 22 Floor, Internal Plaster upto 16 Floor, External Plaster upto 17 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 43.06% |  | 68.21% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 25 | 55.56% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 22 | 52.38% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 16 | 38.1% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 40.48% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Construction details: Average of B Wing = Part B1 & Part B2 | [6 empty] | #REF!
Progress % |  | 57.73% |  | Disbursement % |  |  | 77.64% |  | All work Completed. OC Received.
Construction details: |  | Sale Building 1 (C Wing) (Flat No. 1, 2, 3 & 5) = G + 1st & 2nd Commercial Floor + Service Floor + 1st to 42nd Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 39 Floor, Internal Plaster upto 37 Floor, External Plaster upto 37 Floor, Flooring upto 24 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 2 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 39 Floor, Internal Plaster upto 37 Floor, External Plaster upto 37 Floor, Flooring upto 24 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 74.54% |  | 88.64% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 41 | 91.11% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 39 | 92.86% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 37 | 88.1% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 37 | 88.1% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 24 | 57.14% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Sale Building 2 (A wing - Flat No. 1 & 2) = B + G + 1st to 42nd Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 39 Floor, Internal Plaster upto 39 Floor, External Plaster upto 39 Floor, Flooring upto 15 Floor Completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 39 Floor, Internal Plaster upto 39 Floor, External Plaster upto 39 Floor, Flooring upto 15 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 74.93% |  | 89.32% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 41 | 95.35% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 39 | 92.86% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 39 | 92.86% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 39 | 92.86% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 35.71% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Sale Building 2 (A wing - Flat No. 3 & 4) = B + G + 1st to 42nd Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 16.1 Floor, External Plaster upto 16.1 Floor Completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 16.1 Floor, External Plaster upto 16.1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 43.14% |  | 68.32% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 24 | 55.81% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 23 | 54.76% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 16.1 | 38.33% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.1 | 38.33% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Average of Sale Building 2 (A wing ) = B + G + 1st to 42nd Floor.
Progress % |  | 59.03% |  | Disbursement % |  |  | 78.82%
Construction details: |  | Sale Building 2 (B & C wing) = B + G + 1st to 42nd Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 39 Floor, External Plaster upto 39 Floor, Flooring upto 20 Floor Completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 39 Floor, External Plaster upto 39 Floor, Flooring upto 20 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 76.29% |  | 90.03% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 41 | 95.35% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 40 | 95.24% | [5 empty] | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 39 | 92.86% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 39 | 92.86% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 47.62% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Construction details: |  | Sale Building 3 = B + G + 1st commercial + 1st to 41st Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 37 Floor, Internal Plaster upto 33 Floor, External Plaster upto 33 Floor, Flooring upto 15 Floor Completed
Basement | 1 | Ground | 1 | Podium |  | 1 | Floors | 41
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 37 Floor, Internal Plaster upto 33 Floor, External Plaster upto 33 Floor, Flooring upto 15 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.25
Excavation |  | 41 | 100% |  | 70.79% |  | 86.6% |  | Excavation in process | 20.5
Plinth |  | 41 | 100% | [5 empty] | Excavation Completed | 41
RCC (Including podiums) |  | 39 | 90.7% | [5 empty] | Footing in Process | 10.25
Brickwork | Brickwork & Internal Plaster | 37 | 90.24% | [5 empty] | Footing Completed | 20.5
Internal Plaster | Brickwork & Internal Plaster | 33 | 80.49% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 33 | 80.49% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 36.59% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 30.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 41
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 14500 |  |  |  |  | 13300 to 14000 | 2024-03-28 | smith | verbal
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 30000 |  |  |  | 25K Ither charges add | 2024-01-20 | Trupti
Society Formation Charges | [5 empty] | 50000/-
Club Charges | [5 empty] | 200000/-
Legal Charges | [5 empty] | 25000/-
Development Charges | [5 empty] | 150000/-
Water & Electricity Charges | [5 empty] | 100000/-
MGL Connection | [5 empty] | 10000/-
Recommended rate of Parking | [5 empty] | 600000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 11600
Commercial Area Details : (Sale)
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Sale Building No.1 Wing A, B, C |  | 16 |  | 4614.3115 |  |  | 2224.7896
Commercial Area Details : (Rehab)
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Sale Building No.1 Wing A, B, C |  | 20 |  | 4917.641 |  |  | 7868.2257
Residential Area Details : (Sale)
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Sale Building No.1 | Wing A | 198 |  | 63831.5964 |  |  | 95747.3946
| Wing B | 157 |  | 50613.9426 |  |  | 75920.9139
| Wing C | 198 |  | 63831.5964 |  |  | 95747.3946
Building details floor wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Sale Building No.1
A, B, C Wing
Ground Floor for Parking, Fitness center & Commercial.
S1 | Sale | Shop | 225.3982 |  | 0 | 360.6371 | N | Ground Floor
S2 | Sale | Shop | 225.7211 |  | 0 | 361.1537 | N | Ground Floor
S3 | Sale | Shop | 232.933 |  | 0 | 372.6927 | N | Ground Floor
S4 | Sale | Shop | 226.2593 |  | 0 | 362.0148 | N | Ground Floor
S5 | Sale | Shop | 190.1999 |  | 0 | 304.3198 | N | Ground Floor
S6 | Sale | Shop | 289.9822 |  | 0 | 463.9715 | N | Ground Floor
1 | Rehab | Shop Annx. No.386 | 46.1776 |  | 0 | 73.8841 | N | Ground Floor
2 | Rehab | Shop Annx. No.487 | 180.4046 |  | 0 | 288.6474 | N | Ground Floor
3 | Rehab | Shop Annx. No.398 | 292.0273 |  | 0 | 467.2437 | N | Ground Floor
4 | Rehab | Shop Annx. No.385 | 176.2067 |  | 0 | 281.9307 | N | Ground Floor
5 | Rehab | Shop Annx. No.369 | 361.4551 |  | 0 | 578.3282 | N | Ground Floor
6 | Rehab | Shop Annx. No.373 | 205.9153 |  | 0 | 329.4645 | N | Ground Floor
7 | Rehab | Shop Annx. No.387 | 440.3552 |  | 0 | 704.5684 | N | Ground Floor
8 | Rehab | Shop Annx. No.379 | 94.7232 |  | 0 | 151.5571 | N | Ground Floor
9 | Rehab | Shop Annx. No.375 | 84.7127 |  | 0 | 135.5403 | N | Ground Floor
10 | Rehab | Shop Annx. No.367 | 865.9638 |  | 0 | 1385.5421 | N | Ground Floor
11 | Rehab | Shop Annx. No.381 | 131.2132 |  | 0 | 209.9411 | N | Ground Floor
12 | Rehab | Shop Annx. No.372 | 300.1003 |  | 0 | 480.1605 | N | Ground Floor
13 | Rehab | Shop Annx. No.382 | 42.8407 |  | 0 | 68.5452 | N | Ground Floor
14 | Rehab | Shop Annx. No.383 | 419.796 |  | 0 | 671.6736 | N | Ground Floor
15 | Rehab | Shop Annx. No.380 | 168.6719 |  | 0 | 269.875 | N | Ground Floor
16 | Rehab | Shop Annx. No.368 | 321.1978 |  | 0 | 513.9164 | N | Ground Floor
17 | Rehab | Shop Annx. No.376 | 198.2729 |  | 0 | 317.2366 | N | Ground Floor
18 | Rehab | Shop Annx. No.374 | 53.7124 |  | 0 | 85.9398 | N | Ground Floor
19 | Rehab | Shop Annx. No.432 | 311.2949 |  | 0 | 498.0718 | N | Ground Floor
20 | Rehab | Shop Annx. No.377 | 222.5995 |  | 0 | 356.1592 | N | Ground Floor
Flat No. |  | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | PLC Y/N
Building No.1
1st & 2nd Commercial Floor (A Wing) (Part Health Care)
1 |  | Shop | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
1st & 2nd Commercial Floor (B Wing) (Part Health Care)
1 | Sale | Shop | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | Sale | Shop | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
1st & 2nd Commercial Floor (C Wing) (Part Health Care)
1 |  | Shop | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 |  | Shop | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
Service Floor
1st to 3rd, 5th to 10th, 12th to 17th, 19th to 24th, 26th to 31st, 33rd to 38th & 40th Floor (A Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
5 | 5 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 170
1st to 3rd, 5th to 10th, 12th to 17th, 19th to 24th, 26th to 31st, 33rd to 38th & 40th Floor (B Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  |  |  | 1.5
2 | 2 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 136
1st to 3rd, 5th to 10th, 12th to 17th, 19th to 24th, 26th to 31st, 33rd to 38th & 40th Floor (C Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
5 | 5 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 170
4th, 11th, 18th, 25th, 32nd Floor (A Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 20
4 | 4 | Refuge Area
5 | 5 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4th, 11th, 18th, 25th, 32nd Floor (B Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | Refuge Area
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 15
4th, 11th, 18th, 25th, 32nd Floor (C Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | Refuge Area
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
5 | 5 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 20
39th Floor (A Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | Refuge Area
5 | 5 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 4
39th Floor (B Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | Refuge Area
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 3
39th Floor (C Wing)
1 |  | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
2 | 2 | Refuge Area
3 | 3 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
4 | 4 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA
5 | 5 | 1BHK | 322.3818 | 0 | 322.3818 | 0 | 483.5727 | NA |  | 4
Sale Building No.2
Basement Floor For Tanks
Ground Floor For Parking
Ground Floor (A Wing)
1 | Sale | Shop | 230.7802 | 0 | 230.7802 | 0 | 369.2483 | NA
2 | Sale | Shop | 338.4202 | 0 | 338.4202 | 0 | 541.4723 | NA
1st Floor (A Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 4
1st Floor (B Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 4
1st Floor (C Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | Double Height for Sub Station
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 3
2nd to 7th, 9th to 14th & 16th to 21st, 23rd to 28th, 30th to 35th, 37th to 42nd Floor (A Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 144 | 36
2nd to 7th, 9th to 14th & 16th to 21st, 23rd to 28th, 30th to 35th, 37th to 42nd Floor (B Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 144
2nd to 7th, 9th to 14th & 16th to 21st, 23rd to 28th, 30th to 35th, 37th to 42nd Floor (C Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 144
8th & 15th, 22nd, 29th & 36th Floor (A Wing)
1 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 15
4 | 4 | Refuge Area
8th & 15th, 22nd, 29th & 36th Floor (B Wing)
1 |  | Refuge Area
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 15
8th & 15th, 22nd, 29th & 36th Floor (C Wing)
1 |  | Refuge Area
2 | 2 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
3 | 3 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA
4 | 4 | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956 | NA |  | 15
Sale Building No.3
Basement Floor
Ground + 1st Commercial Floor (Part Amenities)
1 | Sale | Shop (Duplex) | 410.2053 | 0 | 410.2053 | 0 | 656.3284 | Ground + 1st Commercial Floor
2 | Sale | Shop (Duplex) | 388.4082 | 0 | 388.4082 | 0 | 621.4531
3 | Sale | Shop (Duplex) | 391.1745 | 0 | 391.1745 | 0 | 625.8792
4 | Sale | Shop (Duplex) | 388.4189 | 0 | 388.4189 | 0 | 621.4703
5 | Sale | Shop (Duplex) | 388.4189 | 0 | 388.4189 | 0 | 621.4703
6 | Sale | Shop (Duplex) | 389.0863 | 0 | 389.0863 | 0 | 622.5381
7 | Sale | Shop (Duplex) | 402.7889 | 0 | 402.7889 | 0 | 644.4622
8 | Sale | Shop (Duplex) | 396.2315 | 0 | 396.2315 | 0 | 633.9703
9 | Sale | Shop (Duplex) | 441.4101 | 0 | 441.4101 | 0 | 706.2562
10 | Sale | Shop (Duplex) | 462.7078 | 0 | 462.7078 | 0 | 740.3324
11 | Sale | Shop (Duplex) | 302.139 | 0 | 302.139 | 0 | 483.4224
12 | Sale | Shop (Duplex) | 471.7646 | 0 | 471.7646 | 0 | 754.8233
13 | Sale | Shop (Duplex) | 465.4999 | 0 | 465.4999 | 0 | 744.7999
1st to 5th, 7th to 12th, 14th to 19th, 21st to 26th, 28th to 33rd, 35th to 41st Floor | [9 empty] | 432
1 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163 | 1st to 5th, 7th to 12th, 14th to 19th, 21st to 26th, 28th to 33rd, 35th to 41st Floor |  | 45
2 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
3 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163 |  |  | 1507
4 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
5 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
6 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
7 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
8 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
9 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
10 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
11 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
12 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
6th, 13th, 20th, 27th & 34th Floor
1 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163 | 6th, 13th, 20th, 27th & 34th Floor
2 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
3 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
4 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
5 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
6 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
7 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
8 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
9 |  | 1BHK | 315.2776 | 0 | 315.2776 | 0 | 472.9163
10 |  | Refuge Area
11
12
Remarks: 1. Bldg No. 1, 2 (Wing B & Wing C) & 3 = Construction work is in process at the time of visit. Internal photo not allowed. (Speed is slow) Bldg No. 2(Wing A) = we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report dtd 05/04/2025. Building No.1 Wing C (Flat no.4) = Construction work not yet started. 2. We considered saleable area as per our calculation. 3. Car parking is subjected to authentic documentation. 4. We update revised plan of Building No.1 & 2 (on 17/01/2020). 5. We have given 60% Loading for commercial & 50% Loading for Residential. 6. Construction percentages are Reduced due to changes in no. of Floors as per revised Plan. 7. We have considered rate by verifying it from market inquire. 8. We have considered Other charges from cost sheet. 9. We update revised plan of Building No.3 (on 14/02/2020). 10. We have updated CC from Rera (On 21/06/2023). 11. Recommended Rates/Other Charges of the Property have been revised on 28/03/2024. 12. As per our observation, the construction work of ruparel projects (Ruparel Jewel, Ruparel Regalia, Ruparel Millennia, etc.) seems to be on a slow speed since last year. | [9 empty] | 11. As per site person Mr. Samay, Construction work of Building No.1 Wing C - Flat no.4 not yet started. Construction work of Building No.2 Wing A - Flat no.3 & 4 is completed upto 16slab.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  |  | Ruparel Optima (Sale Building 1, 2 & 3)
Google Map :
Building No.1
Wing A
Building No.1
Wing B
Building No.1
Wing C
Building No.2
Wing A (Pt2)
Building No.3
Building No.2
Wing A
Flat No. 3 & 4
Bldg 1A
Bldg 1B
Bldg 1C
Bldg 2A
Bldg 2B
Bldg 2C
Bldg 3

## Valutation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
magicbricks | Ruparel Optima | 1BHK | 323 | 484.5 | 12796.6976 | 6200000
magicbricks | Ruparel Optima | 1BHK | 322 | 483 | 10766.0455 | 5200000
magicbricks | Ruparel Optima | 1BHK | 322 | 483 | 14492.7536 | 7000000
99Acres | Ruparel Optima | 1BHK | 322.81 | 484.215 | 12184.67 | 5900000
squareyards | Ruparel Optima | 1BHK | 320 | 480 | 14145.8333 | 6790000
housing | Ruparel Optima | 1BHK | 322 | 483 | 13099.3789 | 6327000
commonfloor | Ruparel Optima | 1BHK | 0 | 544 | 9558.8235 | 5200000
proptiger | Ruparel Optima | 1BHK | 323 | 484.5 | 13067.0795 | 6331000
dwello | Ruparel Optima | 1BHK | 322.8 | 484.2 | 14929.7811 | 7229000
Average |  |  | 0 |  | 12782.3403
Valuation Adopted |  |  |  |  | 12800

## Note
09/10/2020. | Dhanashree | OLD APF
1. Rate has not changed.
2021-03-04 | Pratiksha

## 1A%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 45
Particulars | total floor | 45
plinth | 10 | 10 | 100%
slab | 46 | 10 | 21.74% |  | Parking |  | Rate
Bricks | 45 | 9 | 20% |  | Palghar |  | 100000/-
plaster | 45 | 4.5 | 10% |  | Ulwe, karanjade |  | 200000/-
Flooring | 45 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 45 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 45 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 8.6957 | 3 | 1 | 0 | 0 | 0
RCC | 8.6957 | 6.5217 |  | Recommended |  | 30 | 6.5217 | 3 | 1 | 0 | 0 | 0
Bricks | 3 | 3
Plaster | 1 | 1
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 22.7% | 40.52% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 1B%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 45
Particulars | total floor | 45
plinth | 10 | 10 | 100%
slab | 46 | 8 | 17.39% |  | Parking |  | Rate
Bricks | 45 | 7 | 15.56% |  | Palghar |  | 100000/-
plaster | 45 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 45 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 45 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 45 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 6.9565 | 2.3333 | 0 | 0 | 0 | 0
RCC | 6.9565 | 5.2174 |  | Recommended |  | 30 | 5.2174 | 2.3333 | 0 | 0 | 0 | 0
Bricks | 2.3333 | 2.3333
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 19.29% | 37.55% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 1C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 45
Particulars | total floor | 45
plinth | 10 | 10 | 100%
slab | 46 | 8 | 17.39% |  | Parking |  | Rate
Bricks | 45 | 7 | 15.56% |  | Palghar |  | 100000/-
plaster | 45 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 45 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 45 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 45 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 6.9565 | 2.3333 | 0 | 0 | 0 | 0
RCC | 6.9565 | 5.2174 |  | Recommended |  | 30 | 5.2174 | 2.3333 | 0 | 0 | 0 | 0
Bricks | 2.3333 | 2.3333
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 19.29% | 37.55% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 2%
Basement | Podium | Ground | Upper Floor
1 | 0 | 1 | 42
Particulars | total floor | 42
plinth | 10 | 10 | 100%
slab | 44 | 11 | 25% |  | Parking |  | Rate
Bricks | 42 | 10 | 23.81% |  | Palghar |  | 100000/-
plaster | 42 | 5 | 11.9% |  | Ulwe, karanjade |  | 200000/-
Flooring | 42 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 42 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 42 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 10 | 3.5714 | 1.1905 | 0 | 0 | 0
RCC | 10 | 7.5 |  | Recommended |  | 30 | 7.5 | 3.5714 | 1.1905 | 0 | 0 | 0
Bricks | 3.5714 | 3.5714
Plaster | 1.1905 | 1.1905
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 24.76% | 42.26% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 3%
Basement | Podium | Ground | Upper Floor
1 | 0 | 1 | 41
Particulars | total floor | 41
plinth | 10 | 10 | 100%
slab | 42 | 6 | 14.29% |  | Parking |  | Rate
Bricks | 41 | 2 | 4.878% |  | Palghar |  | 100000/-
plaster | 41 | 1 | 2.439% |  | Ulwe, karanjade |  | 200000/-
Flooring | 41 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 41 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 41 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5.7143 | 0.73171 | 0.2439 | 0 | 0 | 0
RCC | 5.7143 | 4.2857 |  | Recommended |  | 30 | 4.2857 | 0.73171 | 0.2439 | 0 | 0 | 0
Bricks | 0.73171 | 0.73171
Plaster | 0.2439 | 0.2439
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 16.69% | 35.26% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.9 | 4.33 | 12.557 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.15 | 2 | 4.3 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 3.16 | 8.69 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 2.15 | 2.58 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.3 | 0.9 | 1.17 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 315.3529 | 29.297 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0