## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | Atharv Infra LLP
Name of the builder company |  |  |  | Atharv Infra LLP
Name of the Project |  |  |  | Atharv Aaradhyam
Provided Contact Details (Name & Contact No.) |  |  |  | Miss. Natasha Patel 9619108605
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Vaibhav 8976758402 |  |  |  | 8976758403
Name / No of the Building |  |  |  | Tower 1 to 5
Name / No of the Existing Building |  |  |  | Chandrashekhar CHSL |  |  |  |  | in confusion with vijaynagar building |  |  |  | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Airport Noc | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800052443 |  |  |  | #N/A |  |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Atharv Aaradhyam, CTS No.460/A & 460/B & Redevelopment of building " Chandrashekhar CHSL ", near Hubtown Solaris, Professor NS Phadke Road, Vijay Nagar, Marol, Andheri (East), Andheri, Mumbai - 400053. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 460/A & 460/B & Redevelopment of building " Chandrashekhar CHSL " | [10 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Vijay Nagar | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Professor NS Phadke Road |  | Locality/Village |  | Marol | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Andheri (East) |  | District |  | Mumbai | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Andheri |  | Pin Code |  | 400053 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Hubtown Solaris |  | Distance from city centre: |  | 1.1 KM from Andheri Railway Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Hubtown Solaris
West | NA | 9.15 M W Right of Way |  |  | Paranjape Vidyalaya
North | NA | 36.60 M.W. DP Road (NS Phadke Road) |  |  | Professor NS Phadke Road
South | NA | Other Plot |  |  | Om sai CHSL
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.1144589342,72.849050316
Location Link |  | https://maps.app.goo.gl/pAEZ2Gc3v8zwWVYv8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5555.88
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 2.4469
Total FSI availaible for the project |  |  |  | 3.4469
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19150.43
Total number of Buildings |  |  |  | 5 Towers
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | P-9910/2021/(460)/K/E Ward/GUNDAVALI/337/2/Amend |  |  | Dated | 2023-12-29
Approved Floor plan No. |  | P-9910/2021/(460)/K/E Ward/GUNDAVALI/337/2/Amend |  |  | Dated | 2023-12-29
Commencement-CC No Valid Up to: |  | P-9910/2021/(460)/K/E Ward/GUNDAVALI/CC/1/New |  |  | Dated | 2023-08-07
|  | C.C. up to top of plinth i.e. ht. 0.90 mt. AGL for Building No. 1 & top of (pt.) Stilt i.e. ht. 3.60 mt. for Building No. 1 & 3.35 mt. AGL for Building No. 2 to 5 & Parking Tower as per last approved plan dated 23.01.2023. |  |  | Valid Upto Date | 2024-08-06
Commencement-CC No Valid Up to: |  | P-9910/2021/(460)/K/E Ward/GUNDAVALI/FCC/1/New |  |  | Dated | 2024-07-01
|  | F.C.C. for Tower No.1 up to top of 10th floor i.e. ht. 32.10 mt., Tower No. 3 up to top of 11th floor i.e. ht. 35.20 mt., Tower No. 4 up to top of 11th floor i.e. ht. 35.20 mt., Tower No. 5 up to top of 11th floor i.e. ht. 35.20 mt., + Parking Tower ht. i.e. 38.38 mt. AGL as per last approved plan dated 29.12.2023. |  |  | Valid Upto Date | 2025-06-30
Commencement-CC No Valid Up to: |  | P-9910/2021/(460)/K/E Ward/GUNDAVALI/FCC/1/Amend |  |  | Dated | 2024-11-18
|  | F.C.C. for Tower No. 2 upto top of 8th floor i.e. ht. 26.30 mt., AGL + Parking Tower ht. i.e. 38.38 mt. AGL as per last approved plan dated 29.12.2023. |  |  | Valid Upto Date | 2025-08-06
Commencement-CC No Valid Up to: |  | P-9910/2021/(460)/K/E Ward/GUNDAVALI/FCC/2/Amend |  |  | Dated | 2025-02-13
|  | Further C.C. for Tower No. 1 up to top of 11th floor i.e. ht. 35.20 mt. AGL, for Tower No. 2 up to top of 10th floor i.e. ht. 32.10 mt AGL, for Tower No. 3 up to top of 12th floor i.e. ht. 38.40 mt. AGL+ LMR +OHT , for Tower No. 4 & 5 up to top of 12th floor i.e. ht. 38.40 mt. AGL + Parking Tower ht. i.e. 38.38 mt. AGL as per last approved plan dated 29.12.2023. |  |  | Valid Upto Date | 2025-08-06
Airport Authority of India NOC No. Valid Up to: |  | JUHU/WEST/B/061821/552126 |  |  | Dated | 2021-07-16
|  | 57.13 M (Restricted) (AMSL) |  |  | Valid Upto Date | 2029-07-15
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 19150.43
Approved no of units |  |  | Flats - 223, Shops - 7
Approved no of Floors |  |  | Tower 1 = LG + Gr/Stilt + 1st to 11th Floor Tower 2 = LG + Gr/Stilt + 1st to 12th Floor Tower 3 = LG + Gr/Stilt + 1st to 12th Floor Tower 4 = LG + Gr/Stilt + 1st to 12th Floor Tower 5 = LG + Gr/Stilt + 1st to 12th Floor
Proposed no of Floors |  |  | Tower 1 & 2 = LG + Gr/Stilt + 1st to 12th Floor
Tower 02 = LG + Gr/Stilt + 1st to 12th Floor
Tower 3 = LG + Gr/Stilt + 1st to 12th Floor
Tower 4 = LG + Gr/Stilt + 1st to 12th Floor
Tower 5 = LG + Gr/Stilt + 1st to 12th Floor
Expected Completion |  |  | As per RERA - 30/04/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Board Games, Security Cabin, Cycling & Jogging Track, Manicured Garden, Video Door Security, Terrace Garden, Sun Deck, Multi - Level Parking, Pergola, Solar Lighting, Reflexology Park, CCTV, Kid's Pool, Senior Citizen Siteout, Party Lawn, Gazebo, Indoor Games, Yoga/Meditation Area, Gymnasium, Fire Fighting System
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 1 = LG + Gr/Stilt + 1st to 12th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | , RCC upto 5 Slab, Brickwork upto 4 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 27.88% |  | 58.21% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 5 | 38.46% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 4 | 33.33% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Tower 2 = LG + Gr/Stilt + 1st to 12th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab, Brickwork upto 1 Floor Completed | , RCC upto 6 Slab, Brickwork upto 1 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 29.09% |  | 59.26% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 6 | 46.15% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 1 | 8.333% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Tower 3 = LG + Gr/Stilt + 1st to 12th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 11 Floor, Internal Plaster upto 9.9 Floor, External Plaster upto 8.25 Floor, Flooring upto 2 Floor Completed | , RCC upto 12 Slab, Brickwork upto 11 Floor, Internal Plaster upto 9.9 Floor, External Plaster upto 8.25 Floor, Flooring upto 2 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 11 Floor, Internal Plaster upto 9.9 Floor, External Plaster upto 8.25 Floor, Flooring upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 68.53% |  | 85.67% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 12 | 92.31% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 11 | 91.67% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 9.9 | 82.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8.25 | 68.75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 16.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Tower 4 = LG + Gr/Stilt + 1st to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 10 Floor, External Plaster upto 7.8 Floor Completed | , Internal Plaster upto 10 Floor, External Plaster upto 7.8 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 10 Floor, External Plaster upto 7.8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 70.25% |  | 87.42% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 10 | 83.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7.8 | 65% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Tower 5 = LG + Gr/Stilt + 1st to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 10 Floor, External Plaster upto 7.8 Floor, Flooring upto 2 Floor Completed | , Internal Plaster upto 10 Floor, External Plaster upto 7.8 Floor, Flooring upto 2 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 10 Floor, External Plaster upto 7.8 Floor, Flooring upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 71.92% |  | 88.25% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 10 | 83.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7.8 | 65% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 16.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Online | Visitor | MIS | Cost sheet
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 25000 |  |  | #DIV/0! | #DIV/0! | 21333.3333 | 26000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 40000
Recommended rate of the Shop Per Sq. Ft. (1st & 2nd Floor) |  |  |  |  | 35000 |  |  |  | 25000 Rate : Trupti : On 16/04/2024
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 20000
Commercial Area Details : | [8 empty] | 26500 hubtown
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 01 |  | 7 |  | 6439.5163 |  | 9981.2502
Total |  | 7 |  | 6439.5163 |  | 9981.2502
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 01 |  | 37 |  | 40842.4372 |  | 40842.4372
Tower 02 |  | 46 |  | 59362.3836 |  | 59362.3836
Tower 03 |  | 47 |  | 59953.4887 |  | 59953.4887
Tower 04 |  | 46 |  | 59618.1362 |  | 59618.1362
Tower 05 |  | 47 |  | 59801.0704 |  | 59801.0704
Total |  | 223 |  | 279577.5161 |  | 279577.5161
Grand Total |  | 230 |  | 286017.0324 |  | 289558.7664
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
[5 empty] | 55% |  |  |  | 10.764
Tower 01
Lower Ground Floor for Parking, Meter Room & Pump Room
Ground Floor for Commercial & Parking
1 |  | Shop | 479.0701 | 0 | 742.5587 | Ground Floor for Commercial & Parking |  |  | 38397.6132
2 |  | Shop | 537.6678 | 0 | 833.3851
3 |  | Shop | 826.3146 | 0 | 1280.7876 |  |  |  | =
1st Floor for Part Commercial
1 |  | Shop | 761.025 | 0 | 1179.5888 | 1st Floor for Part Commercial |  |  | 50865.1833
2 |  | Shop | 1537.2068 | 0 | 2382.6706
2nd Floor for Part Commercial
1 |  | Shop | 761.025 | 0 | 1179.5888 | 2nd Floor for Part Commercial
2 |  | Shop | 1537.2068 | 0 | 2382.6706
Tower 02
1st Floor for Part Commercial
1 |  | Shop | 760.9981 | 0 | 1179.5471 | 1st Floor for Part Commercial
2 |  | Shop | 1543.45 | 0 | 2392.3474
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Tower 01
1st Floor for Part Residential
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 1st Floor for Part Residential |  | 43.334
2 |  | Entrance Lobby below | [5 empty] | 62.62
2nd Floor for Part Residential
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 2nd Floor for Part Residential
2 |  | 2BHK | 704.7191 | 0 | 1057.0786 |  |  |  | 23082.4837
3 |  | Fitness Center & Society Office
3rd Floor For Part Residential
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 3rd Floor For Part Residential
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
3 |  | Fitness Center
4th Floor For Fitness Centre
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 4th Floor For Fitness Centre
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
3 + 4 |  | Fitness Center & Gym & Splash Pool
5th Floor
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 5th Floor
2 |  | 2BHK | 704.7191 | 0 | 1057.0786 |  |  |  | 25920.494
3 |  | 3BHK | 978.7705 | 0 | 1468.1558
4 |  | 3BHK | 919.0303 | 0 | 1378.5455 |  |  |  | 26187.0214
6th Floor
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 6th Floor
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
3 |  | 3BHK | 978.7705 | 0 | 1468.1558
4 |  | 3BHK | 919.0303 | 0 | 1378.5455
7th Floor
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 7th Floor
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
3 |  | 3BHK | 978.7705 | 0 | 1468.1558
4 |  | 3BHK | 919.0303 | 0 | 1378.5455
8th Floor (Part Refuge Area)
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
- |  | Refuge Area
3 |  | 1RK | 410.216 | 0 | 615.3241
4 |  | 3BHK | 919.0303 | 0 | 1378.5455
9th Floor
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 9th Floor
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
3 |  | 3BHK | 978.7705 | 0 | 1468.1558
4 |  | 3BHK | 919.0303 | 0 | 1378.5455
10th Floor
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 10th Floor
2 |  | 2BHK | 704.7191 | 0 | 1057.0786
3 |  | 3BHK | 978.7705 | 0 | 1468.1558
4 |  | 3BHK | 919.0303 | 0 | 1378.5455
11th & 12th Floor
1 |  | 1BHK | 494.1752 | 0 | 741.2629 | 11th & 12th Floor |  |  | 24282.8839
2 |  | 2BHK | 704.7191 | 0 | 1057.0786 |  |  |  | 22704.0823
3 |  | 3BHK | 1040.3406 | 0 | 1560.5109
4 |  | 3BHK | 923.1206 | 0 | 1384.681
Tower 02
Lower Ground Floor for Parking, Meter Room, Domestic Tank & Pump Room
Ground Floor for Parking & Entrance Lobby
1st Floor for Residential
1 |  | 2.5BHK | 809.7757 | 0 | 1214.6636 | 1st Floor for Residential |  | 69.24
2 |  | Entrance Lobby below | [6 empty] | #DIV/0!
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 812.8973 | 0 | 1219.3459
2nd Floor
1 |  | 2.5BHK | 809.7757 | 0 | 1214.6636 | 2nd Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292 |  |  |  | 26904.7196
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 812.8973 | 0 | 1219.3459
3rd Floor
1 |  | 2.5BHK | 809.7757 | 0 | 1214.6636 | 3rd Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 963.9162 | 0 | 1445.8743
4 |  | 2.5BHK | 812.8973 | 0 | 1219.3459
4th Floor
1 |  | 2.5BHK | 809.7757 | 0 | 1214.6636 | 4th Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 812.8973 | 0 | 1219.3459
5th Floor
1 |  | 2.5BHK | 809.7757 | 0 | 1214.6636 | 5th Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 812.8973 | 0 | 1219.3459
6th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 6th Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 812.8973 | 0 | 1219.3459
7th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 7th Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 879.0959 | 0 | 1318.6438
8th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 788.463 | 0 | 1182.6945
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 879.0959 | 0 | 1318.6438
9th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 9th Floor
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 879.0959 | 0 | 1318.6438 |  |  |  | 25404.8891
10th Floor
1 |  | 3BHK | 908.9122 | 0 | 1363.3682 | 10th Floor
2 |  | 2BHK | 744.6535 | 0 | 1116.9803
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 879.0959 | 0 | 1318.6438
11th & 12th Floor
1 |  | 3BHK | 908.9122 | 0 | 1363.3682 | 11th & 12th Floor
2 |  | 2BHK | 744.6535 | 0 | 1116.9803
3 |  | 3BHK | 978.1247 | 0 | 1467.187
4 |  | 2.5BHK | 879.0959 | 0 | 1318.6438
12th Floor (Part Terrace Area)
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 12th Floor (Part Terrace Area)
2 |  | 2BHK | 740.8861 | 0 | 1111.3292
3 |  | 3BHK | 963.9162 | 0 | 1445.8743
4 |  | Terrace Area
Tower 03
Lower Ground Floor for Parking, Meter Room, Domestic Tank & Pump Room
Ground Floor for Parking & Entrance Lobby
1st Floor for Residential
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 1st Floor for Residential
2 |  | Entrance Lobby below
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
2nd Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 2nd Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
3rd Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 3rd Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
4th Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 4th Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
5th Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 5th Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
6th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 6th Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
7th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 7th Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 2.5BHK | 810.7445 | 0 | 1216.1167
8th Floor (Part Refuge Area)
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 1RK | 387.8269 | 0 | 581.7404
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
9th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 9th Floor
2 |  | 2BHK | 770.0566 | 0 | 1155.0848
3 |  | 3BHK | 924.3047 | 0 | 1386.457
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
10th Floor
1 |  | 3BHK | 908.9122 | 0 | 1363.3682 | 10th Floor
2 |  | 2BHK | 774.3622 | 0 | 1161.5432
3 |  | 3BHK | 1034.0975 | 0 | 1551.1462
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
11th & 12th Floor
1 |  | 3BHK | 908.9122 | 0 | 1363.3682 | 11th & 12th Floor
2 |  | 2BHK | 774.3622 | 0 | 1161.5432
3 |  | 3BHK | 1034.0975 | 0 | 1551.1462
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
Tower 04
Lower Ground Floor for Parking, Meter Room, Domestic Tank & Pump Room
Ground Floor for Parking & Entrance Lobby
1st Floor for Residential
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 1st Floor for Residential
2 |  | Entrance Lobby below
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
2nd Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 2nd Floor
2 |  | 2BHK | 770.1642 | 0 | 1155.2463
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
3rd Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 3rd Floor
2 |  | 2BHK | 770.1642 | 0 | 1155.2463
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
4th Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 4th Floor
2 |  | 2BHK | 770.1642 | 0 | 1155.2463
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
5th Floor
1 |  | 2.5BHK | 810.5292 | 0 | 1215.7938 | 5th Floor
2 |  | 2BHK | 770.1642 | 0 | 1155.2463 |  |  |  | 24150.6941
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
6th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 6th Floor |  |  | 24010.8923
2 |  | 2BHK | 770.1642 | 0 | 1155.2463
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
7th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 7th Floor
2 |  | 2BHK | 770.1642 | 0 | 1155.2463
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
8th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 818.1716 | 0 | 1227.2575
3 |  | 3BHK | 923.4436 | 0 | 1385.1653
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
9th Floor
1 |  | 3BHK | 905.1448 | 0 | 1357.7171 | 9th Floor
2 |  | 2BHK | 774.4698 | 0 | 1161.7047
3 |  | 3BHK | 1033.2364 | 0 | 1549.8545
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
10th Floor
1 |  | 3BHK | 908.9122 | 0 | 1363.3682 | 10th Floor
2 |  | 2BHK | 774.4698 | 0 | 1161.7047
3 |  | 3BHK | 1033.2364 | 0 | 1549.8545
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
11th & 12th Floor
1 |  | 3BHK | 908.9122 | 0 | 1363.3682 | 11th & 12th Floor
2 |  | 2BHK | 770.1642 | 0 | 1155.2463
3 |  | 3BHK | 1033.2364 | 0 | 1549.8545
4 |  | 3BHK | 905.1448 | 0 | 1357.7171
Tower 05
Lower Ground Floor for Parking, Meter Room, Domestic Tank & Pump Room
Ground Floor for Parking & Entrance Lobby
1st Floor for Residential
1 |  | 2.5BHK | 810.6368 | 0 | 1215.9553 | 1st Floor for Residential
2 |  | Entrance Lobby below
3 |  | 3BHK | 923.9818 | 0 | 1385.9726 |  |  |  | 23882.1453
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
2nd Floor
1 |  | 2.5BHK | 810.6368 | 0 | 1215.9553 | 2nd Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
3rd Floor
1 |  | 2.5BHK | 810.6368 | 0 | 1215.9553 | 3rd Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
4th Floor
1 |  | 2.5BHK | 810.6368 | 0 | 1215.9553 | 4th Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
5th Floor
1 |  | 2.5BHK | 810.6368 | 0 | 1215.9553 | 5th Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
6th Floor
1 |  | 3BHK | 905.4677 | 0 | 1358.2015 | 6th Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
7th Floor
1 |  | 3BHK | 905.4677 | 0 | 1358.2015 | 7th Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 3BHK | 923.9818 | 0 | 1385.9726 |  |  |  | 26768.2052
4 |  | 2.5BHK | 810.8521 | 0 | 1216.2782
8th Floor (Part Refuge Area)
1 |  | 3BHK | 905.4677 | 0 | 1358.2015 | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 770.7024 | 0 | 1156.0536
3 |  | 1RK | 387.6116 | 0 | 581.4175
4 |  | 3BHK | 905.4677 | 0 | 1358.2015
9th Floor
1 |  | 3BHK | 905.4677 | 0 | 1358.2015 | 9th Floor
2 |  | 2BHK | 770.7024 | 0 | 1156.0536 |  |  |  | 26988.368
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 3BHK | 905.4677 | 0 | 1358.2015
10th Floor
1 |  | 3BHK | 909.2351 | 0 | 1363.8526 | 10th Floor
2 |  | 2BHK | 774.4698 | 0 | 1161.7047
3 |  | 3BHK | 923.9818 | 0 | 1385.9726
4 |  | 3BHK | 905.4677 | 0 | 1358.2015
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
11th & 12th Floor
1 |  | 3BHK | 909.2351 | 0 | 1363.8526 | 11th & 12th Floor
2 |  | 2BHK | 774.4698 | 0 | 1161.7047
3 |  | 3BHK | 1034.4204 | 0 | 1551.6306
4 |  | 3BHK | 905.4677 | 0 | 1358.2015
Remarks:
* | Tower 1, 2, 3, 4 & 5 = Construction work is in process at the time of Visit (labour found). Internal visit not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck Area + Dry Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have refered Civil Aviation NOC from MCGM site.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned in approved layout plan & floor plan.
* | Recommended Rates / Other charges of the Property have been revised on 16/04/2024.
* | We have updated approved plans & CC (on 11/07/2024).
* | We have not revised Carpet Area for Commercial Units due dimensions were not provided properly in approved Plans dtd 23/12/2023.
* | We have updated revised CC from MCGM site on 20/11/2024 & 11/07/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Pratik Niwate |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Atharv Aaradhyam
Layout :
Google Map :
Formulas:
Marol = [Marol, row above]
Tower 01
Tower 02
Tower 03
Tower 04
Tower 05
Tower 5
Tower 1
T1
T1
T2
T5
T4
T3
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D63: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC