## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | Alpine Infraheights LLP
Name of the builder company |  |  |  | Alpine Infraheights LLP
Name of the Project |  |  |  | Alpine Primo
Provided Contact Details (Name & Contact No.) |  |  |  | 02249698273/9324400387
Site Person - Contact Details (Name & Contact No.) |  |  |  | Jessica 9594787953
Name / No of the Building |  |  |  | Wing A, B & C
Name / No of the Existing Building |  |  |  | Sunil Shopping Centre CHSL | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Airport Noc | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800030851 |  |  |  | #N/A |  |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Alpine Primo, CTS No.136/A & Redevelopment of building "Sunil Shopping Centre CHSL", near Kamala Apartment, J.P. Road, Navneeth Colony, Andheri, Andheri (West), Andheri, Mumbai - 400058. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 136/A & Redevelopment of building "Sunil Shopping Centre CHSL" | [10 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Navneeth Colony | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | J.P. Road |  | Locality/Village |  | Andheri | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Andheri (West) |  | District |  | Mumbai | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Andheri |  | Pin Code |  | 400058 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Kamala Apartment |  | Distance from city centre: |  | 2.1 KM from Andheri Railway Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Kamala Apartment
West | NA | 9.15 M Wide N.S.Patil Marg |  |  | Ram Baug Lane
North | NA | Nalla |  |  | Nalla
South | NA | 27.45 M Wide Jay Prakash Road |  |  | J.P. Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.124004, 72.842802
Location Link |  | https://maps.app.goo.gl/vsotBPqv6PYHxM8y8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3396.5
Permissible FSI |  |  |  | 1.7 |  |  |  | 1.7282
Permissible TDR/Paid FSI |  |  |  | 0.024937
Total FSI availaible for the project |  |  |  | 1.7249
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5858.75
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | P-1795/2019/(136/A)/K/W WARD/ANDHERI-KW |  |  | Dated | 2024-01-16
Approved Floor plan No. |  | P-1795/2019/(136/A)/K/W WARD/ANDHERI-KW |  |  | Dated | 2024-01-16
Commencement-CC No Valid Up to: |  | P-1795/2019/(136/A)/K/W Ward/ANDHERI-KW/FCC/2/Amend |  |  | Dated | 2025-03-28
|  | Further C.C. for Wing A, B & C up to top of 13th upper floor (height 47.25 mts. AGL) as per the amended plan dated 21.03.2025. |  |  | Valid Upto Date | 2025-06-06
Commencement-CC No Valid Up to: |  | P-1795/2019/(136/A)/K/W Ward/ANDHERI-KW/FCC/1/Amend |  |  | Dated | 2024-02-23
|  | Further C.C. for Wing A, B & C up to top of 8th upper floor (height 31.85 mtr. AGL) as per the amended plan dated 16.01.2024. |  |  | Valid Upto Date | 2024-06-06
Airport Authority of India NOC No. Valid Up to: |  | JUHU/WEST/B/032018/287481 |  |  | Dated | 2018-04-25
|  | 56.9 M (Restricted) (AMSL) |  |  | Valid Upto Date | 2026-04-24
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5858.75
Approved no of units |  |  | Sale Flats - 32, Rehab Flats - 43, Convenience/Rehab Shops - 47, Sale Offices - 23, Rehab Office - 1
Approved no of Floors |  |  | Wing A, B & C = Gr/Stilt + 1st Floor + 2nd to 3rd Podium Floor + 4th to 9th Floor
Proposed no of Floors |  |  | Wing A, B & C = Gr/Stilt + 1st Floor + 2nd to 3rd Podium Floor + 4th to 14th Floor
B Wing = 1B + G + 1st to 20th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Swimming Pool, Kids' Play Areas / Sand Pits, Yoga Areas, Gazebo, Power Backup, 24*7 Water Supply, Party Lawn, 24 x 7 Security, CCTV / Video Surveillance, Fire Fighting Systems, Intercom Facility, Party Hall, Indoor Games, Obeservatory Deck, Senior Citizen Area
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A, B & C = Gr/Stilt + 1st Floor + 2nd to 3rd Podium Floor + 4th to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 5 Floor, External Plaster upto 3 Floor Completed | , RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 5 Floor, External Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 5 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 48.44% |  | 72.71% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 11 | 73.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 8 | 57.14% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 5 | 35.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 21.43% |  |  |  |  | Basement 2 | 0 | stage of const given as per architec certificate & visitor sheet on 09/10/2024
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing C = Gr/Stilt + 1st Floor + 2nd to 3rd Podium Floor + 4th to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab Completed | , RCC upto 6 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 26% |  | 57% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 6 | 40% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Online | Builder | MIS | Visitor
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 19800 |  |  | 20469.3846 | 20877.5382 | 20333.3333 | 22000 | 18666.6667
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 32000 |  |  | Other charges added by Shailesh on 28/08/2024
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 30000
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 320000
Sinking Fund Charges |  |  |  |  | 25000
Utility Charges |  |  |  |  | 30000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges |  |  |  |  | 85000
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 15840
Commercial Area Details : (Convenience / Rehab)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A+B+C | Shop | 47 |  | 11674.7399 |  | 18095.8468
Wing A+B+C | IT Office | 1 |  | 931.6156 |  | 1444.0042
Total |  | 48 |  | 12606.3555 |  | 19539.851
Commercial Area Details : (Sale)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A+B+C | IT Office | 23 |  | 12540.4335 |  | 19437.6719
Total |  | 23 |  | 12540.4335 |  | 19437.6719
Residential Area Details : (Sale)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 7 |  | 3085.2853 |  | 4627.928
Wing B |  | 18 |  | 10906.3001 |  | 16359.4501
Wing C |  | 7 |  | 3164.1854 |  | 4746.2782
Total |  | 32 |  | 17155.7708 |  | 25733.6563
Residential Area Details : (Rehab)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 22 |  | 15036.6622 |  | 22554.9932
Wing B |  | 2 |  | 2081.65 |  | 3122.4749
Wing C |  | 19 |  | 13389.1243 |  | 20083.6865 |  | 75
Total |  | 43 |  | 30507.4364 |  | 45761.1547
Grand Total |  | 146 |  | 72809.9963 |  | 110472.3338
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Sale / Rehab | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Wing A + B + C
Ground Floor for Commercial & Parking | [8 empty] | 10.764
1 | Convenience / Rehab | Shop | 289.7292 | 0 | 449.0803 | Ground Floor for Commercial & Parking
2 | Convenience / Rehab | Shop | 375.7099 | 0 | 582.3503
3 | Convenience / Rehab | Shop | 178.0107 | 0 | 275.9166
4 | Convenience / Rehab | Shop | 334.1641 | 0 | 517.9543
5 | Convenience / Rehab | Shop | 188.2441 | 0 | 291.7783
6 | Convenience / Rehab | Shop | 324.8844 | 0 | 503.5709
7 | Convenience / Rehab | Shop | 599.1393 | 0 | 928.6659
8 | Convenience / Rehab | Shop | 226.2281 | 0 | 350.6535
9 | Convenience / Rehab | Shop | 225.6253 | 0 | 349.7192
10 | Convenience / Rehab | Shop | 223.3907 | 0 | 346.2555
11 | Convenience / Rehab | Shop | 290.699 | 0 | 450.5835
12 | Convenience / Rehab | Shop | 222.0775 | 0 | 344.2201
13 | Convenience / Rehab | Shop | 226.9589 | 0 | 351.7864
14 | Convenience / Rehab | Shop | 222.0775 | 0 | 344.2201
15 | Convenience / Rehab | Shop | 225.8513 | 0 | 350.0696
16 | Convenience / Rehab | Shop | 228.002 | 0 | 353.4031
17 | Convenience / Rehab | Shop | 222.0775 | 0 | 344.2201
18 | Convenience / Rehab | Shop | 728.7755 | 0 | 1129.6021
19 | Convenience / Rehab | Shop | 230.4519 | 0 | 357.2004
20 | Convenience / Rehab | Shop | 227.3604 | 0 | 352.4087
21 | Convenience / Rehab | Shop | 419.2438 | 0 | 649.8279
22 | Convenience / Rehab | Shop | 51.5865 | 0 | 79.959
23 | Convenience / Rehab | Shop | 51.5865 | 0 | 79.959
24 | Convenience / Rehab | Shop | 51.5865 | 0 | 79.959
25 | Convenience / Rehab | Shop | 221.9827 | 0 | 344.0733
26 | Convenience / Rehab | Shop | 224.198 | 0 | 347.5069
27 | Convenience / Rehab | Shop | 224.198 | 0 | 347.5069
28 | Convenience / Rehab | Shop | 69.8584 | 0 | 108.2805
29 | Convenience / Rehab | Shop | 53.9815 | 0 | 83.6713
30 | Convenience / Rehab | Shop | 61.2848 | 0 | 94.9915
31 | Convenience / Rehab | Shop | 230.285 | 0 | 356.9418
32 | Convenience / Rehab | Shop | 224.9073 | 0 | 348.6063
33 | Convenience / Rehab | Shop | 222.7168 | 0 | 345.2111
34 | Convenience / Rehab | Shop | 224.6253 | 0 | 348.1692
35 | Convenience / Rehab | Shop (Duplex with 1st Floor) | 447.4789 | 0 | 693.5922
36 | Convenience / Rehab | Shop | 224.213 | 0 | 347.5302
37 | Convenience / Rehab | Shop | 227.4595 | 0 | 352.5622
38 | Convenience / Rehab | Shop | 273.2711 | 0 | 423.5701
39 | Convenience / Rehab | Shop | 225.5908 | 0 | 349.6658
40 | Convenience / Rehab | Shop | 225.6511 | 0 | 349.7592
41 | Convenience / Rehab | Shop | 330.9446 | 0 | 512.9641
42 | Convenience / Rehab | Shop | 225.7803 | 0 | 349.9594
43 | Convenience / Rehab | Shop (Duplex with 1st Floor) | 506.9941 | 0 | 785.8408
44 | Convenience / Rehab | Shop | 224.1355 | 0 | 347.4101
45 | Convenience / Rehab | Shop | 223.6609 | 0 | 346.6743
46 | Convenience / Rehab | Shop | 224.2626 | 0 | 347.607
47 | Convenience / Rehab | Shop | 193.7994 | 0 | 300.389
1st Floor
1 | Sale | IT Office | 850.7618 | 0 | 1318.6808 | 1st Floor
2 | Sale | IT Office | 330.599 | 0 | 512.4285
3 | Sale | IT Office | 548.344 | 0 | 849.9332
4 | Sale | IT Office | 409.779 | 0 | 635.1575
5 | Sale | IT Office | 389.984 | 0 | 604.4752
6 | Sale | IT Office | 409.779 | 0 | 635.1575
7 | Sale | IT Office | 430.3006 | 0 | 666.9659
8 | Sale | IT Office | 95.5197 | 0 | 148.0556
9 | Sale | IT Office | 276.9836 | 0 | 429.3245
10 | Sale | IT Office | 1010.1799 | 0 | 1565.7788
11 | Sale | IT Office | 454.864 | 0 | 705.0393
12 | Sale | IT Office | 372.0178 | 0 | 576.6276
13 | Sale | IT Office | 447.1742 | 0 | 693.1201
14 | Sale | IT Office | 688.0833 | 0 | 1066.5291
15 | Sale | IT Office | 556.2362 | 0 | 862.166
16 | Sale | IT Office | 583.9104 | 0 | 905.0611
17 | Sale | IT Office | 455.4528 | 0 | 705.9519
18 | Rehab | IT Office | 931.6156 | 0 | 1444.0042
19 | Sale | IT Office | 327.4624 | 0 | 507.5667
20 | Sale | IT Office | 583.9104 | 0 | 905.0611
21 | Sale | IT Office | 548.8564 | 0 | 850.7274
22 | Sale | IT Office | 473.2134 | 0 | 733.4808
23 | Sale | IT Office | 1158.8878 | 0 | 1796.276
24 | Sale | IT Office | 1138.1337 | 0 | 1764.1072
Flat No. (Approved Plan) | Sale / Rehab | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A
2nd & 3rd Podium Floor for Parking
4th Floor for Residential
1 | Rehab | 3BHK | 691.9099 | 0 | 1037.8649 | 4th Floor for Residential |  | 60.2833
2 | Sale | 2BHK | 564.5718 | 0 | 846.8577
3 | Rehab | 2BHK | 576.6275 | 0 | 864.9412 |  |  |  | 21041.8923
4 | Rehab | 3BHK | 762.9523 | 0 | 1144.4285
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784 |  |  |  | 20311.7092 | 20470.3944
5th & 6th Floor
1 | Rehab | 3BHK | 762.9523 | 0 | 1144.4285 | 5th & 6th Floor |  | 60.2833
2 | Rehab | 2BHK | 576.6275 | 0 | 864.9412
3 | Rehab | 2BHK | 576.6275 | 0 | 864.9412 |  |  |  | 21041.8923
4 | Rehab | 3BHK | 762.9523 | 0 | 1144.4285
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784 |  |  |  | 20311.7092 | 20470.3944
7th Floor (Part Refuge Area & Society Office)
1 | Rehab | 3BHK | 762.9523 | 0 | 1144.4285 | 7th Floor (Part Refuge Area & Society Office) |  | 60.2833
2 | Rehab | 2BHK | 576.6275 | 0 | 864.9412
3 | - | Society Office & Refuge Area | [6 empty] | #DIV/0!
4 | Rehab | 3BHK | 783.6192 | 0 | 1175.4288
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784 |  |  |  | 20311.7092 | 20470.3944
8th Floor
1 | Rehab | 3BHK | 783.6192 | 0 | 1175.4288 | 8th Floor |  | 60.2833
2 | Rehab | 2BHK | 597.2944 | 0 | 895.9415
3 | Rehab | 2BHK | 597.2944 | 0 | 895.9415 |  |  |  | 20313.8254
4 | Rehab | 3BHK | 783.6192 | 0 | 1175.4288
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784 |  |  |  | 20311.7092 | 20470.3944
9th Floor
1 | Rehab | 3BHK | 783.6192 | 0 | 1175.4288 | 9th Floor |  | 60.2833
2 | Rehab | 2BHK | 597.2944 | 0 | 895.9415
3 | Rehab | 2BHK | 597.2944 | 0 | 895.9415 |  |  |  | 20313.8254
4 | Rehab | 3BHK | 783.6192 | 0 | 1175.4288
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784 |  |  |  | 20311.7092 | 20470.3944
Wing B
2nd & 3rd Podium Floor for Parking | [9 empty] | 20000
4th Floor for Residential
1 | Rehab | 3.5BHK | 994.2707 | 0 | 1491.406 | 4th Floor for Residential
2 | Rehab | 3.5BHK | 1087.3793 | 0 | 1631.0689
5th & 6th Floor
1 | Sale | 2BHK | 605.9056 | 0 | 908.8583 | 5th & 6th Floor
2 | Sale | 2BHK | 605.9056 | 0 | 908.8583
3 | Sale | 2BHK | 605.9056 | 0 | 908.8583
4 | Sale | 2BHK | 605.9056 | 0 | 908.8583
7th Floor (Part Refuge Area)
1 | Sale | 2BHK | 605.9056 | 0 | 908.8583 | 7th Floor (Part Refuge Area)
2 | Sale | 2BHK | 605.9056 | 0 | 908.8583
3 | - | Refuge Area
4 | -
8th Floor
1 | Sale | 2BHK | 605.9056 | 0 | 908.8583 | 8th Floor
2 | Sale | 2BHK | 605.9056 | 0 | 908.8583
3 | Sale | 2BHK | 605.9056 | 0 | 908.8583
4 | Sale | 2BHK | 605.9056 | 0 | 908.8583
9th Floor
1 | Sale | 2BHK | 605.9056 | 0 | 908.8583 | 9th Floor
2 | Sale | 2BHK | 605.9056 | 0 | 908.8583
3 | Sale | 2BHK | 605.9056 | 0 | 908.8583
4 | Sale | 2BHK | 605.9056 | 0 | 908.8583
Wing C
2nd & 3rd Podium Floor for Parking
4th Floor for Residential
1 | Rehab | 3BHK | 767.7961 | 0 | 1151.6942 | 4th Floor for Residential
2 | Rehab | 1BHK | 482.5501 | 0 | 723.8252
3 | Rehab | 2BHK | 602.5687 | 0 | 903.8531 |  |  |  | 21795.5777
4 | Rehab | 3BHK | 782.5428 | 0 | 1173.8142 |  |  |  | 20360.9737
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784
5th & 6th Floor
1 | Rehab | 3BHK | 782.5428 | 0 | 1173.8142 | 5th & 6th Floor
2 | Rehab | 2BHK | 632.9232 | 0 | 949.3848
3 | Rehab | 2BHK | 634.9684 | 0 | 952.4525
4 | Rehab | 3BHK | 782.5428 | 0 | 1173.8142
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784
7th Floor (Part Refuge Area)
1 | - | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 | -
3 | Rehab | 2BHK | 645.7324 | 0 | 968.5985
4 | Rehab | 3BHK | 782.5428 | 0 | 1173.8142
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784
8th Floor
1 | Rehab | 3BHK | 782.5428 | 0 | 1173.8142 | 8th Floor
2 | Rehab | 2BHK | 643.4719 | 0 | 965.2079
3 | Rehab | 2BHK | 645.7324 | 0 | 968.5985
4 | Rehab | 3BHK | 782.5428 | 0 | 1173.8142
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784
9th Floor (Part Terrace Area)
1 | Rehab | 3BHK | 805.1472 | 0 | 1207.7208 | 9th Floor (Part Terrace Area)
2 | Sale | 2BHK | 643.4719 | 0 | 965.2079
3 | - | Terrace Area
4 | -
5 | Sale | 1BHK | 420.1189 | 0 | 630.1784
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We refer Civil Aviation NOC from MCGM site.
* | As per layout, Nalla is located on North side to the project.
* | As the project is redevelopement project but rehab statement or rehab flats for residential unit is not mentioned in approved layout plan & floor plan.
* | We have updated latest CC & approved floor plans (On 29/02/2024).
* | Recommended Rates / Other charges of the Property have been revised on 28/08/2024.
* | We have updated latest CC from MCGM site ( On 07/04/2025).
* | Validity of CC is expired on 06/06/2025. Please provide revised CC & Please provide revised approved plans dtd. 21/03/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Alpine Primo
Layout :
Google Map :
Formulas:
Andheri = [Andheri, row above]
Wing A
Wing B
Wing C
Wing B
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D59: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC