## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-11
Name of the builder group |  |  |  |  | M/s. Labdhi Lifestyle Limited
Name of the builder company |  |  |  |  | M/s. Labdhi Lifestyle Limited
Name of the Project |  |  |  |  | Labdhi Gardens
Contact Details ( Name & Contect No.) |  |  |  |  | 7666818181
Site Meet Person Contact Details ( Name & Contect No.) |  |  |  |  | Miss. Pooja 8446002783
Name / No of the Building |  |  |  |  | Building (Camellia & Balsam) Building (Aaster) Building (Zinnia & Yarrow) Building (Xyris) Building (Dahlia) Building (Wisteria)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, NA order cum CC, Cost Sheet
RERA No. |  |  |  |  | Phase 6 (Wisteria) - P52000019683 Phase 7 (Xyris) - P52000019815 Phase 8 (Zinnia & Yarrow) - P52000019661 Phase 9 (Aaster) - P52000019710 Phase 10 (Camellia & Balsam) - P52000019679 Phase 11 (Dahlia) - P52000019728
Project location details |  | Labdhi Gardens, Sr no.66/2, Mr no.7280/13, Karjat-Murbad road, Dahivali T. Varedi, Karjat, Raigad.
Sr no |  | 66/2 |  |  | Mr no | 7280/13 | Locality | Dahivali T. Varedi
Road | Karjat-Murbad road |  |  |  | District | Raigad
City | Karjat |  |  |  | Pin Code | 410101
Near by Landmark |  | Anandvan Krishi Phalodyan Society |  |  | Distance from city centre: |  | About 3.6 Km from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Varedi village |  | Dahiwali |  | Open space |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.0476 |  | Longitude |  | 73.3342
Location Link |  | https://goo.gl/maps/8BDMbQXXyZ6AkZG36
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 14337
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.2136
Total FSI availaible for the project |  |  |  |  | 1.3136
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 18833.1
Total number of Buildings |  |  |  |  | 8 Buildings
Approval Detail : Plan approval
Layout Approval No |  | MS/LNA1(B)/PK-157/2018 |  |  |  | Dated | 01/02/2019.
Approved Floor plan No. |  | MS/LNA1(B)/PK-157/2018 |  |  |  | Dated | 01/02/2019.
Na order cum CC |  | MS/LNA1(B)/PK-157/2018 |  |  |  | Dated | 01/02/2019.
Valid Up to: Wisteria = G + 1st to 6th floor Xyris, Zinnia, Yarrow, Aaster, Camellia & Balsam = G + 1st to 7th floor Dahlia = G + 1st floor
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 01/02/2019. |  | Expected Completion |  | 31/12/2025. |  | 30/12/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 18833.1 |  | Approved no of units |  | Flats = 495 Shops = 12
Approved no of Floors |  | Wisteria = G + 1st to 6th floor Xyris, Zinnia, Yarrow, Aaster, Camellia & Balsam = G + 1st to 7th floor Dahlia = G + 1st floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Camellia = G + 1st to 7th floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 61.79% |  | 82.14% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 42.86% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Balsam = G + 1st to 7th floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 92.86% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 71.43% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Aaster = G + 1st to 7th floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 92.86% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 71.43% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Zinnia, Yarrow & Xyris = G + 1st to 7th floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth in process | 5.25
Possession |  | 7 | 100% | [5 empty] | Plinth completed | 7
Construction details: |  | Yarrow = G + 1st to 7th floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 90.71% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 28.57% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Xyris = G + 1st to 7th floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 90% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 14.29% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Dahlia = G + 1st floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 1
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 30% |  | 60% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 1 | 50% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Wisteria = G + 1st to 6th floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 6
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.5
Excavation |  | 6 | 100% |  | 90.83% |  | 95% |  | Excavation in process | 3
Plinth |  | 6 | 100% | [5 empty] | Excavation Completed | 6
RCC (Including podiums) |  | 7 | 100% | [5 empty] | Footing in Process | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Footing Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 83.33% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 33.33% | [5 empty] | Plinth in process | 4.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 6
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) (for Building (Camellia, Balsam, Yarrow, Xyris, Dahlia, Wisteria) | [5 empty] | 3300
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) (for Aaster & Zinnia Building) | [5 empty] | 3800 |  |  | 30/11/2022 BY AKASH
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6000
Water & Electricity Charges | [5 empty] | 100000/- |  |  |  | 156.25 | 484.375
Club House Charges | [5 empty] | 50000/- |  |  |  | 78.125
Recommended rate of Parking | [5 empty] | 200000/- |  |  |  | 250
Development Charges | [5 empty] | 2,50,000/-
Distressed valuation of the Property | [5 empty] | 3040
Residential area details :
Building & Wing |  | Total Flats | Total Carpet Area |  |  | Total Saleable Area
Camellia |  | 28 | 17116.6168 |  |  | 32732
Balsam |  | 60 | 23328.7419 |  |  | 38241.7633
Zinnia |  | 75 | 27045.0505 |  |  | 39215.3233
Yarrow |  | 84 | 30743.6363 |  |  | 44578.2726
Aaster |  | 62 | 22294.7951 |  |  | 32327.4528
Dahlia |  | 8 | 2741.4186 |  |  | 4366.0592
Xyris |  | 95 | 27768.0092 |  |  | 40263.6133
Wisteria |  | 83 | 24627.1494 |  |  | 35709.3666
Total |  | 495 | 175665.4176 |  |  | 267433.8512
Commercisl area details :
Building & Wing |  | Total Carpet Area |  |  |  | Total Saleable Area
Dahila |  | 3056.6531 |  |  |  | 4584.9796
Building details Floor Wise
Details of Flats in Building
Flat No. (as per sale plan) | Flat No. (as per approved plan) | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Type - Camellia
Ground Floor is for Parking
1st to 7th Floor
1 |  | 3 BHK | 573.3445 |  | 0 | 1169 | N | 1st to 7th Floor
2 |  | 3 BHK | 624.608 |  | 0 | 1169 | N
3 |  | 3 BHK | 623.6392 |  | 0 | 1169 | N
4 |  | 3 BHK | 623.6392 |  | 0 | 1169 | N
Type - Balsam
Ground Floor is for Parking & Residential
2 |  | 2 BHK | 404.9417 |  | 0 | 786 | N | Ground floor
4 |  | 2 BHK | 401.0666 |  | 0 | 786 | N
6 |  | 2 BHK | 401.0666 |  | 0 | 786 | N
8 |  | 2 BHK | 402.6812 |  | 0 | 786 | N
1st to 7th Floor
1 |  | 2 BHK | 434.984 |  | 0 | 786 | N | 1st to 7th Floor
2 |  | 2 BHK | 423.7518 |  | 0 | 786 | N
3 |  | 2 BHK | 448.0784 |  | 0 | 786 | N
4 |  | 2 BHK | 448.0784 |  | 0 | 786 | N
5 |  | 2 BHK | 448.0784 |  | 0 | 786 | N | 1st to 7th Floor
6 |  | 2 BHK | 448.0784 |  | 0 | 786 | N
7 |  | 2 BHK | 446.5715 |  | 0 | 786 | N
8 |  | 2 BHK | 440.0754 |  | 0 | 786 | N
Type - Zinnia
Ground Floor is for Parking & Residential
2 |  | 1 BHK | 339.8733 |  | 0 | 640 | N | Ground floor
4 |  | 1 BHK | 339.8733 |  | 0 | 640 | N
6 |  | 1 BHK | 339.8733 |  | 0 | 640 | N
7 |  | 1 BHK | 335.8906 |  | 0 | 640 | N
8 |  | 1 BHK | 339.8733 |  | 0 | 640 | N
1st to 7th Floor
1 |  | 1 BHK | 362.1117 |  | 0 | 640 | N | 1st to 7th Floor
2 |  | 1 BHK | 366.7402 |  | 0 | 640 | N
3 |  | 1 BHK | 384.0864 |  | 0 | 640 | N
4 |  | 1 BHK | 366.7402 |  | 0 | 640 | N
5 |  | 1 BHK | 384.0864 |  | 0 | 640 | N
6 |  | 1 BHK | 366.7402 |  | 0 | 640 | N
9 | 7 | 1 BHK | 384.0864 |  | 0 | 640 | N
7 | 8 | 1 BHK | 366.7402 |  | 0 | 640 | N
8 | 9 | 1 BHK | 320.0245 |  | 0 | 640 | N
10 | 10 | 1 BHK | 320.0245 |  | 0 | 640 | N
Type - Yarrow
Ground Floor is for Parking & Residential
2 |  | 1 BHK | 337.2361 |  | 0 | 640 | N | Ground floor
4 |  | 1 BHK | 339.8733 |  | 0 | 640 | N
5 |  | 1 BHK | 340.7344 |  | 0 | 640 | N
6 |  | 1 BHK | 339.8733 |  | 0 | 640 | N
7 |  | 1 BHK | 339.8733 |  | 0 | 640 | N
8 |  | 1 BHK | 341.8108 |  | 0 | 640 | N
9 |  | 2 BHK | 464.8972 |  | 0 | 786 | N
1st to 7th Floor
1 |  | 1 BHK | 362.1117 |  | 0 | 640 | N | 1st to 7th Floor
2 |  | 1 BHK | 366.7402 |  | 0 | 640 | N
3 |  | 1 BHK | 375.3676 |  | 0 | 640 | N
4 |  | 1 BHK | 366.7402 |  | 0 | 640 | N
5 |  | 1 BHK | 375.3676 |  | 0 | 640 | N
6 |  | 1 BHK | 366.7402 |  | 0 | 640 | N
7 |  | 1 BHK | 358.0214 |  | 0 | 640 | N
8 |  | 1 BHK | 315.073 |  | 0 | 640 | N
9 |  | 2 BHK | 517.8829 |  | 0 | 786 | N
10 |  | 1 BHK | 315.073 |  | 0 | 640 | N
11 |  | 1 BHK | 315.073 |  | 0 | 640 | N
Type - Aaster
Ground Floor is for Parking & Residential
1 |  | 1 BHK | 356.396 |  | 0 | 640 | N | Ground floor
2 |  | 1 BHK | 335.2986 |  | 0 | 640 | N
4 |  | 1 BHK | 335.2986 |  | 0 | 640 | N
6 |  | 1 BHK | 335.2986 |  | 0 | 640 | N
7 |  | 1 BHK | 335.2986 |  | 0 | 640 | N
8 |  | 1 BHK | 356.396 |  | 0 | 640 | N
1st to 7th Floor
1 |  | 1 BHK | 403.1925 |  | 0 | 640 | N | 1st to 7th Floor
2 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
3 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
4 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
5 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
6 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
7 |  | 1 BHK | 403.1925 |  | 0 | 640 | N
8 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
Type - Dahlia
Ground Floor is for Parking & Residential
1 |  | Shop | 286.3224 |  | 0 | 429.4836 | N | Ground floor
2 |  | Shop | 368.1288 |  | 0 | 552.1932 | N
3 |  | Shop | 368.1288 |  | 0 | 552.1932 | N
4 |  | Shop | 223.0301 |  | 0 | 334.5451 | N
5 |  | Shop | 132.9354 |  | 0 | 199.4031 | N
6 |  | Shop | 305.8052 |  | 0 | 458.7079 | N
7 |  | Shop | 305.8052 |  | 0 | 458.7079 | N
8 |  | Shop | 132.9354 |  | 0 | 199.4031 | N
9 |  | Shop | 132.9354 |  | 0 | 199.4031 | N
10 |  | Shop | 305.8052 |  | 0 | 458.7079 | N
11 |  | Shop | 172.9775 |  | 0 | 259.4662 | N
12 |  | Shop | 321.8436 |  | 0 | 482.7654 | N
1st Floor
1 |  | 1 BHK | 342.4028 |  | 198.5958 | 640 | N | 1st Floor
2 |  | 1 BHK | 364.3183 |  | 0 | 640 | N
3 |  | 1 BHK | 316.4616 |  | 192.4065 | 640 | N
4 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
5 |  | 1 BHK | 316.4616 |  | 192.4065 | 640 | N
6 |  | 1 BHK | 347.5265 |  | 0 | 640 | N
7 |  | 1 BHK | 342.4028 |  | 198.5958 | 640 | N
8 |  | 1 BHK | 364.3183 |  | 0 | 640 | N
Type - Xyris
Ground Floor is for Parking & Residential
4 | 1 | 1 RK | 285.9995 |  | 0 | 502 | N | Ground floor
6 | 2 | 1 RK | 285.9995 |  | 0 | 502 | N
8 | 3 | 1 RK | 288.5828 |  | 0 | 502 | N
10 | 4 | 1 RK | 288.5828 |  | 0 | 502 | N
12 | 5 | 1 RK | 281.8015 |  | 0 | 502 | N
11 | 6 | 1 RK | 289.7131 |  | 0 | 502 | N
9 | 7 | 1 RK | 296.4944 |  | 0 | 502 | N
7 | 8 | 1 RK | 296.4944 |  | 0 | 502 | N
5 | 9 | 1 RK | 296.4944 |  | 0 | 502 | N
1 | 11 | 1 RK | 281.8015 |  | 0 | 502 | N
2 | 12 | 1 RK | 279.2182 |  | 0 | 502 | N
1st to 7th Floor
4 | 1 | 1 RK | 287.0759 |  | 0 | 502 | N | 1st to 7th Floor
6 | 2 | 1 RK | 287.0759 |  | 0 | 502 | N
8 | 3 | 1 RK | 251.8884 |  | 0 | 502 | N
10 | 4 | 1 RK | 251.8884 |  | 0 | 502 | N
12 | 5 | 1 RK | 245.107 |  | 0 | 502 | N
11 | 6 | 1 RK | 245.107 |  | 0 | 502 | N
9 | 7 | 1 RK | 251.8884 |  | 0 | 502 | N
7 | 8 | 1 RK | 251.8884 |  | 0 | 502 | N
5 | 9 | 1 RK | 251.8884 |  | 0 | 502 | N
3 | 10 | 1 RK | 251.8884 |  | 0 | 502 | N
1 | 11 | 1 RK | 284.8693 |  | 0 | 502 | N
2 | 12 | 1 RK | 280.2946 |  | 0 | 502 | N
Type - Wisteria
Ground Floor is for Parking & Residential
4 | 1 | 1 RK | 285.9995 |  | 0 | 502 | N | Ground floor
6 | 2 | 1 RK | 285.9995 |  | 0 | 502 | N
8 | 3 | 1 RK | 288.5828 |  | 0 | 502 | N
10 | 4 | 1 RK | 288.5828 |  | 0 | 502 | N
12 | 5 | 1 RK | 281.8015 |  | 0 | 502 | N
11 | 6 | 1 RK | 289.7131 |  | 0 | 502 | N
9 | 7 | 1 RK | 296.4944 |  | 0 | 502 | N
7 | 8 | 1 RK | 296.4944 |  | 0 | 502 | N
5 | 9 | 1 RK | 296.4944 |  | 0 | 502 | N
1 | 11 | 1 RK | 281.8015 |  | 0 | 502 | N
2 | 12 | 1 RK | 279.2182 |  | 0 | 502 | N
1st to 6th Floor
4 | 1 | 1 RK | 287.0759 |  | 0 | 502 | N | 1st to 6th Floor
6 | 2 | 1 RK | 287.0759 |  | 0 | 502 | N
8 | 3 | 1 RK | 251.8884 |  | 0 | 502 | N
10 | 4 | 1 RK | 251.8884 |  | 0 | 502 | N
12 | 5 | 1 RK | 245.107 |  | 0 | 502 | N
11 | 6 | 1 RK | 245.107 |  | 0 | 502 | N
9 | 7 | 1 RK | 251.8884 |  | 0 | 502 | N
7 | 8 | 1 RK | 251.8884 |  | 0 | 502 | N
5 | 9 | 1 RK | 251.8884 |  | 0 | 502 | N
3 | 10 | 1 RK | 251.8884 |  | 0 | 502 | N
1 | 11 | 1 RK | 284.8693 |  | 0 | 502 | N
2 | 12 | 1 RK | 280.2946 |  | 0 | 502 | N
Remarks:
1. Cammellia |  |  |  | Construction work is in process at the time of Visit. (Slow Speed)
2. Aaster, Balsam & Wisteria |  |  |  | Finishing work is pending (Very Slow Speed).
3. Zinnia, Xyris, Yarrow |  |  |  | All work Completed. Please provide OC.
4. Dahlia |  |  |  | Construction work is same as last visit dtd. 07/04/2025.
Construction work was same as visit (25/05/2021).
2. We considered Flat Saleable area as per Builder area sheet & Shop's area as per our calculation 3. We considered Carpet area as per Approved Plan. 4. We have given rate verify by Market Inquire. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Since the project has received first CC on 01/02/2019., But construction work of Cammellia & Dahlia is under construction. 7. On site, we meet Mr.Sagar Kavale - 8208228480
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Labdhi Gardens
Google Map :
Aster
Camellia
Dahlia
Camellia
Balsam
Aaster
Wisteria
Zinnia
Xyris
Yarrow
Dahlia

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
magicbricks | Labdhi Gardens | 1BHK | 0 | 675 | 4148.1481 | 2800000
magicbricks | Labdhi Gardens | 1BHK | 0 | 600 | 4000 | 2400000
magicbricks | Labdhi Gardens | 1BHK | 0 | 502 | 3605.5777 | 1810000
magicbricks | Labdhi Gardens | 1BHK | 0 | 600 | 3333.3333 | 2000000
99Acers | Labdhi Gardens | 1BHK | 319.37 | 463.0865 | 3679.6581 | 1704000
99Acers | Labdhi Gardens | 2BHK | 501 | 726.45 | 3551.5177 | 2580000
99Acers | Labdhi Gardens | 5BHK | 701 | 1016.45 | 3652.9096 | 3713000
Average |  |  | 0 | 0 | 3710.1635
Valuation Adopted |  |  |  |  | 3700

## Note
23/06/2020. | Pratiksha | We considered Flat rate as per builder cost sheet & Shop'srate as per Market Inquire
Matched cost Sheet (16/11/2019).
02/10/2020. | Dhanashree | OLD APF
rate has not Changed.

## Balsam %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 62.5 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 5 | 0 | Progress |  |  | 10 | 25 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 18.75 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 25 | 18.75
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 35 | 48.75

## Camellia% (2)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 7 | 70
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 0 | 0 | Progress |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 7 | 27
| 7 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 7 | 27

## Aaster %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## Zinnia %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 87.5 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 7 | 42.8571 | Progress |  |  | 10 | 35 | 6.4286 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 26.25 | 6.4286 | 0 | 0 | 0 | 0
| 7 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 35 | 26.25
Finishing | Total Floor | completed Floor |  | Bricks | 6.4286 | 6.4286
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 51.4286 | 62.6786

## Xyris %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 85.7143 | Progress |  |  | 10 | 40 | 12.8571 | 1.4286 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 14.2857 | Recommended |  |  | 30 | 30 | 12.8571 | 1.4286 | 0 | 0 | 0
| 7 | 6 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 1 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 12.8571 | 12.8571
| 7 | 0 |  | Plaster | 1.4286 | 1.4286
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 64.2857 | 74.2857

## Yarrow %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 71.4286 | Progress |  |  | 10 | 40 | 10.7143 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 10.7143 | 0 | 0 | 0 | 0
| 7 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 10.7143 | 10.7143
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 60.7143 | 70.7143

## C % Wisteria
Particulars | totaL floor | 6
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 57.1429 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 7 | 4 | 0 | Progress |  |  | 10 | 22.8571 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 17.1429 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 6 | 0 | 0
Flooring | Total Floor | completed Floor
| 6 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 6 | 0 |  | RCC | 22.8571 | 17.1429
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 6 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 32.8571 | 47.1429

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3 | 3.9 | 11.7 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.9 | 2.1 | 3.99 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.4 | 3.25 | 7.8 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.45 | 2.15 | 5.2675 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2 | 2.25 | 4.5 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.7 | 1.2 | 2.04 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 2.1 | 2.52 | DB |  |  | 0 |  |  | 0
| toilet3 | 4.8 | 0.9 | 4.32 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 453.5681 | 42.1375 |  |  | 0 | 0 |  | 0 | 0
|  |  | 453.5681 | 42.1375