## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 15/07/2025
CPC Name: |  |  |  |  | Axis Goregoan
Date Of Property Visit |  |  |  |  | 2025-07-12
Name of the builder group |  |  |  |  | M/s.Satghare Builtcon PVT. LTD
Name of the builder company |  |  |  |  | M/s.Satghare Builtcon PVT. LTD
Name of the Project |  |  |  |  | Adore Garden
Name of the Project as per RERA |  |  |  |  | Adore Garden Bldg No 2 & 3
Contect Details ( Name & Contect No.) |  |  |  |  | 02502349844 / 9326038235
Name / no of the Building |  |  |  |  | Building No.2 & 3(Type D1 & Type D1a)/2 Buildings
Docouments Provided |  |  |  |  | Approved Layout, NA Order cum CC
RERA No. |  |  |  |  | P99000015769
Project location details |  | Adore Garden, Building No.2 & 3, Gut.No.61, 61/1 & 62, Umroli, Palghar.
Gut. No. | 61, 61/1 & 62 |  |  | Plot No. |  | NA | Locality | Umroli west
Road | Palghar Bhoisar Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401404
Near by Landmark |  | Umroli Market |  |  | Distance from city centre: |  | About 0.35 Km from Umroli raiway station Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Open |  | Open Plot |  | Vidhata Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.7534 |  | Longitude |  | 72.7582
Location Link |  | https://goo.gl/maps/dtfwe1cCvJjVzoAW6
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 6175.34
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5557.806
Total number of Buildings |  |  |  |  | 2 Buildings
Approval Detail : Plan approval
Layout Approval No |  | MHSL/KS.1/T.1/NP/SR-282/2017. |  |  |  | Dated | 31/12/2017.
Building plan approval No |  | MHSL/KS.1/T.1/NP/SR-282/2017. |  |  |  | Dated | 31/12/2017. | Expiry date:NA
NA Order cum Commencement of Construction |  | MHSL/KS.1/T.1/NP/SR-282/2017. Vaid up to : Type D1 & D1a = Gr. + 1st to 4th Floor |  |  |  | Dated | 31/12/2017. | Expiry date: One year from date of issue
Part O. Certificate No (Bldg No.3).: Mahsul/KS1/Te1/Bhogwata Pramaanpatra/SR-10/2021 |  |  |  |  | Date of approval: 08/07/2021 |  |  | Expiry date: NA
Commencement date of construction |  |  | 31/12/2017. |  | Expected Completion |  | 2025-12-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5557.806 |  | Approved no of units |  | Flats = 47, Shops = 20 Offices = 09
Approved no of Floors |  |  | Gr. + 1st to 4th Floor
Quality of construction: Good |  |  |  |  | Projected life: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: Building no.2 = Gr. + 1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 3 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 3 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 93.75% |  | 95%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 3 | 75% | [5 empty] | Plinth completed |  | 4
Possession |  | 0 | 0%
Construction details: Building no.3 = Gr. + 1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Part OC Received. | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. Part OC Received.
Excavation |  | 4 | 100% |  | 100% |  | 100%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth completed |  | 4
Possession |  | 4 | 100%
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3000
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 7650
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) | [5 empty] | 6000
Society formation charges | [5 empty] | 75000/-
Recommended rate of Parking | [5 empty] | 100000
Distressed valuation of the Property | [5 empty] | 2400
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No. 2 ( Type D1 )
Ground floor for shops & flat
1 |  | Shop | 142.0848 |  | 0 | 213.1272 | N | Ground floor for shops & flat |  | 13.2 | 10.764
2 |  | Shop | 121.8485 |  | 0 | 182.7727 | N |  |  | 11.32 | 10.764
3 |  | Shop | 164.2586 |  | 0 | 246.388 | N |  |  | 15.26 | 10.764
4 |  | Shop | 158.3384 |  | 0 | 237.5077 | N |  |  | 14.71 | 10.764
5 |  | Shop | 101.5045 |  | 0 | 152.2568 | N |  |  | 9.43 | 10.764
6 |  | Shop | 139.7167 |  | 0 | 209.5751 | N |  |  | 12.98 | 10.764
7 |  | Shop | 129.168 |  | 0 | 193.752 | N |  |  | 12 | 10.764
8 |  | Shop | 164.2586 |  | 0 | 246.388 | N |  |  | 15.26 | 10.764
9 |  | Shop | 121.8485 |  | 0 | 182.7727 | N |  |  | 11.32 | 10.764
10 |  | Shop | 102.1504 |  | 0 | 153.2255 | N |  |  | 9.49 | 10.764
1 |  | 1BHK | 340.573 |  | 0 | 565 | N |  | 1 | 31.64 | 10.764
1st floor
1 |  | Office | 97.7371 |  | 0 | 146.6057 | N | 1st floor |  | 9.08 | 10.764
2 |  | Office | 87.9419 |  | 0 | 131.9128 | N |  |  | 8.17 | 10.764
3 |  | Office | 119.911 |  | 0 | 179.8664 | N |  |  | 11.14 | 10.764
4 |  | Office | 113.9908 |  | 0 | 170.9861 | N |  |  | 10.59 | 10.764
5 |  | Office | 64.3687 |  | 0 | 96.5531 | N |  |  | 5.98 | 10.764
6 |  | Office | 84.7127 |  | 0 | 127.069 | N |  |  | 7.87 | 10.764
7 |  | Office | 119.911 |  | 0 | 179.8664 | N |  |  | 11.14 | 10.764
8 |  | Office | 87.9419 |  | 0 | 131.9128 | N |  |  | 8.17 | 10.764
9 |  | Office | 97.7371 |  | 0 | 146.6057 | N |  |  | 9.08 | 10.764
1 |  | 1BHK | 340.573 |  | 0 | 565 | N |  |  | 31.64 | 10.764
2 |  | 1BHK | 340.573 |  | 0 | 565 | N |  |  | 31.64 | 10.764
3 |  | 1BHK | 341.0035 |  | 0 | 565 | N |  | 3 | 31.68 | 10.764
2nd to 4th floor
1 |  | 1BHK | 341.0035 |  | 0 | 565 | N | 2nd to 4th floor |  | 31.68 | 10.764 | 1.6569
2 |  | 2BHK | 438.5254 |  | 0 | 735 | N |  |  | 40.74 | 10.764
3 |  | 1BHK | 351.014 |  | 0 | 565 | N |  |  | 32.61 | 10.764
4 |  | 1BHK | 340.573 |  | 0 | 565 | N |  |  | 31.64 | 10.764
5 |  | 1BHK | 340.573 |  | 0 | 565 | N |  |  | 31.64 | 10.764
6 |  | 1BHK | 341.0035 |  | 0 | 565 | N |  | 18 | 31.68 | 10.764
Building No. 3 ( Type D1a )
Ground floor for shops & flat
1 |  | Shop | 142.0848 |  | 0 | 213.1272 | N | Ground floor for shops & flat |  | 13.2 | 10.764
2 |  | Shop | 121.8485 |  | 0 | 182.7727 | N |  |  | 11.32 | 10.764
3 |  | Shop | 164.2586 |  | 0 | 246.388 | N |  |  | 15.26 | 10.764
4 |  | Shop | 158.3384 |  | 0 | 237.5077 | N |  |  | 14.71 | 10.764
5 |  | Shop | 101.5045 |  | 0 | 152.2568 | N |  |  | 9.43 | 10.764
6 |  | Shop | 139.7167 |  | 0 | 209.5751 | N |  |  | 12.98 | 10.764
7 |  | Shop | 129.168 |  | 0 | 193.752 | N |  |  | 12 | 10.764
8 |  | Shop | 164.2586 |  | 0 | 246.388 | N |  |  | 15.26 | 10.764
9 |  | Shop | 121.8485 |  | 0 | 182.7727 | N |  |  | 11.32 | 10.764
10 |  | Shop | 102.1504 |  | 0 | 153.2255 | N |  |  | 9.49 | 10.764
1 |  | 1BHK | 340.573 |  | 0 | 565 | N |  | 1 | 31.64 | 10.764 |  | 3097.3451
1st to 4th floor
1 |  | 1BHK | 341.0035 |  | 0 | 565 | N | 1st to 4th floor |  | 31.68 | 10.764
2 |  | 2BHK | 438.5254 |  | 0 | 735 | N |  |  | 40.74 | 10.764 |  | 3204.0816
3 |  | 1BHK | 351.014 |  | 0 | 565 | N |  |  | 32.61 | 10.764
4 |  | 1BHK | 340.573 |  | 0 | 565 | N |  |  | 31.64 | 10.764
5 |  | 1BHK | 340.573 |  | 0 | 565 | N |  |  | 31.64 | 10.764
6 |  | 1BHK | 341.0035 |  | 0 | 565 | N |  | 24 | 31.68 | 10.764
Remarks: 1. Bldg no.2 - Construction Stage is same as last visit dtd.11/01/2025 (Lift work is pending.) Bldg no.3 - All work completed. Part OC received . 2. We considered Shop & Office Saleable area as per our calculation. 3. We considered Flat Saleable area as per builder area sheet. 4. We considered Carpet area as per Approved Plan. 5. We have given rate verify by Market Inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We have updated Part OC from RERA site.(On 14/01/2025). 8. On site, we meet Mr. Sagar (Site Supervisor) - 9892266672. | [8 empty] | 47
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  |  | Adore Garden
Google Map :
Building No.3
Bldg
No.2
Bldg no.3

## C % (B2)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 20 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 1 | 0 | Progress |  |  | 10 | 8 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 6 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 8 | 6
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 18 | 36

## B3 - C %
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 0.625 | 0
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 0.625 | 0
| 4 | 4 | 100
plaster | Total Floor | completed Floor | 12.5
| 4 | 4 | 0
Flooring | Total Floor | completed Floor
| 4 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0.5 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 0.625 | 0.625
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 85.625 | 90.625

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.43 | 9.4325 | CB | 2.75 | 3.35 | 9.2125 | 2.75 | 3.35 | 9.2125
|  | 2.75 | 1.2 | 3.3 | FB | 2.05 | 1.8 | 3.69 | 1.2 | 2.75 | 3.3
|  |  |  | 0 |  | 3.05 | 2.8 | 8.54 | 2.05 | 1.8 | 3.69
| kitch |  |  | 0 | CB | 1.2 | 1.8 | 2.16 | 3.05 | 2.8 | 8.54
|  |  |  | 0 | FB | 1.2 | 1.8 | 2.16 | 1.2 | 1.8 | 2.16
|  |  |  | 0 |  | 1.05 | 2.75 | 2.8875 | 1.2 | 1.8 | 2.16
|  |  |  | 0 |  | 1.8 | 1.5 | 2.7 | 1.5 | 0.45 | 0.675
| Bed1 |  |  | 0 | CB | 2.4 | 1 | 2.4 | 2.4 | 1 | 2.4
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 137.0526 | 12.7325 |  |  | 363.285 | 33.75 |  | 345.928 | 32.1375

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Note
17/06/2020. | Pratiksha | 5. We considered flat rate as per Builder cost sheet.
6. We considered recommended Shop & Office rate as per Market Inquire.

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Adore Garden | 1BHK | 0 | 575 | 3043.4783 | 1750000
housing. | Adore Garden | 2BHK | 0 | 745 | 3161.0738 | 2355000
housing. | Adore Garden | 3BHK | 1466 | 2345.6 | 32528.9905 | 76300000
Magic Brick | Adore Garden | 4BHK | 2275 | 3640 | 32554.9451 | 118500000
Magic Brick | Adore Garden | 4BHK | 2700 | 4320 | 32175.9259 | 139000000
99 Acres | Adore Garden | 3BHK | 1466 | 2345.6 | 32997.9536 | 77400000
99 Acres | Kings Krest - 350m | 4BHK | 1725 | 2760 | 31268.1159 | 86300000
Average |  |  |  |  | 23961.4976
Valuation Adopted |  |  |  |  | 32000