## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 15/07/2025
CPC Name: |  |  |  |  | Axis Goregoan
Date Of Property Visit |  |  |  |  | 2025-07-12
Name of the builder group |  |  |  |  | M/s.Ananta construction & Adore Realty LLP
Name of the builder company |  |  |  |  | M/s.Ananta construction & Adore Realty LLP
Name of the Project |  |  |  |  | Adore Garden
Name of the Project as per RERA |  |  |  |  | Adore - 4
Contect Details ( Name & Contect No.) |  |  |  |  | 2525697700/9326038235
Name / no of the Building |  |  |  |  | Building No.4 (Type D2)/1 Building
Docouments Provided |  |  |  |  | Approved Layout, NA Order cum CC
RERA No. |  |  |  |  | P99000016316
Project location details |  | Adore Garden, Building No.4 (Type D2 ), Gut.No.61, 61/1 & 62, Umroli, Palghar.
Gut. No. | 61, 61/1 & 62 |  |  | Plot No. |  | NA | Locality | Umroli west
Road | Palghar Bhoisar Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401404
Near by Landmark |  | Umroli Market |  |  | Distance from city centre: |  | About 0.35 Km from Umroli raiway station Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building no.5 |  | Bunglow |  | Open Plot |  | Vidhata Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.7534 |  | Longitude |  | 72.7582
Location Link |  | https://goo.gl/maps/Efi3F5NKZYxkebFv5?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 6175.34
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5557.806
Total number of Buildings |  |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | MHSL/KS.1/T.1/NP/SR-282/2017. |  |  |  | Dated | 31/12/2017.
Building plan approval No |  | MHSL/KS.1/T.1/NP/SR-282/2017. |  |  |  | Dated | 31/12/2017.
NA Order cum Commencement of Construction |  | MHSL/KS.1/T.1/NP/SR-282/2017. Vaid up to : Gr + 1st to 4th floor |  |  |  | Dated | 31/12/2017.
O. Certificate No.: NA |  | NA |  |  | Date of approval: | Dated | NA
Commencement date of construction |  |  | 31/12/2017. |  | Expected Completion |  | Completed |  | 2024-03-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5557.806 |  | Approved no of units |  | Flats = 25 Shops = 10
Approved no of Floors |  | Gr + 1st to 4th floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years
Material laying at Site: :Nothing
Construction details: |  | Building no.4 = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC(Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc. 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Builder Saleable area) | [5 empty] | 2950
Recommended rate of the Shop Per Sq. Ft. ( on Builder Saleable area) | [5 empty] | 5500
Society formation charges | [5 empty] | 75000/-
Recommended rate of Parking | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2360
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No. 4 ( Type D2 )
Ground floor is for shops & flat
1 |  | Shop | 142.0848 |  | 0 | 255 | N | Ground floor is for shops & flat |  | 13.2 | 10.764
2 |  | Shop | 121.8485 |  | 0 | 223 | N |  |  | 11.32 | 10.764
3 |  | Shop | 164.2586 |  | 0 | 296 | N |  |  | 15.26 | 10.764
4 |  | Shop | 158.3384 |  | 0 | 284 | N |  |  | 14.71 | 10.764
5 |  | Shop | 101.5045 |  | 0 | 182 | N |  |  | 9.43 | 10.764
6 |  | Shop | 139.7167 |  | 0 | 254 | N |  |  | 12.98 | 10.764
7 |  | Shop | 129.168 |  | 0 | 233 | N |  |  | 12 | 10.764
8 |  | Shop | 164.2586 |  | 0 | 296 | N |  |  | 15.26 | 10.764
9 |  | Shop | 121.8485 |  | 0 | 223 | N |  |  | 11.32 | 10.764
10 |  | Shop | 102.1504 |  | 0 | 182 | N |  |  | 9.49 | 10.764
1 |  | 1BHK | 340.573 |  | 0 | 580 | N |  | 11 | 31.64 | 10.764
1st to 4th floor
1 |  | 1BHK | 341.0035 |  | 0 | 580 | N | 1st to 4th floor |  | 31.68 | 10.764
2 |  | 1BHK | 340.573 |  | 0 | 579 | N |  |  | 31.64 | 10.764
3 |  | 1BHK | 340.573 |  | 0 | 579 | N |  |  | 31.64 | 10.764
4 |  | 1BHK | 351.014 |  | 0 | 597 | N |  |  | 32.61 | 10.764
5 |  | 2BHK | 438.5254 |  | 0 | 746 | N |  |  | 40.74 | 10.764
6 |  | 1BHK | 340.573 |  | 0 | 579 | N |  | 24 | 31.64 | 10.764
Remarks: 1. All work completed. Provide OC 2. We considered Saleable area as per Builder cost sheet. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 6. We have considered Other charges from cost sheet. 7. As per RERA, completion period of project Adore Garden 4 on 31/03/2024 but still project work is pending.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Adore Garden |  |  | Adore - 4
Google Map :

## Construction %
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 1.6667 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 16.6667 | Recommended |  |  | 30 | 30 | 15 | 1.6667 | 0 | 0 | 0
| 3 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0.5 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 3 | 0 |  | Plaster | 1.6667 | 1.6667
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 66.6667 | 76.6667

## Note
2020-10-16 | Pratiksha

## Valuation
2020-10-16 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing | Adore Garden | 1BHK | 307 | 445.15 | 2327.3054 | 1036000
| Housing | Adore Garden | 2BHK | 408 | 591.6 | 2327.5862 | 1377000
| Housing | Adore Garden | 3BHK | 769 | 1115.05 | 2327.2499 | 2595000
| PropTiger | Adore Garden | 1BHK | 396.5517 | 575 | 3043.4783 | 1750000
| PropTiger | Adore Garden | 2BHK | 513.7931 | 745 | 3161.0738 | 2355000
| Makaan | Adore Garden | 1BHK | 396.5517 | 575 | 3417.3913 | 1965000
| Average |  |  |  |  | 2767.3475
| Valuation Adopted |  |  |  |  | 2800

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.43 | 9.4325 | CB | 2.75 | 3.35 | 9.2125 | 2.75 | 3.35 | 9.2125
|  | 2.75 | 1.2 | 3.3 | FB | 2.05 | 1.8 | 3.69 | 1.2 | 2.75 | 3.3
|  |  |  | 0 |  | 3.05 | 2.8 | 8.54 | 2.05 | 1.8 | 3.69
| kitch |  |  | 0 | CB | 1.2 | 1.8 | 2.16 | 3.05 | 2.8 | 8.54
|  |  |  | 0 | FB | 1.2 | 1.8 | 2.16 | 1.2 | 1.8 | 2.16
|  |  |  | 0 |  | 1.05 | 2.75 | 2.8875 | 1.2 | 1.8 | 2.16
|  |  |  | 0 |  | 1.8 | 1.5 | 2.7 | 1.5 | 0.45 | 0.675
| Bed1 |  |  | 0 | CB | 2.4 | 1 | 2.4 | 2.4 | 1 | 2.4
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 137.0526 | 12.7325 |  |  | 363.285 | 33.75 |  | 345.928 | 32.1375

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0