## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/07/2025
CPC Name: |  |  |  |  | Axis Goregaon.
Date Of Property Visit |  |  |  |  | 2025-07-10
Name of the builder group |  |  |  |  | M/s.Supertech Housing Infra Builders & Developers
Name of the builder group |  |  |  |  | Mr. Sheru Shamsher Khan
Name of the Project |  |  |  |  | Flower Valley Complex
Contect Details ( Name & Contact No.) |  |  |  |  | 9167008394
Name / no of the Building |  |  |  |  | Building no.7 (G + 2nd Floors) - Type B Building no.13 (G + 2nd Floors) - Type E Building no.16 (G + 3rd Floors) - Type F (A Wing) Type G (B Wing) Type G (C Wing) Type G1 (D Wing)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, Costsheet
RERA no. |  |  |  |  | P99000017544
Project location details |  | Flower Valley, Gut no.102,103,104,105 , Village- Birwadi, Jammu Pada Road, Umroli west, Palghar 401404
Gut No |  | 102, 103, 104, 105 |  |  | Locality |  | Birwadi
Road |  | Jammu Pada Road |  |  | District |  | Palghar
City |  | Umroli |  |  | Pin Code |  | 401404
Near by Landmark |  | Near Raj mandir Garden |  |  | Distance from city centre: |  | 1.5 Km from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open |  | Open |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed structure
Latitude & Longitude |  | 19.7628106,72.7576129
Location |  | https://goo.gl/maps/tNvCM4xV5XbNBt42A
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 15180
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 11385
Total number of Buildings |  |  |  |  | 6 Wings
Approval Detail : Plan approval
Layout Approval No |  | P.NO.BS/BP/Birwadi/Palghar/ S.S.N.R./437 |  |  |  | Dated | 31/03/2017.
Building plan approval No |  | P.NO.BS/BP/Birwadi/Palghar/ S.S.N.R./437 |  |  |  | Dated | 31/03/2017.
NA Order cum Commencement Construction |  | MHSL/CLASS.1/T.1/NAP/SR-128/2016 |  |  |  | Dated | 23/05/2017.
O. Certificate No.: Under construction |  | NA |  |  | Date of approval: | Dated | NA | Expiry date: NA
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 11385
Approved no of units |  |  | Flats = 75, Shops = 11
Approved no of Floors |  |  | Building no.7 (G + 1st to 2nd Floor) - Type B Building no.13 (G + 1st to 2nd Floor) - Type E Building no.16 (G + 1st to 3rd Floor) - Type F, G, G & G1
Expected Completion |  |  | 2025-12-30
Quality of construction: |  |  | Good
Projected life of the structure: |  |  | 60 Years After Completion
Material laying at Site: : |  |  | Bricks, Cement & Steel etc.
Construction details: Building no.7 = G + 1st to 2nd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 2 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 2 | 100% |  | 23.33% |  | 55%
Plinth |  | 2 | 100%
RCC |  | 1 | 33.33% | [5 empty] | Excavation in process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process | 0.5
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed | 1
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process | 1.5
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 2
Possession |  | 0 | 0%
Construction details: Building no.13 = G + 1st to 2nd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 1.5 Floor completed, Painting upto 1.5 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 2 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 1.5 Floor completed, Painting upto 1.5 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 2 | 100% |  | 86.25% |  | 93.75%
Plinth |  | 2 | 100%
RCC |  | 3 | 100% | [5 empty] | Excavation in process | 1
Brickwork | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Excavation Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 2 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 100% | [5 empty] | Footing in Process | 0.5
Flooring & Fitting | Flooring & Fitting | 1.5 | 75% | [5 empty] | Footing Completed | 1
Painting & Wooden |  | 1.5 | 75% | [5 empty] | Plinth in process | 1.5
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 2
Possession |  | 0 | 0%
Construction details: Building no.16 (A, B, C Wing) = G + 1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed, Finishing upto 1.5 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed, Finishing upto 1.5 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 92.5% |  | 95%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process | 1.5
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Excavation Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 3 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Footing in Process | 0.75
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Footing Completed | 1.5
Painting & Wooden |  | 3 | 100% | [5 empty] | Plinth in process | 2.25
Building Common Amenities | Building Common Amenities | 1.5 | 50% | [5 empty] | Plinth completed | 3
Possession |  | 0 | 0%
Construction details: Building no.16 (D Wing) = G + 1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 2 Floor completed, Finishing upto 0.5 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 2 Floor completed, Finishing upto 0.5 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 89.17% |  | 95%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process | 1.5
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Excavation Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 3 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Footing in Process | 0.75
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Footing Completed | 1.5
Painting & Wooden |  | 2 | 66.67% | [5 empty] | Plinth in process | 2.25
Building Common Amenities | Building Common Amenities | 0.5 | 16.67% | [5 empty] | Plinth completed | 3
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6500
Society formation charges | [5 empty] | 75,000/-
Recommended rate of Parking | [5 empty] | 100000/-
Development charges Per | [5 empty] | 50,000/-
Distressed valuation of the Property | [5 empty] | 2800
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building no.7 - Type B
Ground Floor For Parking & Residential
1 |  | 1 BHK | 313.0171 |  | 0 | 453.8748 | N | Ground
2 |  | 1 BHK | 313.0171 |  | 0 | 453.8748 | N
3 |  | 1 RK | 283.4161 |  | 0 | 410.9534 | N
4 |  | 1 RK | 210.0056 |  | 0 | 304.5082 | N
1st & 2nd Floor
1 |  | 1 BHK | 316.2463 |  | 0 | 458.5572 | N | 1st & 2nd
2 |  | 1 BHK | 316.2463 |  | 0 | 458.5572 | N
3 |  | 1 RK | 285.0307 |  | 0 | 413.2945 | N |  |  | 32752968.3
4 |  | 1 RK | 213.9883 |  | 0 | 310.2831 | N
Building no.13 - Type E
Ground Floor For Parking & Residential
1 |  | Shop | 89.987 |  | 0 | 134.9806 | N | Ground |  | 1.5
2 |  | Shop | 94.7232 |  | 0 | 142.0848 | N
3 |  | Shop | 92.3551 |  | 0 | 138.5327 | N
4 |  | Shop | 89.987 |  | 0 | 134.9806 | N
5 |  | Shop | 94.7232 |  | 0 | 142.0848 | N
6 |  | Shop | 92.3551 |  | 0 | 138.5327 | N
7 |  | Shop | 79.0078 |  | 0 | 118.5116 | N
8 |  | Shop | 102.5809 |  | 0 | 153.8714 | N
9 |  | Shop | 102.5809 |  | 0 | 153.8714 | N
10 |  | Shop | 102.5809 |  | 0 | 153.8714 | N
11 |  | Shop | 75.0251 |  | 0 | 112.5376 | N
1 |  | 1 BHK | 322.4894 |  | 0 | 467.6097 | N
2 |  | 1 RK | 209.6827 |  | 0 | 304.0399 | N
3 |  | 1 RK | 209.6827 |  | 0 | 304.0399 | N
1st & 2nd Floor
1 |  | 1 BHK | 314.6317 |  | 0 | 456.216 | N | 1st & 2nd
2 |  | 1 BHK | 316.2463 |  | 0 | 458.5572 | N
3 |  | 1 BHK | 286.753 |  | 0 | 415.7918 | N
4 |  | 1 RK | 202.5785 |  | 0 | 293.7388 | N
5 |  | 1 RK | 202.5785 |  | 0 | 293.7388 | N
6 |  | 1 RK | 211.8355 |  | 0 | 307.1615 | N
Building no.16
Type F (A Wing)
Ground Floor For Parking & Residential
1 |  | 2 BHK | 389.4415 |  | 0 | 564.6902 | N | Ground
2 |  | 1 BHK | 286.9682 |  | 0 | 416.1039 | N
1st & 2nd Floor
1 |  | 1 BHK | 350.9064 |  | 0 | 508.8143 | N | 1st & 2nd
2 |  | 1 BHK | 375.7712 |  | 0 | 544.8683 | N
3 |  | 1 RK | 451.7651 |  | 0 | 655.0594 | N
4 |  | 1 RK | 350.9064 |  | 0 | 508.8143 | N
3rd Floor
1 |  | 1 BHK | 350.9064 |  | 0 | 508.8143 | N | 3rd
2 |  | 1 BHK | 375.7712 |  | 0 | 544.8683 | N |  | 2569.4283
3 |  | Terrace
4 |  | Terrace
Type G (B Wing)
Ground Floor For Parking & Residential
1 |  | 1 BHK | 286.3224 |  | 0 | 415.1675 | N | Ground
2 |  | 1 BHK | 286.3224 |  | 0 | 415.1675 | N
1st & 2nd Floor
1 |  | 1 BHK | 348.646 |  | 0 | 505.5366 | N | 1st & 2nd
2 |  | 1 BHK | 350.2606 |  | 0 | 507.8778 | N
3 |  | 1 BHK | 342.5105 |  | 0 | 496.6402 | N
4 |  | 1 BHK | 340.8959 |  | 0 | 494.299 | N
3rd Floor
1 |  | 1 BHK | 348.646 |  | 0 | 505.5366 | N | 3rd
2 |  | 1 BHK | 350.2606 |  | 0 | 507.8778 | N
3 |  | Terrace
4 |  | Terrace
Type G (C Wing)
Ground Floor For Parking & Residential
1 |  | 1 BHK | 286.3224 |  | 0 | 415.1675 | N | Ground
2 |  | 1 BHK | 286.3224 |  | 0 | 415.1675 | N
1st & 2nd Floor
1 |  | 1 BHK | 348.646 |  | 0 | 505.5366 | N | 1st & 2nd
2 |  | 1 BHK | 350.2606 |  | 0 | 507.8778 | N
3 |  | 1 BHK | 342.5105 |  | 0 | 496.6402 | N
4 |  | 1 BHK | 340.8959 |  | 0 | 494.299 | N
3rd Floor
1 |  | 1 BHK | 348.646 |  | 0 | 505.5366 | N | 3rd
2 |  | 1 BHK | 350.2606 |  | 0 | 507.8778 | N
3 |  | Terrace
4 |  | Terrace
Type G-1 (D Wing)
Ground Floor For Parking & Residential
1 |  | 1 BHK | 286.3224 |  | 0 | 415.1675 | N | Ground
2 |  | 1 BHK | 286.3224 |  | 0 | 415.1675 | N
1st & 2nd Floor
1 |  | 1 BHK | 340.8959 |  | 0 | 494.299 | N | 1st & 2nd
2 |  | 1 BHK | 342.5105 |  | 0 | 496.6402 | N
3 |  | 1 BHK | 350.2606 |  | 0 | 507.8778 | N
4 |  | 1 BHK | 348.646 |  | 0 | 505.5366 | N
3rd Floor
1 |  | 1 BHK | 340.8959 |  | 0 | 494.299 | N | 3rd
2 |  | 1 BHK | 342.5105 |  | 0 | 496.6402 | N
3 |  | Terrace
4 |  | Terrace
Remarks: 1. We considered carpet area as per Approved plan. 2. Building No.7- Construction work is same as last visit. (dtd.16/01/2025) Building No.13 - Work is same as last visit.(dtd.12/10/2023). Building No. 16 - Construction work is the same as last visit (dtd.07/10/2024). 3. Saleable area as per our calculation. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. We can't identify the building name as per broucher. 7. Car parking is subjected to authentic documentation. 8. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 9. The project has received first CC on 23/05/2017, But construction work is not yet Completed. 10. On site we met Mr. Arun : 9272571432. 11. As checked on RERA portal on date 18/07/2025, we have observed that the project name is changed from "Flower Valley" to "Flower Valley Complex". 9. As per RERA, Completion period of project Flower Valley is expired on Date. 30/12/2022 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Flower Valley Complex
Google Map :
Bldg No. 16

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Construction % of 7
Particulars | totaL floor | 2
| total | completed
plinth | 10 | 5 | 50
slab | total slab | completed slab | 0 |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 3 | 0 | 0 | Progress | 5 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended | 25 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 2 | 0 | 0
Flooring | Total Floor | completed Floor
| 2 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 5 | 25
| 2 | 0 |  |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 2 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 5 | 25

## Construction % of 13
Particulars | totaL floor | 2
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 33.3333 |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 3 | 1 |  | 0 | Progress | 10 | 13.3333 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 0 | Recommended | 30 | 10 | 0 | 0 | 0 | 0 | 0
| 2 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 2 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 2 | 0 |  |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  |  | Plinth | 10 | 30
| 2 | 0 |  |  |  | RCC | 13.3333 | 10
Finishing | Total Floor | completed Floor |  |  |  | Bricks | 0 | 0
| 2 | 0 |  |  |  | Plaster | 0 | 0
[6 empty] | Flooring | 0 | 0
[6 empty] | Wood & painting | 0 | 0
[6 empty] | Finishing | 0 | 0
[6 empty] | total | 23.3333 | 40
Excavation in process |  | 1% | 2%
Excavation Completed |  | 2% | 4%
Footing in Process |  | 4% | 8%
Footing Completed |  | 5% | 15%
Plinth in process |  | 7% | 20%
Plinth completed |  | 10% | 30%

## Construction % of 16
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 100 | Progress | 10 | 40 | 15 | 3.3333 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 33.3333 | Recommended | 30 | 30 | 15 | 3.3333 | 0 | 0 | 0
| 3 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 1 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 3 | 0 |  |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  |  | Bricks | 15 | 15
| 3 | 0 |  |  | Plaster | 3.3333 | 3.3333
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 68.3333 | 78.3333

## VALUATIOn
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
magicabode | Flower Valley | 1BHK | 348 | 504.6 | 2774.4748 | 1400000
magicabode | Flower Valley | 1RK | 210 | 304.5 | 2663.3826 | 811000
Average |  |  |  |  | 2718.9287
Valuation Adopted |  |  |  |  | 2700