## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-11
Name of the builder group |  |  |  | Trident Ozone LLP
Name of the builder company |  |  |  | Trident Ozone LLP
Name of the Project |  |  |  | Fairmont
Contact Details ( Name & Contact No.) |  |  |  | 955421000/02225942037
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Akshay Utekar 8286335695
Name / No of the Building |  |  |  | A Wing (Rehab) B Wing (Sale)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800024818
Project location details |  | Fairmont, CTS No.110, 111 & 112, near JBD Cooperative Housing Society, Jungal Mangal Road, Kanjur, Bhandup West, Kurla, Mumbai - 400078.
CTS No |  | 110, 111 & 112
Road |  | Jungal Mangal Road |  | Village |  | Kanjur
City |  | Bhandup West |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400078
Nearby Landmark |  | JBD Cooperative Housing Society |  | Distance from city centre: |  | 2KM from Bhandup Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Slum
South | NA | NA |  |  | Jungal Mangal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.149697,72.932159
Location Link |  | https://goo.gl/maps/3LTqrmm4bw393Br48
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1196.28
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 0.94654
Total FSI availaible for the project |  |  |  | 4.9465
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5917.45
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | S/PVT/130/20160808/AP |  |  | Dated | 2021-08-26
Approved Floor plan No. |  | S/PVT/130/20160808/AP |  |  | Dated | 2021-08-26
Commencement-CC No Valid Up to: |  | S/PVT/130/20160808/AP |  |  | Dated | 2022-02-11
This C.C is further extended for RCC Framework only for 20th to 22nd upper floors including LMR & OHWT of sale wing B of composite building a per approved amended plans dated 26/08/2021.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5917.45
Approved no of units |  |  | Sale Flats - 121, Rehab Flats - 74, Rehab Shops - 15
Approved no of Floors |  |  | A & B Wing = G + 1st to 22nd Floor B Wing = G + 1st to 22nd Floor
Proposed no of Floors |  |  | A & B Wing = G + 1st to 22nd Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative Entrance etc
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = G + 1st to 22nd Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 92.05% |  | 94.77% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 21 | 95.45% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 21 | 95.45% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 54.55% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | B Wing = G + 1st to 22nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 19 Floor Completed, Painting upto 14 Floor Completed, Finishing upto 5 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 19 Floor Completed, Painting upto 14 Floor Completed, Finishing upto 5 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 87.95% |  | 94.32% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 19 | 86.36% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 14 | 63.64% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 22.73% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 12300
Recommended rate of the Shop(Ground Floor) Per Sq. Ft. |  |  |  |  | 22000
Recommended rate of the Shop(1st Floor) Per Sq. Ft. |  |  |  |  | 20000
Recommended rate of Parking |  |  |  |  | 600000 |  |  | Shop rate is not given as al shops are rehab
Distressed valuation of the Property |  |  |  |  | 9840
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing - Rehab Shops |  | 7 |  | 1611.0479 |  | 2577.6766
B Wing - Rehab Shops |  | 8 |  | 1808.9978 |  | 2894.3965
Total |  | 15 |  | 3420.0457 |  | 5472.0732
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing - Rehab Flat |  | 73 |  | 27855.6174 |  | 43176.207
A Wing - Sale Flat |  | 4 |  | 1575.8496 |  | 2442.5669
B Wing - Rehab Flat |  | 1 |  | 300.1003 |  | 465.1555
B Wing - Sale Flat |  | 117 |  | 37460.8728 |  | 58064.3528
Total |  | 195 |  | 67192.4401 |  | 104148.2822
Grand Total |  | 210 |  | 70612.4858 |  | 109620.3553
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Rehab & Sale) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
A Wing - Rehab Wing
Ground Floor For Parking & Commercial
1 | Rehab | Shop | 210.1133 | 0 | 336.1812 | Ground Floor For Parking & Commercial
2 | Rehab | Shop | 220.0162 | 0 | 352.0259 | Ground Floor For Parking & Commercial
3 | Rehab | Shop | 240.3601 | 0 | 384.5762 | Ground Floor For Parking & Commercial
4 | Rehab | Shop | 226.6898 | 0 | 362.7037 | Ground Floor For Parking & Commercial
5 | Rehab | Shop | 286.6453 | 0 | 458.6325 | Ground Floor For Parking & Commercial
6 | Rehab | Shop | 199.9951 | 0 | 319.9922 | Ground Floor For Parking & Commercial
1st Floor For Parking, Amenities & Commercial
2 | Rehab | Shop | 227.228 | 0 | 363.5649 | 1st Floor For Parking, Amenities & Commercial
B Wing - Sale Wing
Ground Floor For Parking & Commercial
7 | Rehab | Shop | 202.0403 | 0 | 323.2644 | Ground Floor For Parking & Commercial
8 | Rehab | Shop | 137.241 | 0 | 219.5856 | Ground Floor For Parking & Commercial
9 | Rehab | Shop | 287.8294 | 0 | 460.527 | Ground Floor For Parking & Commercial
10 | Rehab | Shop | 214.6342 | 0 | 343.4147 | Ground Floor For Parking & Commercial
11 | Rehab | Shop | 226.7975 | 0 | 362.876 | Ground Floor For Parking & Commercial
12 | Rehab | Shop | 258.5513 | 0 | 413.682 | Ground Floor For Parking & Commercial
13 | Rehab | Shop | 223.353 | 0 | 357.3648 | Ground Floor For Parking & Commercial
1st Floor For Parking, Amenities & Commercial
4 | Rehab | Shop | 258.5513 | 0 | 413.682 | 1st Floor For Parking, Amenities & Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
A Wing - Rehab Wing
1st Floor For Parking, Amenities & Commercial
2nd Floor For Parking & Amenities (Society Office, Library & Skill Development Center)
3rd Floor (Part Parking Area)
1 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 3rd Floor (Part Parking Area) |  | 27.3225
2 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 3rd Floor (Part Parking Area)
3 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 3rd Floor (Part Parking Area)
4th to 7th, 9th to 14th & 16th to 21st Floor
1 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 4th to 7th, 9th to 14th & 16th to 21st Floor
2 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 4th to 7th, 9th to 14th & 16th to 21st Floor
3 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 4th to 7th, 9th to 14th & 16th to 21st Floor
4 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 4th to 7th, 9th to 14th & 16th to 21st Floor
8th Floor (Part Refuge Area)
1 | - | Refuge Area | 381.5838 | 0 | 591.4549 | 8th Floor (Part Refuge Area)
2 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 8th Floor (Part Refuge Area)
3 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 8th Floor (Part Refuge Area)
4 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 8th Floor (Part Refuge Area)
15th Floor (Part Refuge Area)
1 | - | Refuge Area | 381.5838 | 0 | 591.4549 | 15th Floor (Part Refuge Area)
2 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 15th Floor (Part Refuge Area)
3 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 15th Floor (Part Refuge Area)
4 | Rehab | 1BHK | 381.5838 | 0 | 591.4549 | 15th Floor (Part Refuge Area)
22nd Floor
1 | Sale | 1BHK | 393.9624 | 0 | 610.6417 | 22nd Floor
2 | Sale | 1BHK | 393.9624 | 0 | 610.6417 | 22nd Floor
3 | Sale | 1BHK | 393.9624 | 0 | 610.6417 | 22nd Floor
4 | Sale | 1BHK | 393.9624 | 0 | 610.6417 | 22nd Floor
B Wing - Sale Wing
1st Floor For Parking, Amenities & Commercial
1 | - | Parking Area |  |  |  | 1st Floor For Parking, Amenities & Commercial
2 | - |  |  |  |  | 1st Floor For Parking, Amenities & Commercial
3 | Rehab | 1BHK | 300.1003 | 0 | 465.1555 | 1st Floor For Parking, Amenities & Commercial |  | 27.305
4 | - | Rehab Shop |  | 0 | 0 | 1st Floor For Parking, Amenities & Commercial
5 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 1st Floor For Parking, Amenities & Commercial
6 | Sale | 1BHK | 322.1665 | 0 | 499.3581 | 1st Floor For Parking, Amenities & Commercial
2nd Floor For Parking & Amenities
1 | - | Parking Area |  |  |  | 2nd Floor For Parking & Amenities
2 | - |  |  |  |  | 2nd Floor For Parking & Amenities
3 | - | Society Office |  |  |  | 2nd Floor For Parking & Amenities
4 | - | Fitness Center |  |  |  | 2nd Floor For Parking & Amenities
5 | - |  |  |  |  | 2nd Floor For Parking & Amenities
6 | Sale | 1BHK | 322.1665 | 0 | 499.3581 | 2nd Floor For Parking & Amenities
3rd Floor (Part Parking Area)
1 | - | Parking Area |  |  |  | 3rd Floor (Part Parking Area)
2 | - |  |  |  |  | 3rd Floor (Part Parking Area)
3 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 3rd Floor (Part Parking Area)
4 | Sale | 1BHK | 321.0901 | 0 | 497.6897 | 3rd Floor (Part Parking Area)
5 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 3rd Floor (Part Parking Area)
6 | Sale | 1BHK | 322.1665 | 0 | 499.3581 | 3rd Floor (Part Parking Area)
4th to 7th, 9th to 14th & 16th to 21st Floor
1 | Sale | 1BHK | 318.6144 | 0 | 493.8523 | 4th to 7th, 9th to 14th & 16th to 21st Floor
2 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 4th to 7th, 9th to 14th & 16th to 21st Floor
3 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 4th to 7th, 9th to 14th & 16th to 21st Floor
4 | Sale | 1BHK | 321.0901 | 0 | 497.6897 | 4th to 7th, 9th to 14th & 16th to 21st Floor
5 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 4th to 7th, 9th to 14th & 16th to 21st Floor
6 | Sale | 1BHK | 322.1665 | 0 | 499.3581 | 4th to 7th, 9th to 14th & 16th to 21st Floor
8th Floor (Part Refuge Area)
1 | Sale | 1BHK | 318.6144 | 0 | 493.8523 | 8th Floor (Part Refuge Area)
2 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 8th Floor (Part Refuge Area)
3 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 8th Floor (Part Refuge Area)
4 | Sale | 1BHK | 321.0901 | 0 | 497.6897 | 8th Floor (Part Refuge Area)
5 | - | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
6 | - |  |  |  |  | 8th Floor (Part Refuge Area)
15th Floor (Part Refuge Area)
1 | Sale | 1BHK | 318.6144 | 0 | 493.8523 | 15th Floor (Part Refuge Area)
2 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 15th Floor (Part Refuge Area)
3 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 15th Floor (Part Refuge Area)
4 | Sale | 1BHK | 321.0901 | 0 | 497.6897 | 15th Floor (Part Refuge Area)
5 | - | Refuge Area |  |  |  | 15th Floor (Part Refuge Area)
6 | - |  |  |  |  | 15th Floor (Part Refuge Area)
22nd Floor
1 | Sale | 1BHK | 318.6144 | 0 | 493.8523 | 22nd Floor
2 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 22nd Floor
3 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 22nd Floor
4 | Sale | 1BHK | 321.0901 | 0 | 497.6897 | 22nd Floor
5 | Sale | 1BHK | 319.6908 | 0 | 495.5207 | 22nd Floor
6 | Sale | 1BHK | 322.1665 | 0 | 499.3581 | 22nd Floor
Remarks:
* | Construction work is in process at the time of Visit. (Internal Photo was not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved CC (on 07/10/2022).
* | As checked on RERA portal on date 14/07/2025, we have observed that above project "Fairmount" is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nainesh Tambe |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Fairmont
Google Map :
Wing A
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 1bhk | 382 | 611.2 | 0
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted