## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder |  |  |  | Mr. Sunil Manoharlal Puri
Name of the builder company |  |  |  | My Home Foundation Group
Name of the Project |  |  |  | Puri SeleQt
Provided Contact Details (Name & Contact No.) |  |  |  | 022 49634477/022 4002 2116
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rohan 9112696111
Name / No of the Building |  |  |  | Wing A, B, C & D
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51800049868
Project location details |  | Puri SeleQt, CTS No.116 (PT), 116/1 to 3, 116/5 to 17, near Raaj Chamber, RK Paramhans Road, Natwar Nagar, Mogra, Andheri (East), Andheri, Mumbai - 400069.
CTS No |  | 116 (PT), 116/1 to 3, 116/5 to 17
Locality |  | Natwar Nagar
Road |  | RK Paramhans Road |  | Locality/Village |  | Mogra
City |  | Andheri (East) |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400069
Nearby Landmark |  | Raaj Chamber |  | Distance from city centre: |  | 1.8 KM from Andheri Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Raaj Chamber
North | NA | NA |  |  | Neechem Industries
South | NA | NA |  |  | RK Paramhans Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.124056,72.850333
Location Link |  | https://goo.gl/maps/ZegXGSReowTJvEeB6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2956.2
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 0.35847
Total FSI availaible for the project |  |  |  | 4.3585
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12884.52
Total number of Buildings |  |  |  | 04 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | SRA/ENG/K-E/PVT/0257/20211118/ AP/C |  |  | Dated | 2023-11-08
Approved Floor plan No. |  | SRA/ENG/K-E/PVT/0257/20211118/ AP/C |  |  | Dated | 2023-11-08
Commencement-CC No Valid Up to: |  | SRA/ENG/K-E/PVT/0257/20211118/ AP/C |  |  | Dated | 2022-09-07
This CC is granted for work up to Plinth Level.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 12884.52
Approved no of units |  |  | Sale Flats - 73, Shops - 30, Offices - 21, PTC Flats - 112
Approved no of Floors |  |  | A & B Wing = 1B + G + 1st to 2nd floor + 3rd to 4th (Podium) + 5th (E-Deck) + 6th to 16th Floor C Wing = 1B + G + 1st to 2nd floor + 3rd to 4th (Podium) + 5th (E-Deck) + 6th to 14th Floor D Wing = 1B + G + 1st to 2nd floor + 3rd to 4th (Podium) + 5th (E-Deck) + 6th to 13th Floor
Proposed no of Floors |  |  | A Wing = 1B + G + 1st to 2nd floor + 4P + 5th (E-Deck) + 6th to 16th Floor
B & C Wing = 1B + G + 1st to 2nd floor + 4P + 5th (E-Deck) + 6th to 16th Floor
D Wing = 1B + G + 1st to 2nd floor + 4P + 5th (E-Deck) + 6th to 16th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Multipurpose play court, Banquet hall, Mini theater, Fitness Center
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = 1B + G + 1st to 2nd floor + 4P + 5th (E-Deck) + 6th to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor Completed | , RCC upto 14 Slab, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 46.69% |  | 72.21% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 14 | 82.35% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 6 | 37.5% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 2 | 12.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Construction details: |  | B & C Wing = 1B + G + 1st to 2nd floor + 4P + 5th (E-Deck) + 6th to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 6 Floor, Internal Plaster upto 3 Floor Completed | , RCC upto 14 Slab, Brickwork upto 6 Floor, Internal Plaster upto 3 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 6 Floor, Internal Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 47.16% |  | 72.52% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 14 | 82.35% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 6 | 37.5% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 3 | 18.75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Construction details: |  | D Wing = 1B + G + 1st to 2nd floor + 4P + 5th (E-Deck) + 6th to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 10 Slab, Brickwork upto 2 Floor Completed | , RCC upto 10 Slab, Brickwork upto 2 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 10 Slab, Brickwork upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4 | 2024-08-01 | D- wing Excavation 50% done Site person extra work given
Excavation |  | 16 | 100% | 34.47% |  | 63.27% |  | Excavation in process | 8 | 2024-10-10 | D- wing Footing in process done Site person extra work given
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 10 | 58.82% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 2 | 12.5% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 18000
Recommended rate of the Shop Per Sq. Ft. (Ground Floor) |  |  |  |  | 35000
Recommended rate of the Shop Per Sq. Ft. (Gr + 1st Floor) |  |  |  |  | 30000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 25000
Floor Rise Rate
Development Charges |  |  |  |  | 500000
Club Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 65000
Society Formation Charges |  |  |  |  | 30000
Advance Maintenance Charges |  |  |  |  | 150000
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 14400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | Cost Sheet | 99 Acres
Wing A to D | Shop | 30 |  | 23379.1378 |  | 37406.6205 |  | 28000 to 30000
| Office | 21 |  | 11378.1938 |  | 18205.1101 |  | 19354.8387 | #REF!
Total |  | 51 |  | 34757.3317 |  | 55611.7307
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A Sale |  | 42 |  | 41297.8082 |  | 64011.6028 |  |  | 72
Wing B Sale |  | 31 |  | 25606.1567 |  | 39689.5429
Wing C + D PTC Flats |  | 112 |  | 34066.6607 |  | 52803.3241
Total |  | 185 |  | 100970.6256 |  | 156504.4697
Grand Total |  | 236 |  | 135727.9573 |  | 212116.2003 |  | https://www.99acres.com/puri-seleqt-andheri-east-mumbai-andheri-dahisar-npxid-r407476
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing A to D
Basement Floor For Meter Room & Parking
Ground Floor For Entrance Lobby, Commercial & Parking
1 |  | Shop | 1514.6024 | 0 | 2423.3639 | Ground Floor For Entrance Lobby, Commercial & Parking |  | 34.3885
2 |  | Shop | 301.9302 | 0 | 483.0883 |  |  |  | 10.764
3 |  | Shop | 2059.6914 | 0 | 3295.5062
4 |  | Shop | 534.4326 | 0 | 855.0922
5 |  | Shop | 392.886 | 0 | 628.6176 |  |  |  | 42594.4038
6 |  | Shop | 322.8124 | 0 | 516.4998 |  |  | 67.5415 | 62100.4457
7 |  | Shop | 1192.5436 | 0 | 1908.0697
8 |  | Shop | 1178.5504 | 0 | 1885.6806
9 |  | Shop | 387.0734 | 0 | 619.3175
10 |  | Shop | 300.5309 | 0 | 480.8494
11 |  | Shop | 447.9977 | 0 | 716.7963 |  |  |  | 9871.7633
12 |  | Shop | 1392.8616 | 0 | 2228.5786 |  |  | 67.5415 | 15909.3753
13 |  | Shop | 360.4864 | 0 | 576.7782
14 |  | Shop | 200.4257 | 0 | 320.6811
15 |  | Shop | 424.8551 | 0 | 679.7681
16 |  | Shop Duplex with 1st Floor | 1079.0361 | 0 | 1726.4578
1st Floor For Entrance Lobby, Commercial & Parking
1 |  | Shop | 1236.1378 | 0 | 1977.8204 | 1st Floor For Entrance Lobby, Commercial & Parking |  | 34.3885
2 |  | Shop | 544.8737 | 0 | 871.7979 |  |  |  | 10.764
3 |  | Shop | 206.6688 | 0 | 330.6701
4 |  | Shop | 420.7648 | 0 | 673.2236
5 |  | Shop | 1396.629 | 0 | 2234.6064 |  |  |  | 24679.4082
6 |  | Shop | 557.1446 | 0 | 891.4314 |  |  | 67.5415 | 34411.6456
7 |  | Shop | 940.7736 | 0 | 1505.2378
8 |  | Shop | 1030.2224 | 0 | 1648.3559
9 |  | Shop | 1621.5966 | 0 | 2594.5546
10 |  | Shop | 878.6653 | 0 | 1405.8645
11 |  | Shop | 880.7105 | 0 | 1409.1368 |  |  |  | 22909.0059
12 |  | Shop | 600.2006 | 0 | 960.321 |  |  | 67.5415 | 18199.953
13 |  | Shop | 199.7798 | 0 | 319.6477
14 |  | Shop | 774.2545 | 0 | 1238.8072
2nd Floor Commercial & Parking
1 |  | Office | 718.3894 | 0 | 1149.423 | 2nd Floor Commercial & Parking
2 |  | Office | 517.2102 | 0 | 827.5363
3 |  | Office | 518.5019 | 0 | 829.603
4 |  | Office | 260.0582 | 0 | 416.0932
5 |  | Office | 321.8436 | 0 | 514.9498
6 |  | Office | 1297.3849 | 0 | 2075.8159
7 |  | Office | 663.8159 | 0 | 1062.1054
8 |  | Office | 882.0022 | 0 | 1411.2035
9 |  | Office | 932.3777 | 0 | 1491.8043
9A |  | Office | 2639.9786 | 0 | 4223.9658
10 |  | Office | 331.8541 | 0 | 530.9666
10A |  | Office | 299.9927 | 0 | 479.9883
11 |  | Office | 201.9326 | 0 | 323.0922
12 |  | Office | 192.1374 | 0 | 307.4198
13 |  | Office | 200.1028 | 0 | 320.1644
14 |  | Office | 404.7264 | 0 | 647.5622
15 |  | Office | 200.1028 | 0 | 320.1644
16 |  | Office | 198.8111 | 0 | 318.0977
17 |  | Office | 199.7798 | 0 | 319.6477
18 |  | Office | 199.7798 | 0 | 319.6477
19 |  | Office | 197.4118 | 0 | 315.8588
3rd & 4th Podium Floor For Parking
5th E-Deck Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing A
6th Floor For Refuge Area & Residential
1 |  | 2BHK | 792.7686 | 0 | 1228.7913 | 6th Floor For Refuge Area & Residential |  | 63.796
2 |  | 2BHK | 792.7686 | 0 | 1228.7913
3 |  | Refuge Area
4 |  | 3BHK | 1188.5609 | 0 | 1842.2694
7th to 12th Floor
1 |  | 2BHK | 792.7686 | 0 | 1228.7913 | 7th to 12th Floor
2 |  | 2BHK | 792.7686 | 0 | 1228.7913
3 |  | 3BHK | 1164.7724 | 0 | 1805.3973
4 |  | 3BHK | 1188.5609 | 0 | 1842.2694
13th Floor (Part Refuge Area)
1 |  | 2BHK | 792.7686 | 0 | 1228.7913 | 13th Floor (Part Refuge Area)
2 |  | 2BHK | 792.7686 | 0 | 1228.7913
3 |  | Refuge Area
4 |  | 4BHK | 1488.3383 | 0 | 2306.9243
14th Floor
1 |  | 2BHK | 792.7686 | 0 | 1228.7913 | 14th Floor
2 |  | 2BHK | 792.7686 | 0 | 1228.7913
3 |  | 3BHK | 1164.7724 | 0 | 1805.3973
4 |  | 3BHK | 1188.5609 | 0 | 1842.2694
15th & 16th Floor
1 |  | 2BHK | 792.7686 | 0 | 1228.7913 | 15th & 16th Floor
2 |  | 2BHK | 792.7686 | 0 | 1228.7913
3 |  | 3BHK | 1164.7724 | 0 | 1805.3973
4 |  | 3BHK | 1188.5609 | 0 | 1842.2694
Wing B
6th Floor For Refuge Area & Residential
1 |  | 2BHK | 708.5941 | 0 | 1098.3209 | 6th Floor For Refuge Area & Residential |  | 63.796
2 |  | 3BHK | 980.708 | 0 | 1520.0975
7th to 12th Floor
1 |  | 2BHK | 708.5941 | 0 | 1098.3209 | 7th to 12th Floor
2 |  | 2BHK | 851.0018 | 0 | 1319.0529
3 |  | 2BHK | 859.7207 | 0 | 1332.5671
13th Floor (Part Refuge Area)
1 |  | 2BHK | 708.5941 | 0 | 1098.3209 | 13th Floor (Part Refuge Area)
2 |  | 3BHK | 1434.4106 | 0 | 2223.3365
14th Floor
1 |  | 2BHK | 708.5941 | 0 | 1098.3209 | 14th Floor
2 |  | 2BHK | 851.0018 | 0 | 1319.0529
3 |  | 2BHK | 859.7207 | 0 | 1332.5671
15th & 16th Floor
1 |  | 2BHK | 708.5941 | 0 | 1098.3209 | 15th & 16th Floor
2 |  | 2BHK | 851.0018 | 0 | 1319.0529
3 |  | 2BHK | 859.7207 | 0 | 1332.5671
Wing C + D
6th Floor For Refuge Area & Residential
1 |  | Library | 792.7686 | 0 | 1228.7913 | 6th Floor For Refuge Area & Residential |  | 63.796
2 |  | Balwadi | 792.7686 | 0 | 1228.7913
3 |  | Health Care Center
4 |  | Wel Fare Center | 1188.5609 | 0 | 1842.2694
5 | PTC | 1BHK | 302.576 | 0 | 468.9929 |  |  | 63.796
6 | PTC | 1BHK | 302.4684 | 0 | 468.826
7 |  | Society Office
8 |  | Refuge Area
9 | [7 empty] | 63.796
10
11
12 | PTC | 1BHK | 303.5448 | 0 | 470.4944
13 | PTC | 1BHK | 303.5448 | 0 | 470.4944
14 | PTC | 1BHK | 303.5448 | 0 | 470.4944
15 | PTC | 1BHK | 300.7462 | 0 | 466.1565
7th to 12th Floor
1 | PTC | 1BHK | 306.3434 | 0 | 474.8323 | 7th to 12th Floor
2 | PTC | 1BHK | 305.4823 | 0 | 473.4976
3 | PTC | 1BHK | 310.5414 | 0 | 481.3392
4 | PTC | 1BHK | 309.0344 | 0 | 479.0034
5 | PTC | 1BHK | 302.576 | 0 | 468.9929
6 | PTC | 1BHK | 302.4684 | 0 | 468.826
7 | PTC | 1BHK | 300.5309 | 0 | 465.8229
8 | PTC | 1BHK | 300.6385 | 0 | 465.9897
9 | PTC | 1BHK | 300.5309 | 0 | 465.8229
10 | PTC | 1BHK | 311.9407 | 0 | 483.5081
11 | PTC | 1BHK | 303.5448 | 0 | 470.4944
12 | PTC | 1BHK | 303.5448 | 0 | 470.4944
13 | PTC | 1BHK | 303.5448 | 0 | 470.4944
14 | PTC | 1BHK | 303.5448 | 0 | 470.4944
15 | PTC | 1BHK | 300.7462 | 0 | 466.1565
13th Floor (Part Refuge Area)
1 | PTC | 1BHK | 306.3434 | 0 | 474.8323 | 13th Floor (Part Refuge Area)
2 | PTC | 1BHK | 305.4823 | 0 | 473.4976
3 | PTC | 1BHK | 310.5414 | 0 | 481.3392
4 | PTC | 1BHK | 309.0344 | 0 | 479.0034
5 | PTC | 1BHK | 302.576 | 0 | 468.9929
6 | PTC | 1BHK | 302.4684 | 0 | 468.826
7 | PTC | 1BHK | 300.5309 | 0 | 465.8229
8 | PTC | 1BHK | 300.6385 | 0 | 465.9897
9 | PTC | 1BHK | 300.5309 | 0 | 465.8229
10 | Refuge Area
11
12 | PTC | 1BHK | 303.5448 | 0 | 470.4944
13 | PTC | 1BHK | 303.5448 | 0 | 470.4944
14 | PTC | 1BHK | 303.5448 | 0 | 470.4944
15 | PTC | 1BHK | 300.7462 | 0 | 466.1565
14th Floor (Part Terrace Area)
1 | Terrace Area |  |  |  |  | 14th Floor (Part Terrace Area)
2
3
4
5
6
7
8
9
10
11
12 | PTC | 1BHK | 303.5448 | 0 | 470.4944
13 | PTC | 1BHK | 303.5448 | 0 | 470.4944
14 | PTC | 1BHK | 303.5448 | 0 | 470.4944
Remarks:
* | Construction work is in process at the time of Visit. Internal visit was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved plan (on.03/02/2024).
* | Please provide revised approved CC, As the construction work goes beyond the CC permission.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Pratik Niwate |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Puri SeleQt
Layout :
Google Map :
Formulas:
Mogra = [Mogra, row above]
Wing B
Wing A
Wing B & C
Wing D
Wing A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted