## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-10
Name of the builder group |  |  |  |  | M/s. Mangalnath Developers
Name of the builder company |  |  |  |  | M/s. Mangalnath Developers
Name of the Project |  |  |  |  | Safal Sai
Name & No of Buildings |  |  |  |  | A, B & C wings
Docouments Provided |  |  |  |  | Refer Data
RERA No. |  |  |  |  | P51800009799
Project location details |  | Safal Sai, CTS no. 453 & 453 (1 to 74) of village Borla, Kelkar wadi raod, Near Ghatla Municipal Marathi School, Chembur, Mumbai 400 071
CTS No | 453 & 453 (1 to 74) |  |  |  |  | Locality | Borla
Road | Kelkar Wadi road |  |  |  | District | Mumbai
City | Chembur |  |  |  | Pin Code | 400 071
Near by Landmark |  | Near Ghatla Municipal Marathi School |  |  | Distance from city centre: |  | About 1.2 Km from Govandi Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Ghatla Municipal Marathi School |  | Ashirwad Hospital |  | Open plot |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.052181,72.907929
Location Link |  | https://goo.gl/maps/TXAFofFyrerDXC3B7
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
[5 empty] | Slum |  | Non slum | Total
Total land area of the project in Sq. Mt. |  |  |  |  | 2440.4 |  | 712.6 | 3153
Permissible FSI |  |  |  |  | 3 |  | 1 | 4
Permissible TDR/Paid FSI |  |  |  |  | NA |  | NA | NA
Total fungible area to project |  |  |  |  | Rehab - 637.27 |  |  | Sale - 1899.76
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 7296.3 |  | 304.9 | 7601.2
Total number of Buildings |  |  |  |  | 3 Wings
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/3851/MW/PL/AP |  |  |  | Dated | 12/09/2018.
Building plan approval No |  | SRA/ENG/3851/MW/PL/AP |  |  |  | Dated | 12/09/2018. | Expiry date:NA
C.certificate No |  | SRA/ENG/3851/MW/PL/AP This CC is Re endorsed for further extended for 4th to 9th floor for wing C, 1st to 9th floor for wing A and 4th, 5th(pt) floor for wing B |  |  |  | Dated | 12/09/2018.
C.certificate No |  | SRA/ENG/3851/MW/PL/AP This CC is granted for 9th to 12th upper floors incl. LMR & OHWT to Sale Wing A & 5th (Pt) upper floor for Sale Wing B & 6th to 12th upper floors for RCC frame work Sale Wing B & 9th to 12th upper floors incl. LMR & OHWT for Sale Wing C as per approved amended plan dtd 24/12/2019. |  |  |  | Dated | 23/07/2020.
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 12/09/2018. |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 7296.3 |  | Approved no of units |  |  | NA
Approved no of Floors |  | Wing A & C - Pit parking + Stilt + 1st to 10th floor, Wing B - Pit parking + Stilt + 1st to 5th(pt) floor |  |  | No of floors at site : See Construction details
Proposed no of Floors |  | Stilt/Ground + 1st to 12th upper floor (All wings)
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Wing A, B & C = G + 1st to 12th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 10 Floor, Painting upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 10 Floor, Painting upto 4 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% |  | 85% |  | 94.17% |  | Excavation in process | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% | [5 empty] | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 83.33% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 33.33% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 12
Construction details: |  | Wing C = G + 1st to 13th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 10 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 13
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 10 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% |  | 52.91% |  | 76.7% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% | [5 empty] | Excavation Completed | 13
RCC (Including podiums) |  | 13 | 92.86% | [5 empty] | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 10 | 76.92% | [5 empty] | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 13
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Carpet area) | [5 empty] | 27000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 600000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 21600
Remarks: 1. Construction work is the same as last visit (dtd.07/04/2025), but work is in process at the time of the visit. (Slow Speed) 2. Car parking is subjected to authentic documentation. 3. We considered given rate verify by market inquire. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 5. We have updated CC taken from Rera 15/07/2024. 6. Since the project has received first CC on 23/07/2020., But construction work of Wing A, B & C is under construction. 7. As checked on RERA portal on date 14/07/2025, we have observed that above project name has changed to Safal Sai And Safal Sainath. Please check from your end. 7. As per RERA, completion period of project Safal Sai is expired on 31/03/2025 but still project is under construction. | [8 empty] | Hiten Adani - 7303199999.
Authorized Signatory Name & Seal of the agency
Photographs of Property : |  |  | Safal Sai
`
Google Map :
Wing B
Wing C
Wing A
Wing B

## A %
Particulars | totaL floor | 13
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 92.8571 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 14 | 13 | 76.9231 | Progress |  |  | 10 | 37.1429 | 11.5385 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 27.8571 | 11.5385 | 0 | 0 | 0 | 0
| 13 | 10 | 0
plaster | Total Floor | completed Floor | 0
| 13 | 0 | 0
Flooring | Total Floor | completed Floor
| 13 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 13 | 0 |  | RCC | 37.1429 | 27.8571
Finishing | Total Floor | completed Floor |  | Bricks | 11.5385 | 11.5385
| 13 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 58.6813 | 69.3956

## B %
Particulars | totaL floor | 13
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 78.5714 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 14 | 11 | 53.8462 | Progress |  |  | 10 | 31.4286 | 8.0769 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 23.5714 | 8.0769 | 0 | 0 | 0 | 0
| 13 | 7 | 0
plaster | Total Floor | completed Floor | 0
| 13 | 0 | 0
Flooring | Total Floor | completed Floor
| 13 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 13 | 0 |  | RCC | 31.4286 | 23.5714
Finishing | Total Floor | completed Floor |  | Bricks | 8.0769 | 8.0769
| 13 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 49.5055 | 61.6484

## C %
Particulars | totaL floor | 13
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 92.8571 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 14 | 13 | 61.5385 | Progress |  |  | 10 | 37.1429 | 9.2308 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 27.8571 | 9.2308 | 0 | 0 | 0 | 0
| 13 | 8 | 0
plaster | Total Floor | completed Floor | 0
| 13 | 0 | 0
Flooring | Total Floor | completed Floor
| 13 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 13 | 0 |  | RCC | 37.1429 | 27.8571
Finishing | Total Floor | completed Floor |  | Bricks | 9.2308 | 9.2308
| 13 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 56.3736 | 67.0879

## Note
2020-10-12
2020-01-13 | Pratiksha

## Valuation
2020-10-12 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| 99acres | Safal Sai | 1BHK | 431 | 646.5 | 17788.0897 | 11500000
| 99acres | Safal Sai | 2BHK | 630 | 945 | 17566.1376 | 16600000
| MagicBrick | Safal Sai | 1BHK | 456 | 752 | 15957.4468 | 12000000
| MagicBrick | Safal Sai | 2BHK | 696 | 1100 | 17000 | 18700000
| MagicBrick | Safal Sai | 1BHK | 738 | 1107 | 17615.1762 | 19500000
| Average |  |  |  |  | 17677.1136
| Valuation Adopted |  |  |  |  | 17700

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0