## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-09 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Deraiya Realtors Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Deraiya Realtors Private Limited | [9 empty] | IBHF Thane
Name of the Project as per Rera |  |  |  | Nehru Nagar Nirmal C.H.S. Ltd. | [9 empty] | IBHF Andheri
Name of the Project as per Builder |  |  |  | Deraiya Classico | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 9082495942
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Anand 8368127481
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | Nehru Nagar Nirmal CHSL / Building No.8 | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Cost Sheet | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800050064 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Nehru Nagar Nirmal C.H.S. Ltd., CTS No.11 (Pt), S.No.229 & 267 & Redevelopment of building "Nehru Nagar Nirmal CHSL & Building No.8", near Mangalprabhat CHS, Kedarnath Temple Road, Nehru Nagar, Kurla, Kurla (East), Kurla, Mumbai - 400024. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 11 (Pt), S.No.229 & 267 & Redevelopment of building "Nehru Nagar Nirmal CHSL & Building No.8" | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Nehru Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Kedarnath Temple Road |  | Locality/Village |  | Kurla | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kurla (East) |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400024 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Mangalprabhat CHS |  | Distance from city centre: |  | 3.6 KM from Kurla Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 12.20 M Wide Existing Road |  |  | Kedarnath Temple Road
West | NA | Nalla |  |  | Nalla
North | NA | Building No.7 |  |  | Saptarshi Classic Apartment
South | NA | Building No.9 |  |  | Mangalprabhat CHS
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.061230,72.879521
Location Link |  | https://maps.app.goo.gl/6jiJ52ZbsFuhqYL26
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 952.57
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 2.6295
Total FSI availaible for the project |  |  |  | 5.6295
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5362.51
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority(MHADA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Mhada-22/1205/2022 |  |  | Dated | 2023-11-29 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | Mhada-22/1205/2022 |  |  | Dated | 2023-11-29 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-22/1205/2023/CC/1/New |  |  | Dated | 2023-02-27 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is permitted upto Plinth level as per approved I.O.A. plans dtd. 25.11.2022. |  |  | Valid Upto Date | 2024-02-26 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-22/1205/2024/FCC/1/New |  |  | Dated | 2024-01-16 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is further extended upto top of 13th floor i.e. Wing A & Wing B consist of Basement for Pump Room + Ground (pt) + Stilt (pt) + 1st to 11th + 12 & 13th (pt) upper floor (Including OHT + LMR)as per approved amended plan dtd. 29.11.2023. |  |  | Valid Upto Date | 2025-02-26 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [10 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Building wise Construction details | [17 empty] | Town Planning Thane | Raigad Zilha Parishad
Approved area of building (Sq.Mt) |  |  | 5362.51 | [14 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Approved no of units |  |  | Sale Flats - 109, Rehab Flats - 40 | [14 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Approved no of Floors |  |  | Wing A & B = 1B +Gr/Stilt + 1st to 13th Floor | [14 empty] | Bhiwandi Nizampur City Municipal Corporation
Proposed no of Floors |  |  | Wing A & B = 1B +Gr/Stilt + 1st to 13th Floor | [14 empty] | Maharashtra Industrial Development Corporation (MIDC)
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Children's Play Area, Landscape Garden, Walking Track, Rooftop Reading Deck, Meditation Are, Yoga Zone, Gymnasium, CCTV Surveillance
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = 1B +Gr/Stilt + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 9 Floor, Flooring upto 3 Floor Completed | , External Plaster upto 9 Floor, Flooring upto 3 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 9 Floor, Flooring upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 74.23% |  | 89.62% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 69.23% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 23.08% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | Wing B = 1B +Gr/Stilt + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 11 Floor, Flooring upto 3 Floor Completed | , External Plaster upto 11 Floor, Flooring upto 3 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 11 Floor, Flooring upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 75.77% |  | 90.38% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 84.62% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 23.08% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Online | Cost sheet | Visitor
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 12500 |  |  | 11992.1308 | 13348.2616 | 10636
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 75000
Infrastructure & LUC Tax |  |  |  |  | 100000
Club Charges
Gas Connection Charges
Water & Electricity Charges |  |  |  |  | 40000
Society Formation Charges |  |  |  |  | 25000
Miscellaneous Expenditure |  |  |  |  | 10000
Maintenance Charges for 12 months |  |  |  |  | 25000
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 10000
Residential Area Details : (Sale)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 57 |  | 22034.4462 |  | 33051.6693
Wing B |  | 52 |  | 22240.1462 |  | 33360.2194
Total |  | 109 |  | 44274.5924 |  | 66411.8887
Residential Area Details : (Rehab)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 20 |  | 10678.9644 |  | 16018.4466
Wing B |  | 20 |  | 10611.5818 |  | 15917.3726
Total |  | 40 |  | 21290.5462 |  | 31935.8192
Grand Total |  | 149 |  | 65565.1386 |  | 98347.7079
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Sale / Rehab | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 50% |  |  | 106
Wing A
Basement For Meter Panel Room, Space For Storage of Household, Flushing Tank & PIT Parking | [8 empty] | 10.764
Ground Floor for Residential & Parking | [8 empty] | 10.764
MP 1 | Sale | MP Room | 244.1275 | 0 | 244.1275 | 0 | 366.1913 | 22.8996
MP 2 | Sale | MP Room | 289.9822 | 0 | 289.9822 | 0 | 434.9732
2 | - | Entrance Room, Meter Room & Parking |  |  |  |  | -
3 | - | [5 empty] | -
4 | Sale | 1.5BHK | 531.311 | 0 | 531.311 | 0 | 796.9666
5 | Sale | 1BHK | 359.8405 | 0 | 359.8405 | 0 | 539.7608 | 31.3775 | 13339.2426
6 | Sale | 1BHK | 376.5247 | 0 | 376.5247 | 0 | 564.7871
1st Floor For Residential
MP 1 | Sale | MP Room | 359.6252 | 0 | 359.6252 | 0 | 539.4379
MP 2 | Sale | MP Room | 380.3998 | 0 | 380.3998 | 0 | 570.5996
2 | Sale | 1BHK | 390.195 | 0 | 390.195 | 0 | 585.2925 |  | 14047.677
3 | Sale | 1BHK | 400.2055 | 0 | 400.2055 | 0 | 600.3083 |  | 13992.8105
4 | Rehab | 1.5BHK | 531.311 | 0 | 531.311 | 0 | 796.9666
5 | Sale | 1BHK | 359.8405 | 0 | 359.8405 | 0 | 539.7608 | 31.4825
6 | Rehab | 1.5BHK | 536.5854 | 0 | 536.5854 | 0 | 804.8781
2nd to 7th, 9th & 10th Floor
1 | Sale | 1BHK | 417.2126 | 0 | 417.2126 | 0 | 625.819 |  | 13901.784
2 | Sale | 1BHK | 390.195 | 0 | 390.195 | 0 | 585.2925
3 | Sale | 1BHK | 400.2055 | 0 | 400.2055 | 0 | 600.3083
4 | Rehab | 1.5BHK | 531.311 | 0 | 531.311 | 0 | 796.9666
5 | Sale | 1BHK | 359.8405 | 0 | 359.8405 | 0 | 539.7608
6 | Rehab | 1.5BHK | 536.5854 | 0 | 536.5854 | 0 | 804.8781
8th Floor (Part Refuge Area)
1 | - | Refuge Area |  |  |  |  | -
2 | Sale | 1BHK | 390.195 | 0 | 390.195 | 0 | 585.2925
3 | Sale | 1BHK | 400.2055 | 0 | 400.2055 | 0 | 600.3083
4 | Rehab | 1.5BHK | 531.311 | 0 | 531.311 | 0 | 796.9666
5 | Sale | 1BHK | 359.8405 | 0 | 359.8405 | 0 | 539.7608 |  | 12059.0459
6 | Rehab | 1.5BHK | 536.5854 | 0 | 536.5854 | 0 | 804.8781
11th Floor
1 | Sale | 1BHK | 417.2126 | 0 | 417.2126 | 0 | 625.819
2 | Sale | 1BHK | 390.195 | 0 | 390.195 | 0 | 585.2925
3 | Sale | 1BHK | 400.2055 | 0 | 400.2055 | 0 | 600.3083
4 | Sale | 1BHK | 390.0874 | 0 | 390.0874 | 0 | 585.131
5 | Sale | MP Room | 262.1034 | 0 | 262.1034 | 0 | 393.1551 |  | 114951.2128
6 | Sale | 1BHK | 377.4935 | 0 | 377.4935 | 0 | 566.2402
12th Floor (Part Terrace Area)
1 | Sale | 1BHK | 417.2126 | 0 | 417.2126 | 0 | 625.819 |  | 126234.5903
2 | Sale | 1BHK | 390.195 | 0 | 390.195 | 0 | 585.2925
3 | Sale | 1BHK | 400.2055 | 0 | 400.2055 | 0 | 600.3083
4 | - | Terrace Area |  |  |  |  | -
5 | - | [5 empty] | -
6 | - | [5 empty] | -
13th Floor
1 | Sale | 1BHK | 417.2126 | 0 | 417.2126 | 0 | 625.819
2 | Sale | 1BHK | 390.195 | 0 | 390.195 | 0 | 585.2925 | 142
3 | Sale | 1BHK | 400.2055 | 0 | 400.2055 | 0 | 600.3083
Wing B
Basement For Pump Room, Domestic Tank, Fire Tank, Flushing Tank & PIT Parking
Ground Floor for Residential & Parking Pump Room & Parking
1 | - | Parking |  |  |  |  | - | 43.3775
2 | - | [5 empty] | -
3 | Sale | 1.5BHK | 537.8771 | 0 | 537.8771 | 0 | 806.8156
4 | Sale | MP Room | 266.8396 | 0 | 266.8396 | 0 | 400.2593
5 | Sale | MP Room | 167.7031 | 0 | 167.7031 | 0 | 251.5547
1st Floor For Residential
1 | Rehab | 1.5BHK | 535.1861 | 0 | 535.1861 | 0 | 802.7791 | 43.3775
2 | Sale | 1BHK | 418.8272 | 0 | 418.8272 | 0 | 628.2409
3 | Rehab | 1.5BHK | 537.8771 | 0 | 537.8771 | 0 | 806.8156
4 | Sale | 1BHK | 400.8514 | 0 | 400.8514 | 0 | 601.277
5 | Sale | 1BHK | 403.9729 | 0 | 403.9729 | 0 | 605.9594
2nd to 7th, 9th Floor
1 | Rehab | 1.5BHK | 535.1861 | 0 | 535.1861 | 0 | 802.7791
2 | Sale | 1BHK | 418.8272 | 0 | 418.8272 | 0 | 628.2409
3 | Rehab | 1.5BHK | 537.8771 | 0 | 537.8771 | 0 | 806.8156
4 | Sale | 1BHK | 400.8514 | 0 | 400.8514 | 0 | 601.277
5 | Sale | 1BHK | 403.9729 | 0 | 403.9729 | 0 | 605.9594
6 | Sale | 1.5BHK | 515.5956 | 0 | 515.5956 | 0 | 773.3934
10th Floor
1 | Rehab | 1.5BHK | 535.1861 | 0 | 535.1861 | 0 | 802.7791
2 | Rehab | 1BHK | 418.8272 | 0 | 418.8272 | 0 | 628.2409
3 | Sale | 1.5BHK | 537.8771 | 0 | 537.8771 | 0 | 806.8156
4 | Sale | 1BHK | 400.8514 | 0 | 400.8514 | 0 | 601.277
5 | Sale | 1BHK | 403.9729 | 0 | 403.9729 | 0 | 605.9594
6 | Sale | 1.5BHK | 515.5956 | 0 | 515.5956 | 0 | 773.3934
8th Floor (Part Refuge Area)
1 | Rehab | 1.5BHK | 535.1861 | 0 | 535.1861 | 0 | 802.7791
2 | Sale | 1BHK | 418.8272 | 0 | 418.8272 | 0 | 628.2409
3 | Rehab | 1.5BHK | 537.8771 | 0 | 537.8771 | 0 | 806.8156
4 | Sale | 2BHK | 584.9158 | 0 | 584.9158 | 0 | 877.3736
5 | - | Refuge Area |  |  |  |  | -
6 | - | [5 empty] | -
11th Floor
1 | Sale | 1BHK | 371.8962 | 0 | 371.8962 | 0 | 557.8443
2 | Sale | MP Room | 296.1176 | 0 | 296.1176 | 0 | 444.1765
3 | Sale | MP Room | 378.0317 | 0 | 378.0317 | 0 | 567.0475
4 | Sale | 1BHK | 400.8514 | 0 | 400.8514 | 0 | 601.277
5 | Sale | 1BHK | 403.9729 | 0 | 403.9729 | 0 | 605.9594
6 | Sale | 1.5BHK | 515.5956 | 0 | 515.5956 | 0 | 773.3934 |  | 12749.0098
12th Floor (Part Terrace Area)
1 | - | Terrace Area |  |  |  |  | -
2 | - | [5 empty] | -
3 | - | [5 empty] | -
4 | Sale | 1BHK | 400.8514 | 0 | 400.8514 | 0 | 601.277
5 | Sale | 1BHK | 403.9729 | 0 | 403.9729 | 0 | 605.9594
6 | Sale | 1.5BHK | 515.5956 | 0 | 515.5956 | 0 | 773.3934
13th Floor
4 | Sale | 1BHK | 400.8514 | 0 | 400.8514 | 0 | 601.277
5 | Sale | 1BHK | 403.9729 | 0 | 403.9729 | 0 | 605.9594
6 | Sale | 1.5BHK | 515.5956 | 0 | 515.5956 | 0 | 773.3934
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Construction work is in process at the time of Visit. Internal Visit was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Nalla is located west side to the project.
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved CC from MHADA site on 15/07/2024.
* | Validity of CC is expired on 26/02/2024. Please provide latest approved CC.
* | We have updated revised approved Plans & CC Revalidation Letter on 06/08/2024.
* | Validity of CC is expired on 26/02/2025. Please provide revised CC.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Nehru Nagar Nirmal C.H.S. Ltd.
Layout :
Google Map :
Formulas:
Kurla = [Kurla, row above]
Nalla
Note on E13: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E14: Sachin: If exisiting Building is provided write it or else NA
Note on D59: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar