## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 15/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-10
Name of the builder group |  |  |  |  | M/s.Shakti Developers
Name of the builder company |  |  |  |  | M/s.Shakti Developers
Name of the Project |  |  |  |  | The Green Orchid Phase III
Contact Details ( Name & Contact No.) |  |  |  |  | 9819933845
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Monish 7507459045 |  |  |  |  | 8421346925
Name / No of the Building |  |  |  |  | A Wing = Blossom B Wing = Daisy C Wing = Hibiscus D Wing = Jasmine
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000022859
Project location details |  | The Green Orchid Phase III, Survey No.S.No.136/1 (Old S.No.86, H.No.4), S.No.136/40 (Old S.No.86, H.No.4), 81/2, 81/3, 86/3, Station Road, Bandhiwali, Shelu , Karjat, Raigad.
Survey No |  | S.No.136/1 (Old S.No.86, H.No.4), S.No.136/40 (Old S.No.86, H.No.4), 81/2, 81/3, 86/3
Road |  | Station Road |  |  | Locality/Village |  | Bandhiwali
City |  | Shelu |  |  | District |  | Raigad
Taluka |  | Karjat |  |  | Pin Code |  | 410101
Near by Landmark |  | Excell Finserv |  |  | Distance from city centre: |  | About 1.3Km from Shelu Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.0587 |  | Longitude |  | 73.324
Location Link |  | https://goo.gl/maps/MW7r3UaoTXsbgSZq8
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 16550
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 19582.46
Total number of Buildings |  |  |  |  | 04 Wings
Approval Detail : Plan approval
Layout Approval No |  | MS/LNA-1/S.R/97/2021 |  |  |  | Dated | 2022-05-13
Approved Floor plan No. |  | MS/LNA-1/S.R/97/2021 |  |  |  | Dated | 2022-05-13
Commencement Certificate No. |  | MS/LNA/A.1(B)/T.No.15826/P.K.97/2021 Valid Up to: A, B, C & D Wing = Gr/Stilt + 1st to 6th Floor |  |  |  | Dated | 2022-05-13
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 44694 |  | Expected Completion |  | 30/12/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5711.92 |  | Approved no of units |  | Flats = 158
Approved no of Floors |  | A & B Wing = G + 1st to 5th + 6th(pt)Floor C & D Wing = G + 1st to 5th + 6th(pt)Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | A Wing (Blossom) = G + 1st to 5th + 6th(pt)Floor B Wing (Daisy) = G + 1st to 5th + 6th(pt)Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 7 Slab completed, Brickwork upto 6 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 4 Floor completed, Painting upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 6 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 7 Slab completed, Brickwork upto 6 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 4 Floor completed, Painting upto 3 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 1.5
Excavation |  | 6 | 100% |  | 84.17% |  | 93.33% |  | Excavation in process |  | 3
Plinth |  | 6 | 100% | [5 empty] | Excavation Completed |  | 6
RCC |  | 7 | 100% | [5 empty] | Footing in Process |  | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Footing Completed |  | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 100% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 66.67% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 3 | 50% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 4.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 6
Construction details: |  | C Wing (Hibiscus) = G + 1st to 5th + 6th(pt)Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 7 Slab completed, Brickwork upto 6 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 6 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 7 Slab completed, Brickwork upto 6 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 1.5
Excavation |  | 6 | 100% |  | 76.67% |  | 90.83% |  | Excavation in process |  | 3
Plinth |  | 6 | 100% | [5 empty] | Excavation Completed |  | 6
RCC |  | 7 | 100% | [5 empty] | Footing in Process |  | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Footing Completed |  | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 83.33% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 2 | 33.33% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 4.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 6
Construction details: |  | D Wing (Jasmine) = G + 1st to 5th + 6th(pt)Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 7 Slab completed, Brickwork upto 6 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 1 Floor completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 6 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 7 Slab completed, Brickwork upto 6 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 1 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 1.5
Excavation |  | 6 | 100% |  | 75% |  | 90% |  | Excavation in process |  | 3
Plinth |  | 6 | 100% | [5 empty] | Excavation Completed |  | 6
RCC |  | 7 | 100% | [5 empty] | Footing in Process |  | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Footing Completed |  | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 83.33% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 1 | 16.67% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 4.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 6
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500
Club House Charges | [5 empty] | 30000/-
Grill Charges | [5 empty] | 60000/-
Legal charges | [5 empty] | 12000/-
Recommended rate of Parking | [5 empty] | 50000/-
Development charges | [5 empty] | 200000/-
Distressed valuation of the Property | [5 empty] | 2800
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
A Wing = Blossom |  | 36 | 14342.0612 |  |  | 21148.9404
B Wing = Daisy |  | 43 | 15671.7382 |  |  | 23087.3053
C Wing = Hibiscus |  | 43 | 15671.7382 |  |  | 23087.3053
D Wing = Jasmine |  | 36 | 14342.0612 |  |  | 21148.9404
Total |  | 158 | 60027.5988 |  |  | 88472.4914
Building details Floor Wise
Details of Flats in Building
Flat No. (As per Sale Plan) |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
A Wing (Blossom)
Ground Floor For Driver Room, Society Office, Entrance Looby, Parking & Residential
- |  | Driver Room/ Parking | [5 empty] | Ground Floor
- |  | Society Office
1 |  | 2BHK | 464.4128 |  | 0 | 673.3985 | N
2 |  | 1BHK | 348.7536 |  | 0 | 505.6927 | N
3 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N
1st To 5th Floor
1 |  | 1BHK | 348.7536 |  | 0 | 505.6927 | N | 1st To 5th Floor
2 |  | 2BHK | 464.4128 |  | 0 | 673.3985 | N
3 |  | 2BHK | 464.4128 |  | 0 | 673.3985 | N
4 |  | 1BHK | 348.7536 |  | 0 | 505.6927 | N
5 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N
6 |  | 1BHK | 387.7946 |  | 0 | 562.3022 | N
6th Floor (Part Terrace Area)
- |  | - | [5 empty] | 6th Floor (Part Terrace Area)
1 |  | 2BHK | 464.4128 |  | 348.7536 | 789.6497 | N
2 |  | 2BHK | 464.4128 |  | 348.7536 | 789.6497 | N
- |  | -
3 |  | 1BHK | 361.3475 |  | 361.3475 | 644.403 | N
- |  | Terrace Area
B Wing (Daisy)
Ground Floor For Entrance Lobby, Parking & Residential
1 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N | Ground Floor
2 |  | 1BHK | 365.0072 |  | 0 | 529.2605 | N |  |  |  |  | `
3 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
4 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
5 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
6 |  | Parking
7
1st To 5th Floor
1 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N | 1st To 5th Floor
2 |  | 1BHK | 365.0072 |  | 0 | 529.2605 | N
3 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
4 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
5 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
6 |  | 1BHK | 365.0072 |  | 0 | 529.2605 | N
7 |  | 1BHK | 358.2259 |  | 0 | 519.4276 | N
6th Floor (Part Terrace Area)
- |  | - | [5 empty] | 6th Floor (Part Terrace Area)
- |  | -
1 |  | 1BHK | 366.6218 |  | 365.0072 | 653.2707 | N
2 |  | 1BHK | 366.6218 |  | 366.6218 | 653.8089 | N
- |  | -
3 |  | 1BHK | 365.0072 |  | 358.2259 | 648.6691 | N
7 |  | -
C Wing (Hibiscus)
Ground Floor For Entrance Lobby, Parking & Residential
1 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N | Ground Floor
2 |  | 1BHK | 365.0072 |  | 0 | 529.2605 | N |  |  |  |  | `
3 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
4 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
5 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
6 |  | Parking
7
1st To 5th Floor
1 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N | 1st To 5th Floor
2 |  | 1BHK | 365.0072 |  | 0 | 529.2605 | N
3 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
4 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
5 |  | 1BHK | 366.6218 |  | 0 | 531.6017 | N
6 |  | 1BHK | 365.0072 |  | 0 | 529.2605 | N
7 |  | 1BHK | 358.2259 |  | 0 | 519.4276 | N
6th Floor (Part Terrace Area)
- |  | - | [5 empty] | 6th Floor (Part Terrace Area)
- |  | -
1 |  | 1BHK | 366.6218 |  | 365.0072 | 653.2707 | N
2 |  | 1BHK | 366.6218 |  | 366.6218 | 653.8089 | N
- |  | -
3 |  | 1BHK | 365.0072 |  | 358.2259 | 648.6691 | N
7 |  | -
D Wing (Jasmine)
Ground Floor For Driver Room, Society Office, Entrance Looby, Parking & Residential
- |  | Driver Room/ Parking | [5 empty] | Ground Floor
- |  | Society Office
1 |  | 2BHK | 464.4128 |  | 0 | 673.3985 | N
2 |  | 1BHK | 348.7536 |  | 0 | 505.6927 | N
3 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N
1st To 5th Floor
1 |  | 1BHK | 348.7536 |  | 0 | 505.6927 | N | 1st To 5th Floor
2 |  | 2BHK | 464.4128 |  | 0 | 673.3985 | N
3 |  | 2BHK | 464.4128 |  | 0 | 673.3985 | N
4 |  | 1BHK | 348.7536 |  | 0 | 505.6927 | N
5 |  | 1BHK | 361.3475 |  | 0 | 523.9538 | N
6 |  | 1BHK | 387.7946 |  | 0 | 562.3022 | N
6th Floor (Part Terrace Area)
- |  | - | [5 empty] | 6th Floor (Part Terrace Area)
1 |  | 2BHK | 464.4128 |  | 348.7536 | 789.6497 | N
2 |  | 2BHK | 464.4128 |  | 348.7536 | 789.6497 | N
- |  | -
3 |  | 1BHK | 361.3475 |  | 361.3475 | 644.403 | N
- |  | Terrace Area
Remarks: | [12 empty] | sd
1. Wing A, B, C & D = Construction work is in process at the time of visit. (Slow Speed) 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Balcony Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. We have considered Other charges from cost sheet. 8. Car parking is subjected to authentic documentation. 9. We have updated revised plans (on 19/10/2023). 10. We have updated latest CC (On 26/07/2024).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | The Green Orchid Phase III
Google Map :
Formulas:
Bandhiwali = [Bandhiwali, row above]
A Wing
B Wing
C Wing
D Wing
A Wing
C Wing
B Wing
D Wing

## B & C Wing -C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 1 | 10%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 1 | 21 |  | Progress |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 21 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 1% | 21% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## A & D Wing - C% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 2 | 40% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 16 | 0 | 0 | 0 | 0 | 0
RCC | 16 | 12 |  | Recommended |  | 30 | 12 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 26% | 42% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
Date |  | Description
02/03/2020.
Rate As per site 1RK = 13Lac, 1BHK = 20 to 23Lac.
match builder cost sheet = 3200/- & 2900/-
online = 2850/-
04/07/2020. | Pratiksha | 8. On Site, we meet Mr.Patel - Builder (9987892360). | cost sheet match - 3300/-
2020-12-15 | Pratiksha

## valuation
2020-12-15 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing | The Green Orchid | 1RK | 218 | 316.1 | 3514.7105 | 1111000
| Housing | The Green Orchid | 1BHK | 308 | 446.6 | 3414.6888 | 1525000
| Proptiger | The Green Orchid | 1RK | 218 | 316.1 | 3514.7105 | 1111000
| Average |  |  |  |  | 3481.3699
| Valuation Adopted |  |  |  |  | 3500

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0