## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s. Raymond Limited
Name of the builder company |  |  |  | M/s. Raymond Limited
Name of the Project |  |  |  | Ten X Habitat Raymond Realty Tower F & G
Contact Details ( Name & Contact No.) |  |  |  | Mayur Parte 7700023042
Name / No of the Building |  |  |  | Tower F & G
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Tower F - P51700034190 Tower G - P51700047152 |  |  |  | P51700047152
Project location details |  | Ten X Habitat Raymond Realty Tower F & G, Survey No.122, 126B1/1, 126B/2, 126B1/3, 127, 128/B, 129/1, 129/3, near Smt. Sunitidevi Singhania school, Pokharan Road Number 2, , Panchpakhadi, Thane West, Thane, Thane - 400606.
Survey No |  | 122, 126B1/1, 126B/2, 126B1/3, 127, 128/B, 129/1, 129/3
Locality
Road |  | Pokharan Road Number 2 |  | Village |  | Panchpakhadi
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400606
Nearby Landmark |  | Smt. Sunitidevi Singhania school |  | Distance from city centre: |  | 4.5 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Smt. Sunitidevi Singhania school
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.213424,72.96819
Location Link |  | https://goo.gl/maps/Po4QyeAiBMXsz4y17
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 62497.59
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.86648
Total FSI availaible for the project |  |  |  | 1.8665
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 116650.74
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation (TMC)
Layout Approval No |  | S04/0161/19TMC/TD-DP/TPS/4089/22 |  |  | Dated | 2022-06-21
Approved Floor plan No. |  | TMC/TDD/4089/22/1 (V.P.No TMCB/TDD/0001/[P/C]/2022/AutoDCR) |  |  | Dated | 2022-12-26
Commencement-CC No Valid Up to: |  | TMCB/TDD/0001/[P/C]/2022/AutoDCR |  |  | Dated | 2022-12-26
Tower F & G = G + 1st to 50th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 116650.74
Approved no of units |  |  | Flats - 682
Approved no of Floors |  |  | Wing F & G = G + 1st to 50th Floor
Proposed no of Floors |  |  | Wing F = G + 1st to 50th Floor
Wing G = G + 1st to 50th Floor
Expected Completion |  |  | As per RERA - 31/03/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2.Granite Kitchen Platform 3.Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing F & G = G + 1st to 50th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 35 Floor, Painting upto 25 Floor Completed | , Flooring upto 35 Floor, Painting upto 25 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 50 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 35 Floor, Painting upto 25 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 12.5
Excavation |  | 50 | 100% | 84.5% |  | 93.5% |  | Excavation in process | 25
Plinth |  | 50 | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 51 | 100% |  |  |  |  | Footing in Process | 12.5
Brickwork | Brickwork & Internal Plaster | 50 | 100% |  |  |  |  | Footing Completed | 25
Internal Plaster | Brickwork & Internal Plaster | 50 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 50 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 35 | 70% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 25 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 37.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 50
Construction details: |  | Wing G = G + 1st to 50th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 36 Floor, Painting upto 23 Floor Completed | , Flooring upto 36 Floor, Painting upto 23 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 50 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 36 Floor, Painting upto 23 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 12.5
Excavation |  | 50 | 100% | 84.5% |  | 93.6% |  | Excavation in process | 25
Plinth |  | 50 | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 51 | 100% |  |  |  |  | Footing in Process | 12.5
Brickwork | Brickwork & Internal Plaster | 50 | 100% |  |  |  |  | Footing Completed | 25
Internal Plaster | Brickwork & Internal Plaster | 50 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 50 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 36 | 72% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 23 | 46% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 37.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 50
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 16600 |  |  | 15000 to 16600 | Sanket | Cost sheet | 2022-11-22
Other Charges |  |  |  |  | 300000
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 13280
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower F |  | 391 |  | 250359.2183 |  | 375538.8275
Tower G |  | 291 |  | 189804.5904 |  | 284706.8856
Total |  | 682 |  | 440163.8087 |  | 660245.7131
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Tower F
Ground Floor For Parking & Library
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28 to 31st, 33rd to 36th, 38th to 41st, 43rd to 46th & 48th to 50th Floor For Residential | [9 empty] | 10.764
1 |  | 2 | 680.6928 | 0 | 1021.0391 | 1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28 to 31st, 33rd to 36th, 38th to 41st, 43rd to 46th & 48th to 50th Floor For Residential |  |  |  | 56.0584 | 3.107 | 649.8238
2 |  | 2 | 528.4349 | 0 | 792.6523 | [6 empty] | 503.8359
3 |  | 2 | 528.4349 | 0 | 792.6523 | [6 empty] | 503.8359
4 |  | 2 | 680.6928 | 0 | 1021.0391 | [6 empty] | 649.4621
5 |  | 2 | 676.0955 | 0 | 1014.1432 | [6 empty] | 649.4621
6 |  | 2 | 679.6314 | 0 | 1019.4471 | [6 empty] | 646.3965
7 |  | 2 | 679.6314 | 0 | 1019.4471 | [6 empty] | 646.3965
8 |  | 2 | 676.0955 | 0 | 1014.1432 | [6 empty] | 649.8238
Service Floor Inbetween 26th & 27th Floor
7th, 12th, 17th, 22nd, 27th, 32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
1 |  | 2 | 680.6928 | 0 | 1021.0391 | 7th, 12th, 17th, 22nd, 27th, 32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
2 |  | 2 | 528.4349 | 0 | 792.6523 |  |  |  |  | 2.0889
3 |  | 2 | 528.4349 | 0 | 792.6523
4 |  | Refuge Area
5 |  | 2 | 676.0955 | 0 | 1014.1432
6 |  | 2 | 679.6314 | 0 | 1019.4471
7 |  | 2 | 679.6314 | 0 | 1019.4471
8 |  | 2 | 676.0955 | 0 | 1014.1432
Tower G
Ground Floor For Parking & Library
1st Floor For Residential | [9 empty] | 10.764
1 |  | 2 | 649.109 | 0 | 973.6635 | 1st Floor For Residential |  |  | 649.109 |  | 3.107 | 649.8238
2 |  | 2 | 649.109 | 0 | 973.6635 |  |  |  | 649.109 |  |  | 503.8359
3 |  | 2 | 647.5299 | 0 | 971.2949 |  |  |  | 647.5299 |  |  | 503.8359
4 |  | 2 | 654.7289 | 0 | 982.0934 |  |  |  | 654.7289 |  |  | 649.4621
5 |  | 2 | 657.6998 | 0 | 986.5497 |  |  |  | 657.6998 |  |  | 649.4621
6 |  | 2 | 654.7547 | 0 | 982.1321 |  |  |  | 654.7547 |  |  | 646.3965
2nd to 6th, 8th to 11th, 13th to 15th Floor For Residential
1 |  | 2 | 649.109 | 0 | 973.6635 | 2nd to 6th, 8th to 11th, 13th to 15th Floor For Residential
2 |  | 2 | 649.109 | 0 | 973.6635
3 |  | 2 | 647.5299 | 0 | 971.2949
4 |  | 2 | 654.7289 | 0 | 982.0934
5 |  | 2 | 657.6998 | 0 | 986.5497
6 |  | 2 | 654.7547 | 0 | 982.1321
7th & 12th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th & 12th Floor (Part Refuge Area)
2 |  | 2 | 649.109 | 0 | 973.6635
3 |  | 2 | 647.5299 | 0 | 971.2949
4 |  | 2 | 654.7289 | 0 | 982.0934
5 |  | 2 | 657.6998 | 0 | 986.5497
6 |  | 2 | 654.7547 | 0 | 982.1321
16th, 18th to 21st, 23rd to 26th, 28th to 30th Floor
1 |  | 2 | 649.109 | 0 | 973.6635 | 16th, 18th to 21st, 23rd to 26th, 28th to 30th Floor
2 |  | 2 | 649.109 | 0 | 973.6635
3 |  | 2 | 647.5299 | 0 | 971.2949
4 |  | 2 | 654.7289 | 0 | 982.0934
5 |  | 2 | 657.6998 | 0 | 986.5497
6 |  | 2 | 654.7547 | 0 | 982.1321
17th, 22nd & 27th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 17th, 22nd & 27th Floor (Part Refuge Area)
2 |  | 2 | 649.109 | 0 | 973.6635
3 |  | 2 | 647.5299 | 0 | 971.2949
4 |  | 2 | 654.7289 | 0 | 982.0934
5 |  | 2 | 657.6998 | 0 | 986.5497
6 |  | 2 | 654.7547 | 0 | 982.1321
31st, 33rd to 36th, 38th to 41st, 43rd to 46th, 48th to 50th Floor
1 |  | 2 | 649.109 | 0 | 973.6635 | 31st, 33rd to 36th, 38th to 41st, 43rd to 46th, 48th to 50th Floor
2 |  | 2 | 649.109 | 0 | 973.6635
3 |  | 2 | 647.5299 | 0 | 971.2949
4 |  | 2 | 654.7289 | 0 | 982.0934
5 |  | 2 | 657.6998 | 0 | 986.5497
6 |  | 2 | 654.7547 | 0 | 982.1321
32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
2 |  | 2 | 649.109 | 0 | 973.6635
3 |  | 2 | 647.5299 | 0 | 971.2949
4 |  | 2 | 654.7289 | 0 | 982.0934
5 |  | 2 | 657.6998 | 0 | 986.5497
6 |  | 2 | 654.7547 | 0 | 982.1321
Remarks:
* | Construction work is in process at the time of Visit. (Internal photographs not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Chajja + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated Approved Floor Plan of Tower F (on 25/01/2023).
* | We have updated Approved Floor Plan of Tower G (on 08/02/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ten X Habitat Raymond Realty Tower F & G
Google Map :
K
I
H
G
F
J

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted