## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | Varsha Buildcon
Name of the builder company |  |  |  | Varsha Buildcon
Name of the Project |  |  |  | Balaji Vista
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Chunilal Choudhari (9322901002)
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr.Sakharam : 9321062719
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000046718
Project location details |  | Balaji Vista, Plot No.32, Sector 17, near Bhoomi Landmark, Internal Road, Khanda Colony, New Panvel, New Panvel (West), Panvel, Raigad - 410206.
Plot No |  | 32, Sector 17
Locality |  | Khanda Colony
Road |  | Internal Road |  | Locality/Village |  | New Panvel
City |  | New Panvel (West) |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Bhoomi Landmark |  | Distance from city centre: |  | 1.1KM from Khandeshwar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Bhoomi Landmark
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Shri Sai Shraddha CHS
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.0061 |  | Longitude |  | 73.106
Location Link |  | https://goo.gl/maps/R7EbhGzB9YoT9iwR7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4029.3
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.5844
Total FSI availaible for the project |  |  |  | 3.0844
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12428.01
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation (PMC)
Layout Approval No |  | PMP/NRV/16354/JK-1976/2022 |  |  | Dated | 2022-06-30
Approved Floor plan No. |  | PMP/NRV/16354/JK-1976/2022 |  |  | Dated | 2022-06-30
Commencement-CC No Valid Up to: |  | PMC/TP/N.Panvel/17/32/21-22/16354/1976/2022 |  |  | Dated | 2022-06-30
Wing A & B = Basment + Gr + 1st to 14th Upper Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 12428.01
Approved no of units |  |  | Flats -120, Shops -20, Offices -20
Approved no of Floors |  |  | Wing A & B = Basment + Gr + 1st to 14th Upper Floor
Proposed no of Floors |  |  | Wing A = Basment + Gr + 1st to 14th Upper Floor
Wing B = Basment + Gr + 1st to 14th Upper Floor
C Wing = G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/05/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative Entrance
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Basment + Gr + 1st to 14th Upper Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 7 Floor, Painting upto 5 Floor Completed | , External Plaster upto 12 Floor, Flooring upto 7 Floor, Painting upto 5 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 7 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 80.36% |  | 91.79% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 50% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 35.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing B = Basment + Gr + 1st to 14th Upper Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 7 Floor, Painting upto 5 Floor Completed | , External Plaster upto 12 Floor, Flooring upto 7 Floor, Painting upto 5 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 7 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 80.36% |  | 91.79% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 50% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 35.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | C Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 9400 |  |  | 8100
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 18500
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 15500
Development Charges |  |  |  |  | 455000
Development Charges
Club Membership |  |  |  |  | 350000
Grill Charges |  |  |  |  | 75000
Legal Charges |  |  |  |  | 10500
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 100000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 500000 |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 7520
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | rate sheet
Wing A & B | Shop | 20 |  | 8724.222 |  | 13958.7552 |  |  | visitor | cost sheet
| Office | 20 |  | 4860.1936 |  | 7776.3097 |  |  | 8100 | 9100
Total |  | 40 |  | 13584.4156 |  | 21735.0649
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 157155.3693 | 103293.0662
Wing A |  | 61 |  | 45487.7248 |  | 68730.5525
Wing B |  | 59 |  | 44220.9258 |  | 66689.7519
Total |  | 120 |  | 89708.6507 |  | 135420.3044
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing A + B
Basement Floor for Parking
Ground Floor For Commercial & Parking
1 |  | Shop | 336.7625 | 0 | 538.82 | Ground Floor For Commercial & Parking |  | 339.3779 | 10.764
2 |  | Shop | 346.1164 | 0 | 553.7863 | Ground Floor For Commercial & Parking
3 |  | Shop | 465.317 | 0 | 744.5071 | Ground Floor For Commercial & Parking
4 |  | Shop | 465.952 | 0 | 745.5233 | Ground Floor For Commercial & Parking
5 |  | Shop | 462.0985 | 0 | 739.3576 | Ground Floor For Commercial & Parking |  | 466.8939
6 |  | Shop | 442.1744 | 0 | 707.479 | Ground Floor For Commercial & Parking
7 |  | Shop | 460.3548 | 0 | 736.5676 | Ground Floor For Commercial & Parking |  | 18701.6099
8 |  | Shop | 446.1893 | 0 | 713.9029 | Ground Floor For Commercial & Parking
9 |  | Shop | 464.8541 | 0 | 743.7666 | Ground Floor For Commercial & Parking |  | 18554.2086
10 |  | Shop | 472.6149 | 0 | 756.1839 | Ground Floor For Commercial & Parking
11 |  | Shop | 472.6149 | 0 | 756.1839 | Ground Floor For Commercial & Parking
12 |  | Shop | 464.8541 | 0 | 743.7666 | Ground Floor For Commercial & Parking
13 |  | Shop | 446.1893 | 0 | 713.9029 | Ground Floor For Commercial & Parking
14 |  | Shop | 460.3548 | 0 | 736.5676 | Ground Floor For Commercial & Parking
15 |  | Shop | 442.1744 | 0 | 707.479 | Ground Floor For Commercial & Parking
16 |  | Shop | 462.0985 | 0 | 739.3576 | Ground Floor For Commercial & Parking
17 |  | Shop | 465.3062 | 0 | 744.4899 | Ground Floor For Commercial & Parking
18 |  | Shop | 465.317 | 0 | 744.5071 | Ground Floor For Commercial & Parking
19 |  | Shop | 346.1164 | 0 | 553.7863 | Ground Floor For Commercial & Parking
20 |  | Shop | 336.7625 | 0 | 538.82 | Ground Floor For Commercial & Parking
1st Floor For Commercial & Parking
1 |  | Office | 238.4764 | 0 | 381.5623 | 1st Floor For Commercial & Parking |  | 233.4356
2 |  | Office | 238.4764 | 0 | 381.5623 | 1st Floor For Commercial & Parking
3 |  | Office | 258.4652 | 0 | 413.5443 | 1st Floor For Commercial & Parking |  | 11570.708
4 |  | Office | 272.4368 | 0 | 435.8989 | 1st Floor For Commercial & Parking
5 |  | Office | 265.1496 | 0 | 424.2394 | 1st Floor For Commercial & Parking
6 |  | Office | 232.0934 | 0 | 371.3494 | 1st Floor For Commercial & Parking
7 |  | Office | 232.0934 | 0 | 371.3494 | 1st Floor For Commercial & Parking
8 |  | Office | 226.5284 | 0 | 362.4454 | 1st Floor For Commercial & Parking
9 |  | Office | 235.0642 | 0 | 376.1028 | 1st Floor For Commercial & Parking
10 |  | Office | 238.9716 | 0 | 382.3545 | 1st Floor For Commercial & Parking
11 |  | Office | 238.9716 | 0 | 382.3545 | 1st Floor For Commercial & Parking
12 |  | Office | 235.0642 | 0 | 376.1028 | 1st Floor For Commercial & Parking
13 |  | Office | 226.5284 | 0 | 362.4454 | 1st Floor For Commercial & Parking
14 |  | Office | 232.0934 | 0 | 371.3494 | 1st Floor For Commercial & Parking
15 |  | Office | 232.0934 | 0 | 371.3494 | 1st Floor For Commercial & Parking
16 |  | Office | 265.1496 | 0 | 424.2394 | 1st Floor For Commercial & Parking
17 |  | Office | 265.4725 | 0 | 424.7561 | 1st Floor For Commercial & Parking
18 |  | Office | 265.4725 | 0 | 424.7561 | 1st Floor For Commercial & Parking
19 |  | Office | 233.3958 | 0 | 373.4333 | 1st Floor For Commercial & Parking
20 |  | Office | 228.1968 | 0 | 365.1149 | 1st Floor For Commercial & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A
Basement Floor For Parking
Ground, Mezzanine & 1st Floor Level For Parking
2nd Floor For Residential & Amenities
1 |  | 2BHK | 630.8135 | 312.1129 | 1024.2484 | 2nd Floor For Residential & Amenities |  | 55.953 | 10.764 | 26.892
2 |  | 2BHK | 651.7817 | 404.1236 | 1078.7035 | 2nd Floor For Residential & Amenities
3 |  | 3BHK | 834.2638 | 353.4467 | 1339.7574 | 2nd Floor For Residential & Amenities
4 |  | 2BHK | 577.8976 | 363.7694 | 957.7888 | 2nd Floor For Residential & Amenities
3rd to 6th, 8th to 11th Floor For Residential
1 |  | 2BHK | 632.6084 | 0 | 948.9125 | 3rd to 6th, 8th to 11th Floor For Residential |  | 8366.103
2 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 3rd to 6th, 8th to 11th Floor For Residential
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 3rd to 6th, 8th to 11th Floor For Residential
4 |  | 3BHK | 974.4864 | 0 | 1461.7297 | 3rd to 6th, 8th to 11th Floor For Residential |  | 9170.9844
5 |  | 2BHK | 665.409 | 0 | 998.1134 | 3rd to 6th, 8th to 11th Floor For Residential
7th Floor (Part Refuge Area)
1 |  | 2BHK | 632.6084 | 0 | 948.9125 | 7th Floor (Part Refuge Area) |  | 9379.1574
2 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 7th Floor (Part Refuge Area)
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 7th Floor (Part Refuge Area)
4 |  | 3BHK | 974.4864 | 0 | 1461.7297 | 7th Floor (Part Refuge Area)
5 |  | 2BHK | 665.409 | 0 | 998.1134 | 7th Floor (Part Refuge Area)
12th Floor (Part Refuge Area)
1 |  | 2BHK | 632.6084 | 0 | 948.9125 | 12th Floor (Part Refuge Area)
2 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 12th Floor (Part Refuge Area)
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 12th Floor (Part Refuge Area)
4 |  | 3BHK | 948.4537 | 0 | 1422.6806 | 12th Floor (Part Refuge Area)
5 |  | 2BHK | 623.6662 | 0 | 935.4992 | 12th Floor (Part Refuge Area) |  | 605.9486
13th Floor
1 |  | 2BHK | 632.6084 | 0 | 948.9125 | 13th Floor
2 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 13th Floor
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 13th Floor
4 |  | 3BHK | 948.4537 | 0 | 1422.6806 | 13th Floor
5 |  | 2BHK | 623.6662 | 0 | 935.4992 | 13th Floor
14th Floor (Part Terrace Area)
1 |  | 2BHK | 718.384 | 48.9977 | 1126.5737 | 14th Floor (Part Terrace Area)
2 |  | 1BHK | 548.415 | 366.4173 | 914.2269 | 14th Floor (Part Terrace Area)
Wing B
Basement Floor For Parking
Ground, Mezzanine & 1st Floor Level For Parking
2nd Floor For Residential & Amenities
1 |  | 2BHK | 577.8976 | 363.7694 | 957.7888 | 2nd Floor For Residential & Amenities
2 |  | 3BHK | 834.2638 | 353.4467 | 1339.7574 | 2nd Floor For Residential & Amenities
3 |  | 2BHK | 651.7817 | 404.1236 | 1078.7035 | 2nd Floor For Residential & Amenities
4 |  | 2BHK | 630.8135 | 312.1129 | 1024.2484 | 2nd Floor For Residential & Amenities
3rd to 6th, 8th to 11th Floor For Residential
1 |  | 2BHK | 665.409 | 0 | 998.1134 | 3rd to 6th, 8th to 11th Floor For Residential
2 |  | 3BHK | 974.4864 | 0 | 1461.7297 | 3rd to 6th, 8th to 11th Floor For Residential
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 3rd to 6th, 8th to 11th Floor For Residential
4 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 3rd to 6th, 8th to 11th Floor For Residential
5 |  | 2BHK | 632.6084 | 0 | 948.9125 | 3rd to 6th, 8th to 11th Floor For Residential
7th Floor (Part Refuge Area)
1 |  | 2BHK | 665.409 | 0 | 998.1134 | 7th Floor (Part Refuge Area)
2 |  | 3BHK | 974.4864 | 0 | 1461.7297 | 7th Floor (Part Refuge Area) |  | 9170.9844
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 7th Floor (Part Refuge Area)
4 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 7th Floor (Part Refuge Area)
5 |  | 2BHK | 632.6084 | 0 | 948.9125 | 7th Floor (Part Refuge Area)
12th Floor (Part Refuge Area)
1 |  | 2BHK | 623.6662 | 0 | 935.4992 | 12th Floor (Part Refuge Area)
2 |  | 3BHK | 948.4537 | 0 | 1422.6806 | 12th Floor (Part Refuge Area)
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 12th Floor (Part Refuge Area)
4 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 12th Floor (Part Refuge Area)
5 |  | 2BHK | 632.6084 | 0 | 948.9125 | 12th Floor (Part Refuge Area)
13th Floor
1 |  | 2BHK | 623.6662 | 0 | 935.4992 | 13th Floor
2 |  | 3BHK | 948.4537 | 0 | 1422.6806 | 13th Floor
3 |  | 2BHK | 767.3817 | 0 | 1151.0726 | 13th Floor
4 |  | 2BHK | 747.5437 | 0 | 1121.3155 | 13th Floor
5 |  | 2BHK | 632.6084 | 0 | 948.9125 | 13th Floor |  | 8366.103
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Balaji Vista
Layout Plan :
Balaji Vista
Balaji Vista
Google Map :
Balaji Vista
Wing A
A Wing
B Wing
B Wing
A & B Wing
A & B Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted