## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | Shreenathji Enterprises
Name of the builder company |  |  |  | Shreenathji Enterprises
Name of the Project |  |  |  | Delta Greens
Contact Details ( Name & Contact No.) |  |  |  | 9428617913
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | NA |  |  |  | Mr. Sanjeev 9920891911
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000034901
Project location details |  | Delta Greens, Plot No.8, Sector - 4, near Ranumata Mandir, Internal Road, Pushpak Nagar, Dapoli, Dapoli, Panvel, Raigad - 410206.
Plot No |  | 8, Sector - 4
Locality |  | Pushpak Nagar
Road |  | Internal Road |  | Village |  | Dapoli
City |  | Dapoli |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Ranumata Mandir |  | Distance from city centre: |  | 7.4 KM from Khandeshwar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.97186134,73.0804506
Location Link |  | https://goo.gl/maps/cLWHvp4ykcAfyZ1M9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3409.67
Permissible FSI |  |  |  | 2
Permissible TDR/Paid FSI |  |  |  | 1.2149
Total FSI availaible for the project |  |  |  | 3.2149
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10961.698
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | City and Industrial Development Corporation (CIDCO)
Layout Approval No |  | CIDCO/BP-17925/TPO(NM & K)/ 2021/10062 |  |  | Dated | 2022-11-18
Approved Floor plan No. |  | CIDCO/BP-17925/TPO(NM & K)/ 2021/10062 |  |  | Dated | 2022-11-18
Commencement-CC No Valid Up to: |  | CIDCO/BP-17925/TPO(NM & K)/ 2021/10062 |  |  | Dated | 2022-11-17
Wing A & B = B + Gr + P + 2nd to 12th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10961.698
Approved no of units |  |  | Flats -128, Shops -23
Approved no of Floors |  |  | Wing A & B = B + Gr + P + 2nd to 12th Floor
Proposed no of Floors |  |  | Wing A & B = B + Gr + P + 2nd to 12th Floor
Expected Completion |  |  | As per RERA - 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative Entrance, etc
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A & B = B + Gr + P + 2nd to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 4 Floor Completed | , Finishing upto 4 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 91.67% |  | 95% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 33.33% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5700
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 255500
Club Charges |  |  |  |  | 200000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Charges |  |  |  |  | 150000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 4560
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop (Wing A & B) |  | 23 |  | 11038.116 |  | 24715
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 73 |  | 50049.7825 |  | 83497
Wing B |  | 55 |  | 35858.7913 |  | 58275
Total |  | 128 |  | 85908.5739 |  | 141772
Grand Total |  | 151 |  | 96946.6899 |  | 166487
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable Area | Floor
Wing A + B
Basement Floor for Parking
Ground Floor For Commercial
1 |  | Shop | 457.8252 | 0 | 1000 | Ground Floor For Commercial
2 |  | Shop | 496.0482 | 0 | 1085
3 |  | Shop | 443.4983 | 0 | 970
4 |  | Shop | 449.7737 | 0 | 980
5 |  | Shop | 602.1597 | 0 | 1315
6 |  | Shop | 482.6685 | 0 | 1075
7 |  | Shop | 460.0426 | 0 | 1025
8 |  | Shop | 401.8416 | 0 | 910
9 |  | Shop | 953.2706 | 0 | 2380
10 |  | Shop | 348.9474 | 0 | 780
11 |  | Shop | 409.1073 | 0 | 900
12 |  | Shop | 406.8039 | 0 | 900
13 |  | Shop | 414.2633 | 0 | 910
14 |  | Shop | 495.3378 | 0 | 1075
15 |  | Shop | 520.6977 | 0 | 1130
16 |  | Shop | 429.3867 | 0 | 1170
17 |  | Shop | 533.5177 | 0 | 1160
18 |  | Shop | 460.9683 | 0 | 1030
19 |  | Shop | 523.97 | 0 | 1080
20 |  | Shop | 359.41 | 0 | 800
21 |  | Shop | 325.7402 | 0 | 730
22 |  | Shop | 533.5069 | 0 | 1160
23 |  | Shop | 529.3305 | 0 | 1150
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable Area | Floor
Wing A
1st Floor For Parking
2nd Floor For Residential
203 |  | 2BHK | 633.2596 | 396.1905 | 1435 | 2nd Floor For Residential
204 |  | 2BHK | 635.3451 | 427.8367 | 1490
205 |  | 1BHK | 393.9624 | 356.2561 | 1000
206 |  | 3BHK | 837.4392 | 704.676 | 2095
207 |  | 2BHK | 594.7325 | 353.5328 | 1367
3rd to 6th Floor
301 to 601 |  | 2BHK | 698.6912 | 0 | 1110 | 3rd to 6th Floor
302 to 602 |  | 2BHK | 631.1525 | 0 | 1065
303 to 603 |  | 2BHK | 656.7924 | 0 | 1110
304 to 604 |  | 2BHK | 725.2783 | 0 | 1150
305 to 605 |  | 1BHK | 451.6036 | 0 | 720
306 to 606 |  | 3BHK | 952.9638 | 0 | 1515
307 to 607 |  | 2BHK | 673.6865 | 0 | 1085
7th Floor (Part Refuge Area)
701 |  | 2BHK | 698.6912 | 0 | 1110 | 7th Floor (Part Refuge Area)
702 |  | 2BHK | 631.1525 | 0 | 1065
703 |  | 2BHK | 656.7924 | 0 | 1110
704 |  | 2BHK | 725.2783 | 0 | 1150
705 |  | Refuge Area
706 |  | 3BHK | 904.2029 | 0 | 1515
707 |  | 2BHK | 700.731 | 0 | 1085
8th to 10th Floor
801 to 1001 |  | 2BHK | 698.6912 | 0 | 1110 | 8th to 10th Floor
802 to 1002 |  | 2BHK | 631.1525 | 0 | 1065
803 to 1003 |  | 2BHK | 656.7924 | 0 | 1110
804 to 1004 |  | 2BHK | 725.2783 | 0 | 1150
805 to 1005 |  | 1BHK | 451.6036 | 0 | 720
806 to 1006 |  | 3BHK | 952.9638 | 0 | 1515
807 to 1007 |  | 2BHK | 673.6865 | 0 | 1085
11th Floor (Part Refuge Area)
1101 |  | 2BHK | 698.6912 | 0 | 1110 | 11th Floor (Part Refuge Area)
1102 |  | 2BHK | 631.1525 |  | 1065
1103 |  | 2BHK | 656.7924 | 0 | 1110
1104 |  | 2BHK | 725.2783 | 0 | 1150
1105 |  | Refuge Area
1106 |  | 3BHK | 904.2029 | 0 | 1515
1107 |  | 2BHK | 700.731 | 0 | 1085
12th Floor
1201 |  | 2BHK | 698.6912 | 0 | 1110 | 12th Floor
1202 |  | 2BHK | 631.1525 | 0 | 1065
1203 |  | 2BHK | 656.7924 | 0 | 1110
1204 |  | 2BHK | 725.2783 | 0 | 1150
1205 |  | 1BHK | 451.6036 | 0 | 720
1206 |  | 3BHK | 952.9638 | 0 | 1515
1207 |  | 2BHK | 673.6865 | 0 | 1085
Wing B
1st Floor For Parking
2nd Floor For Residential
203 |  | 2 | 630.3291 | 372.9941 | 1430 | 2nd Floor For Residential
204 |  | 2 | 635.3882 | 366.0191 | 1430
205 |  | 3 | 813.9199 | 430.6784 | 1815
3rd to 6th Floor
301 to 601 |  | 1BHK | 463.0673 | 0 | 730 | 3rd to 6th Floor
302 to 602 |  | 1BHK | 456.4151 | 0 | 720
303 to 603 |  | 2BHK | 720.5852 | 0 | 1145
304 to 604 |  | 2BHK | 725.2783 | 0 | 1150
305 to 605 |  | 3BHK | 929.1216 | 0 | 1475
306 to 606 |  | 1BHK | 452.2118 | 0 | 715
7th Floor (Part Refuge Area & Natural Terrace)
701 |  | 1BHK | 463.0673 | 0 | 730 | 7th Floor (Part Refuge Area & Natural Terrace)
702 |  | Natural Terrace
703 |  | 2BHK | 695.9626 | 0 | 1145
704 |  | 2BHK | 725.2783 | 0 | 1150
705 |  | 3BHK | 931.382 | 0 | 1475
706 |  | Refuge Area
8th to 10th Floor
801 to 1001 |  | 1BHK | 463.0673 | 0 | 730 | 8th to 10th Floor
802 to 1002 |  | Natural Terrace on 7th Floor
803 to 1003 |  | 2BHK | 720.5852 | 0 | 1145
804 to 1004 |  | 2BHK | 725.2783 | 0 | 1150
805 to 1005 |  | 3BHK | 929.1216 | 0 | 1475
806 to 1006 |  | 1BHK | 452.2118 | 0 | 715
11th Floor (Part Refuge Area)
1101 |  | 1BHK | 463.0673 | 0 | 730 | 11th Floor (Part Refuge Area)
1102 |  | Natural Terrace on 7th Floor
1103 |  | 2BHK | 695.9626 | 0 | 1145
1104 |  | 2BHK | 725.2783 | 0 | 1150
1105 |  | 3BHK | 931.382 | 0 | 1475
1106 |  | Refuge Area |  | 0
12th Floor
1201 |  | 1BHK | 463.0673 | 0 | 730 | 12th Floor
1202 |  | Natural Terrace on 7th Floor
1203 |  | 2BHK | 720.5852 | 0 | 1145
1204 |  | 2BHK | 725.2783 | 0 | 1150
1205 |  | 3BHK | 929.1216 | 0 | 1475
1206 |  | 1BHK | 452.2118 | 0 | 715
Remarks:
* | Finishing work is pending.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Akshay Barkade (9112875592).
* | We have updated CC & Approved Floor plans for wing A & B (on 06/01/2023) | [6 empty] | as per approved plan Dtd 18/11/2022 B wing only part I is approved and as per as per site visit 07/10/2024 and site engineer B wing part II work is started
Undertaking : | [7 empty] | as per site visit 07/10/2024 and site engineer B wing part II work is started
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Delta Greens
Google Map :
Formulas:
Dapoli = [Dapoli, row above]
A
A Wing
B Wing Part I

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted