## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder |  |  |  | Mr.Sunil Chamanlal Gupta
Name of the builder company |  |  |  | Kartikya Builders
Name of the Project |  |  |  | Kartikya Vatika
Provided Contact Details (Name & Contact No.) |  |  |  | 9324435637
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA |  |  |  | Mr.Prafull : 9769911869
Name / No of the Building |  |  |  | Building No.1,2 & 3
Name / No of the Existing Building |  |  |  | NA | [11 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet | [11 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000049066 |  |  |  | #N/A | [7 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Kartikya Vatika, Survey No.3/1/A, near Shri Ram Mandir, Vajepur Road, Cheravali, Cheravali, Panvel East, Panvel, Raigad - 410206. | [13 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 3/1/A | [13 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Cheravali | [13 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Vajepur Road |  | Locality/Village |  | Cheravali | [9 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Panvel East |  | District |  | Raigad | [9 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410206 | [12 empty] | Mahad | Daund
Nearby Landmark |  | Shri Ram Mandir |  | Distance from city centre: |  | 10.6 KM from Panvel Railway Station | [12 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [14 empty] | Mangaon | Ambegaon
[19 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [14 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [14 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [14 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | House
North | NA | Residential Existing Structure/Vajepur Road |  |  | Open Plot/Vajepur Road
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.009611,73.201944
Location Link |  | https://maps.app.goo.gl/fyRbzM6zEP5ZeD6o7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5538.299
Permissible Sale FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | -0.0026667
Total FSI availaible for the project |  |  |  | 0.99733
Total Approved Sale Builtup area of the project (Sq.Mt) |  |  |  | 5523.53 |  |  |  | 6629.58 | 6607.02
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Airport Influence Notified Area (NAINA)
Layout Approval No |  | CIDCO/NAINA/Panvel/Cheravali/BP-00552/CC/2022/0220 |  |  | Dated | 2022-07-14
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Cheravali/BP-00552/CC/2022/0220 |  |  | Dated | 2022-07-14
Commencement-CC No Valid Up to: |  | CIDCO/NAINA/Panvel/Cheravali/BP-00552/CC/2022/0220 |  |  | Dated | 2022-07-14
Total Net Builtup Area = 6629.58 Sq.M Residential - Sale Component-159 Nos, EWS Component - 20Nos Convenient Shop - 02Nos
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved Sale Builtup area of building (Sq.Mt) |  |  | 5523.53
Approved no of units |  |  | Flats - 159, Shops - 2
Approved no of Floors |  |  | Building No.1 (Wing A, B & C) = Gr + 1st to 4th Floor Building No.2 (Wing A & B) = Gr + 1st to 4th Floor Building No.3 (Wing A & B) = Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Building No.1 (Wing A, B & C) = Gr + 1st to 4th Floor
Building No.2 (Wing A & B) = Gr + 1st to 4th Floor
Building No.3 (Wing A & B) = Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gym, Club House, Indoor Game, Multipurpose Hall, CCTV, Cover Car Parking, 24/7 Hour Security, Inverter Backup, Lift, Kids Play Area, Sit-Out Area, Meditation etc. |  |  |  |  | https://housing.com/in/buy/projects/page/293240-kartikya-vatika-by-kartikya-builders-in-panvel/brochure
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (Wing A, B & C) = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 10% |  | 45% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.2 (Wing A) = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 2.5 Floor Completed | , External Plaster upto 2.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 2.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 71.25% |  | 88.12% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2.5 | 62.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.2 (Wing B) = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 2.5 Floor Completed | , External Plaster upto 2.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 2.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 71.25% |  | 88.12% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2.5 | 62.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.3 (Wing A) = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 2 Floor Completed | , External Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 62.5% |  | 82.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.3 (Wing B) = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 2 Floor Completed | , Internal Plaster upto 3 Floor, External Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 68.12% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3800 |  |  | 3600 to 3900
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 100000
Club Charges |  |  |  |  | 50000
Grill Charges
Gas Connection Charges
Water, MSEB, Grill Charges |  |  |  |  | 70000
Society Formation Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 3040
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.3 | Wing B | 2 |  | 194.8284 |  | 301.984
Total |  | 2 |  | 194.8284 |  | 301.984
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 | Wing A | 16 |  | 5755.5108 |  | 8771.2338
| Wing B | 24 |  | 8757.5904 |  | 13042.9541
| Wing C | 16 |  | 5852.6021 |  | 8906.4996 |  | 159
Building No.2 | Wing A | 36 |  | 13215.0489 |  | 20004.4268
| Wing B | 16 |  | 5817.7267 |  | 8855.9303
Building No.3 | Wing A | 17 |  | 6140.3238 |  | 9326.2794
| Wing B | 34 |  | 12567.6158 |  | 18926.3627
Total |  | 159 |  | 58106.4186 |  | 87833.6867
Grand Total |  | 161 |  | 58301.247 |  | 88135.6708
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building No.3 | [7 empty] | 10.764
Wing B
Ground Floor For Commercial, Entrance Lobby, Parking & Part Residential Area
1 |  | Shop | 97.4142 | 0 | 150.992 | Ground Floor For Commercial, Entrance Lobby, Parking & Part Residential Area |  | 9.5 | 1.6938
2 |  | Shop | 97.4142 | 0 | 150.992 |  |  |  | 1.6938
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Building No.1
A Wing
Ground Floor For Driver Room, Entrance Lobby, Society Office & Parking | [7 empty] | https://kartikyavatika.com/
1st Floor For Residential | [12 empty] | Loading
1 |  | 1BHK | 361.5628 | 0 | 524.266 | Ground Floor For Driver Room, Entrance Lobby, Society Office & Parking |  | 29.918 | 25.9657 | 5.29 | 2.8875 | 638 | 1.7646 |  | 1.7646
2 |  | 1BHK | 356.9342 | 37.4587 | 555.0134 |  |  | 3.4748 | 28.7157 | 2.39 | 3.4748 | 646 | 1.7049 | 36.64
3 |  | 1BHK | 357.6877 | 37.4587 | 556.1059 |  |  |  | 30.9558 |  |  | 646 | 1.7013
4 |  | 1BHK | 362.6392 | 40.2843 | 566.1111 |  |  | 3.7425 | 30.9558 |  | 649 | 649 | 1.6786
2nd & 4th Floor | [12 empty] | #DIV/0!
1 |  | 1BHK | 362.101 | 34.7677 | 559.8141 | 2nd & 4th Floor |  | 25.9657 |  | 3.2287 |  | 646 | 1.688
2 |  | 1BHK | 356.396 | 0 | 516.7743 |  |  |  |  | 2.8875 |  | 638 | 1.7901
3 |  | 1BHK | 357.2572 | 32.1844 | 550.2072 | [6 empty] | 638 | 1.6957
4 |  | 1BHK | 363.1774 | 34.7677 | 561.3749 | [6 empty] | 645 | 1.6803
3rd Floor
1 |  | 1BHK | 361.5628 | 0 | 524.266 | 3rd Floor
2 |  | 1BHK | 356.9342 | 37.4587 | 555.0134
3 |  | 1BHK | 357.6877 | 37.4587 | 556.1059 |  |  | 3.4748
4 |  | 1BHK | 362.6392 | 32.1844 | 558.0111 |  |  | 2.9925
B Wing
Ground Floor For Entrance Lobby & Parking
1st Floor For Residential
1 |  | 1BHK | 351.337 | 0 | 509.4386 | 1st Floor For Residential |  | 25.8193 | 5.025
2 |  | 1BHK | 390.5179 | 0 | 566.251 |  |  |  | 8.502
3 |  | 1BHK | 363.5003 | 0 | 527.0754 |  |  |  |  | 2.9137
4 |  | 1BHK | 368.3441 | 37.7816 | 571.8806 |  |  |  |  | 3.5055
5 |  | 1BHK | 351.6599 | 37.4587 | 547.3655 |  |  |  |  | 3.4748
6 |  | 1BHK | 361.5628 | 0 | 524.266 |  |  |  |  | 2.8875
2nd & 4th Floor | [10 empty] | 4000
1 |  | 1BHK | 356.1808 | 27.9864 | 544.4485 | 2nd & 4th Floor |  |  |  |  | 2177794.008 | 2447794.008
2 |  | 1BHK | 390.5179 | 0 | 566.251 | [5 empty] | 2265003.936 | 2535003.936
3 |  | 1BHK | 364.0385 | 33.5837 | 561.4395 | [5 empty] | 2245757.904 | 2515757.904
4 |  | 1BHK | 367.8059 | 0 | 533.3185 | [5 empty] | 2133274.104 | 2403274.104
5 |  | 1BHK | 351.2293 | 0 | 509.2825 | [5 empty] | 2037130.056 | 2307130.056
6 |  | 1BHK | 362.101 | 35.4136 | 560.46 | [5 empty] | 2241839.808 | 2511839.808
3rd Floor | [10 empty] | 0 | 270000
1 |  | 1BHK | 351.337 | 0 | 509.4386 | 3rd Floor |  |  |  |  | 2037754.368 | 2307754.368
2 |  | 1BHK | 390.5179 | 0 | 566.251 | [5 empty] | 2265003.936 | 2535003.936
3 |  | 1BHK | 363.5003 | 0 | 527.0754 | [5 empty] | 2108301.624 | 2378301.624
4 |  | 1BHK | 368.3441 | 37.7816 | 571.8806 | [5 empty] | 2287522.224 | 2557522.224
5 |  | 1BHK | 351.6599 | 37.4587 | 547.3655 | [5 empty] | 2189462.184 | 2459462.184
6 |  | 1BHK | 361.5628 | 0 | 524.266 | [5 empty] | 2097064.008 | 2367064.008
C Wing
Ground Floor For Entrance Lobby & Parking
1st Floor For Residential
1 |  | 1BHK | 363.7156 | 32.1844 | 559.5719 | 1st Floor For Residential |  | 29.917
2 |  | 1BHK | 368.667 | 37.7816 | 572.3488
3 |  | 1BHK | 367.8059 | 37.7816 | 571.1002
4 |  | 1BHK | 362.9621 | 0 | 526.295
2nd & 4th Floor
1 |  | 1BHK | 364.2538 | 35.0906 | 563.2586 | 2nd & 4th Floor
2 |  | 1BHK | 368.1288 | 32.1844 | 565.9711
3 |  | 1BHK | 367.2677 | 0 | 532.5381
4 |  | 1BHK | 363.5003 | 35.0906 | 562.166
3rd Floor
1 |  | 1BHK | 363.7156 | 32.1844 | 559.5719 | 3rd Floor
2 |  | 1BHK | 368.667 | 37.7816 | 572.3488
3 |  | 1BHK | 367.8059 | 37.7816 | 571.1002
4 |  | 1BHK | 362.9621 | 0 | 526.295
Building No.2
A Wing
Ground Floor For Entrance Lobby, Organic Waste Converter, Meter Room & Parking
1st Floor For Residential
1 |  | 1BHK | 402.7889 | 38.7504 | 622.7943 | 1st Floor For Residential |  | 28.5662 | 6.1595 | 3.5977 |  | 1.7677
2 |  | 1BHK | 370.4969 | 36.7052 | 573.9257 | [6 empty] | 1.7841
3 |  | 1BHK | 402.7566 | 0 | 583.9971 | [6 empty] | 1.6188
4 |  | 1BHK | 367.16 | 32.1844 | 564.5664 | [6 empty] | 1.7567
5 |  | 1BHK | 359.3023 | 37.4587 | 558.4471 | [6 empty] | 1.7256
6 |  | 1BHK | 316.7845 | 59.3096 | 518.6472 |  |  |  | 5.514
7 |  | 1BHK | 364.0385 | 37.7816 | 565.6374
8 |  | 1BHK | 363.5003 | 0 | 527.0754
9 |  | 1BHK | 370.174 | 30.6774 | 567.4296
2nd & 4th Floor
1 |  | 1BHK | 395.8999 | 0 | 574.0549 | 2nd & 4th Floor |  | 28.5662 | 6.1595 | 3.5977
2 |  | 1BHK | 363.9308 | 0 | 527.6997
3 |  | 1BHK | 402.8642 | 0 | 584.1531
4 |  | 1BHK | 367.6982 | 35.7365 | 568.8989
5 |  | 1BHK | 358.8718 | 32.1844 | 552.5484
6 |  | 1BHK | 307.0969 | 0 | 445.2905
7 |  | 1BHK | 363.5003 | 0 | 527.0754
8 |  | 1BHK | 364.0385 | 35.7365 | 563.5923
9 |  | 1BHK | 366.6218 | 44.7782 | 576.3799
3rd Floor
1 |  | 1BHK | 402.7889 | 38.7504 | 622.7943 | 3rd Floor |  | 28.5662 | 6.1595 | 3.5977
2 |  | 1BHK | 370.4969 | 36.7052 | 573.9257
3 |  | 1BHK | 402.7566 | 0 | 583.9971
4 |  | 1BHK | 367.16 | 32.1844 | 564.5664
5 |  | 1BHK | 359.3023 | 37.4587 | 558.4471
6 |  | 1BHK | 316.7845 | 59.3096 | 518.6472
7 |  | 1BHK | 364.0385 | 37.7816 | 565.6374
8 |  | 1BHK | 363.5003 | 0 | 527.0754
9 |  | 1BHK | 370.174 | 30.6774 | 567.4296
B Wing
Ground Floor For Entrance Lobby & Parking
1st Floor For Residential
1 |  | 1BHK | 362.9621 | 0 | 526.295 | Ground Floor For Entrance Lobby & Parking |  | 28.5662 | 6.1595 | 3.5977
2 |  | 1BHK | 363.5003 | 37.7816 | 564.857
3 |  | 1BHK | 364.2538 | 37.7816 | 565.9496
4 |  | 1BHK | 363.7156 | 32.1844 | 559.5719
2nd & 4th Floor
1 |  | 1BHK | 363.5003 | 35.0906 | 562.166 | 2nd & 4th Floor
2 |  | 1BHK | 362.9621 | 0 | 526.295
3 |  | 1BHK | 363.7156 | 32.1844 | 559.5719
4 |  | 1BHK | 364.2538 | 35.0906 | 563.2586
3rd Floor
1 |  | 1BHK | 362.9621 | 0 | 526.295 | 3rd Floor
2 |  | 1BHK | 363.5003 | 37.7816 | 564.857
3 |  | 1BHK | 364.2538 | 37.7816 | 565.9496
4 |  | 1BHK | 363.7156 | 32.1844 | 559.5719
Building No.3
A Wing
Ground Floor For Residential, Entrance Lobby, Meter Room & Parking
1 |  | 1BHK | 357.4724 | 0 | 518.335 | Ground Floor For Residential, Entrance Lobby, Meter Room & Parking |  | 26.0645
1st Floor For Residential
1 |  | 1BHK | 363.5003 | 0 | 527.0754 | 1st Floor For Residential
2 |  | 1BHK | 358.5488 | 37.7816 | 557.6775
3 |  | 1BHK | 359.41 | 37.7816 | 558.9261
4 |  | 1BHK | 364.2538 | 32.1844 | 560.3523
2nd & 4th Floor
1 |  | 1BHK | 364.0385 | 35.7365 | 563.5923 | 2nd & 4th Floor
2 |  | 1BHK | 358.0106 | 0 | 519.1154
3 |  | 1BHK | 358.8718 | 32.1844 | 552.5484
4 |  | 1BHK | 364.792 | 35.7365 | 564.6848
3th Floor
1 |  | 1BHK | 363.5003 | 0 | 527.0754 | 3th Floor
2 |  | 1BHK | 358.5488 | 37.7816 | 557.6775
3 |  | 1BHK | 359.41 | 37.7816 | 558.9261
4 |  | 1BHK | 364.2538 | 32.1844 | 560.3523
B Wing
Ground Floor For Residential, Entrance Lobby, Parking & Part Commercial Area
1 |  | 1BHK | 357.3648 | 0 | 518.179 | Ground Floor For Residential, Entrance Lobby, Parking & Part Commercial Area
2 |  | 1BHK | 354.1356 | 0 | 513.4966
1st Floor For Residential
1 |  | 1BHK | 364.0385 | 37.7816 | 565.6374 | 1st Floor For Residential
2 |  | 1BHK | 363.5003 | 0 | 527.0754
3 |  | 1BHK | 387.7193 | 34.0142 | 596.2072 |  |  | 3.1648
4 |  | 1BHK | 376.74 | 35.7365 | 582.0095
5 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
6 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
7 |  | 1BHK | 371.2504 | 36.7052 | 575.0183 |  |  | 2.9925
8 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
2nd & 4th Floor
1 |  | 1BHK | 363.5003 | 0 | 527.0754 | 2nd & 4th Floor
2 |  | 1BHK | 363.5003 | 32.9378 | 560.0132
3 |  | 1BHK | 383.0908 | 0 | 555.4816
4 |  | 1BHK | 370.174 | 0 | 536.7522
5 |  | 1BHK | 364.6843 | 0 | 528.7923
6 |  | 1BHK | 370.7122 | 32.1844 | 569.717
7 |  | 1BHK | 370.7122 | 32.1844 | 569.717
8 |  | 1BHK | 364.6843 | 0 | 528.7923
3th Floor
1 |  | 1BHK | 364.0385 | 37.7816 | 565.6374 | 3th Floor
2 |  | 1BHK | 363.5003 | 0 | 527.0754
3 |  | 1BHK | 387.7193 | 34.0142 | 596.2072
4 |  | 1BHK | 376.74 | 35.7365 | 582.0095
5 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
6 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
7 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
8 |  | 1BHK | 371.2504 | 36.7052 | 575.0183
Remarks:
1 | Construction work is in process at the time of Visit (Labour found).
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Cantilever Enclosed Balcony + Proj. Balcony.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | We have not considered the terrace area, which is near the W.C. and Bath, near Duct (in the internal Chowk).
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
11 | The water body is on the north side of the project.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra Vishwakarma |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kartikya Vatika
Remark No. 10
Layout :
Google Map :
Formulas:
Cheravali = [Cheravali, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building
Building No.2 (Wing A)
Building No.3 (Wing B)
Building No.3 (Wing A)
Terrace Area Provided Near duct
Water Body
1A
3A
3B
1A
1B
1C
2A
2B
3A
3B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC