## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | M/s. T. L. Realities
Name of the builder company |  |  |  | M/s. T. L. Realities
Name of the Project |  |  |  | Ideal Enclave
Contact Details ( Name & Contact No.) |  |  |  | 9892713565
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Akash 9029664475
Name / No of the Building |  |  |  | Building No.1 Type A1 = A Wing Type A2 = B Wing Type A3 = C Wing
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P99000027773
Project location details |  | Ideal Enclave, Gut No.232/A/2, near Soham Garden Buildings, Padghe Road, Umroli, Palghar, Palghar, Palghar.
Gut No |  | 232/A/2
Road |  | Padghe Road |  | Locality/Village |  | Umroli
City |  | Palghar |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Nearby Landmark |  | Soham Garden Buildings |  | Distance from city centre: |  | 0.85 Km from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Umroli Railway Station
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.7565 |  | Longitude |  | 72.7647
Location Link |  | https://maps.app.goo.gl/TDG95yoGFPU9fokn6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2500
Permissible FSI |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 0.9
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2250
Total number of Buildings |  |  |  | 3 Wings
Approval Detail : Plan approval
Layout Approval No |  | MAHSUL/KAKSH.1/MEJ1/NAP/SR/189/18 |  |  | Dated | 2019-06-07
Approved Floor plan No. |  | MAHSUL/KAKSH.1/MEJ1/NAP/SR/189/18 |  |  | Dated | 2019-06-07
Commencement Certificate No. |  | MAHSUL/KAKSH.1/T.1/NAP/SR - 189/2018 |  |  | Dated | 2019-06-07
Valid Up to: Building 1 (Type A1) = Gr + 1st to 2nd Floor Building 1 (Type A2 & A3) = Gr + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2250
Approved no of units |  |  | Flats - 53, Shops - 15
Approved no of Floors |  |  | Building No.1 (Type A1 - A Wing) = Gr + 1st to 2nd Floor Building No.1 (Type A2 - B Wing & A3 - C Wing) = Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Building No.1 (Type A1 - A Wing) = Gr + 1st to 2nd Floor
Building No.1 (Type A2 - B Wing & A3 - C Wing) = Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.1 (Type A1 - A Wing) = Gr + 1st to 2nd Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 2 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.5
Excavation |  | 2 | 100% | 57.5% |  | 80% |  | Excavation in process |  | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed |  | 2
RCC (Including podiums) |  | 3 | 100% |  |  |  |  | Footing in Process |  | 0.5
Brickwork | Brickwork & Internal Plaster | 2 | 100% |  |  |  |  | Footing Completed |  | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 2
Construction details: |  | Building No.1 (Type A2 - B Wing) = Gr + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 4 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.75 Floor, External Plaster upto 1.5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.75 Floor, External Plaster upto 1.5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Part I (Flat No.3,4,5,6) | Part II (Flat No.1 & 2) | Slab/Floor Average of Part I & II | Complition % | Progress % | Disbursement % | Piling Work in process | 1
Excavation |  | 4 | 4 | 4 | 100% | 52.78% | 75.56% | Excavation in process | 2
Plinth |  | 4 | 4 | 4 | 100% |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 3 | 4 | 80% |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 0 | 2 | 50% |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3.5 | 0 | 1.75 | 43.75% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 0 | 1.5 | 37.5% |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0 | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0 | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0 | 0 | 0% |  |  | Plinth in process | 3
Possession |  | 0 | 0 | 0 | 0% |  |  | Plinth completed | 4
Construction details: |  | Building No.1 (Type A3 - C Wing) = Gr + 1st to 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 75% |  | 90% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 2 | 50% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3000
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5500
Legal Charges |  |  |  |  | 10,000/-
Other Charges |  |  |  |  | 1,00,000/-
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 2400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A1 |  | 8 |  | 1092.3307 |  | 1693.1126
Type A2 |  | 7 |  | 911.7108 |  | 1413.1517
Total |  | 15 |  | 2004.0415 |  | 3106.2644
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A1 |  | 8 |  | 3091.6361 |  | 4637.4541
Type A2 |  | 26 |  | 9138.0978 |  | 13707.1467
Type A3 |  | 19 |  | 6104.8026 |  | 9157.2039
Total |  | 53 |  | 18334.5365 |  | 27501.8047
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Building No.1
Type A1 - A Wing
Ground Floor for Commercial & Parking
1 |  | Shop | 117.1123 | 0 | 181.5241 | Ground Floor for Commercial & Parking
2 |  | Shop | 156.9391 | 0 | 243.2556 | Ground Floor for Commercial & Parking
3 |  | Shop | 131.3208 | 0 | 203.5472 | Ground Floor for Commercial & Parking
4 |  | Shop | 180.6199 | 0 | 279.9609 | Ground Floor for Commercial & Parking
5 |  | Shop | 76.855 | 0 | 119.1252 | Ground Floor for Commercial & Parking
6 |  | Shop | 165.7656 | 0 | 256.9367 | Ground Floor for Commercial & Parking
7 |  | Shop | 114.206 | 0 | 177.0194 | Ground Floor for Commercial & Parking
8 |  | Shop | 149.512 | 0 | 231.7435 | Ground Floor for Commercial & Parking
Type A2 - B Wing
Ground Floor for Commercial & Parking
1 |  | Shop | 145.0987 | 0 | 224.903 | Ground Floor for Commercial & Parking
2 |  | Shop | 110.7616 | 0 | 171.6804 | Ground Floor for Commercial & Parking
3 |  | Shop | 161.3524 | 0 | 250.0962 | Ground Floor for Commercial & Parking
4 |  | Shop | 155.8627 | 0 | 241.5872 | Ground Floor for Commercial & Parking
5 |  | Shop | 113.6678 | 0 | 176.1852 | Ground Floor for Commercial & Parking
6 |  | Shop | 152.4182 | 0 | 236.2483 | Ground Floor for Commercial & Parking
7 |  | Shop | 72.5494 | 0 | 112.4515 | Ground Floor for Commercial & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.1
Type A1 - A Wing
1st & 2nd Floor for Residential
101 & 201 |  | 1BHK | 324.9652 | 0 | 487.4477 | 1st & 2nd Floor for Residential |  |  |  |  | 101 & 201 | 101 | 201
102 & 202 |  | 2BHK | 500.7413 | 0 | 751.1119 | 1st & 2nd Floor for Residential |  |  |  |  | 102 & 202 | 102 | 202
103 & 203 |  | 1.5BHK | 396.4381 | 0 | 594.6572 | 1st & 2nd Floor for Residential |  |  |  |  | 103 & 203 | 103 | 203
104 & 204 |  | 1BHK | 323.6735 | 0 | 485.5102 | 1st & 2nd Floor for Residential |  |  |  |  | 104 & 204 | 104 | 204
Type A2 - B Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 318.1838 | 0 | 477.2758 | Ground Floor for Residential & Parking
2 |  | 1BHK | 324.9652 | 0 | 487.4477 | Ground Floor for Residential & Parking
1st to 4th Floor
101 to 401 |  | 1BHK | 323.6735 | 0 | 485.5102 | 1st to 4th Floor |  |  |  |  | 101 to 401 | 101 | 401
102 to 402 |  | 1BHK | 323.6735 | 0 | 485.5102 | 1st to 4th Floor |  |  |  |  | 102 to 402 | 102 | 402
103 to 403 |  | 2BHK | 508.2761 | 0 | 762.4141 | 1st to 4th Floor |  |  |  |  | 103 to 403 | 103 | 403
104 to 404 |  | 1BHK | 318.1838 | 0 | 477.2758 | 1st to 4th Floor |  |  |  |  | 104 to 404 | 104 | 404
105 to 405 |  | 1BHK | 324.9652 | 0 | 487.4477 | 1st to 4th Floor |  |  |  |  | 105 to 405 | 105 | 405
106 to 406 |  | 1BHK | 324.9652 | 0 | 487.4477 | 1st to 4th Floor |  |  |  |  | 106 to 406 | 106 | 406
Type A3 - C Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 324.9652 | 0 | 487.4477 | Ground Floor for Residential & Parking
2 |  | 1BHK | 311.4025 | 0 | 467.1038 | Ground Floor for Residential & Parking
3 |  | 1BHK | 324.9652 | 0 | 487.4477 | Ground Floor for Residential & Parking
1st to 4th Floor for Residential
101 to 401 |  | 1BHK | 324.5346 | 0 | 486.8019 | 1st to 4th Floor for Residential |  |  |  |  | 101 to 401 | 101 | 401
102 to 402 |  | 1BHK | 311.4025 | 0 | 467.1038 | 1st to 4th Floor for Residential |  |  |  |  | 102 to 402 | 102 | 402
103 to 403 |  | 1BHK | 324.9652 | 0 | 487.4477 | 1st to 4th Floor for Residential |  |  |  |  | 103 to 403 | 103 | 403
104 to 404 |  | 1BHK | 324.9652 | 0 | 487.4477 | 1st to 4th Floor for Residential |  |  |  |  | 104 to 404 | 104 | 404
Remarks:
1 | Wing A & B = Construction work was stopped. Construction work is same as last visit dtd.07/10/2024 Wing C = Construction work was stopped. Work is same as last visit dtd.05/04/2025. | [6 empty] | Building No.1 (C Wing) = Construction work is in process at the time of visit (Slow Speed). Building No.1 (A, B Wing) = Construction work is the same as last visit, but work is in process at the time of the visit. (Slow Speed)
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony.
5 | We have considered rate by verifying it from market inquire.
6 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Ms. Padnya Gawand(Sales)(8788228660).
8 | The project has received first CC on 07/06/2019, But construction work is not yet Completed.
9 | As per RERA, completion period of project Ideal Enclave is expired on 31/09/2024 but still project work is pending.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gaurav Naik |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ideal Enclave
Google Map :
Formulas:
Umroli = [Umroli, row above]
Part I
Part II
A Wing
B Wing
C Wing
Part I
Part I
Part II

## AXIS
Actual Stage Provided by AXIS Bank
Stage calculator as per Revised Valuation Manual
| Completed | Net completed | Recommended | Net recommended | No of floors in building | No of constructed floors | Completed (%) | Recommended (%)
Excavation | 0 | 0 | 20 | 20 | 20 | 20 | 0 | 20
Plinth | 10 | 10 | 45 | 25 | 20 | 20 | 10 | 25
RCC (Including podiums) | 50 | 40 | 75 | 30 | 25 | 25 | 40 | 30
Brickwork & Internal Plaster | 65 | 15 | 85 | 10 | 20 | 20 | 15 | 10
Flooring & Fitting | 75 | 10 | 90 | 5 | 20 | 20 | 10 | 5
External Plaster & Plumbing | 85 | 10 | 95 | 5 | 20 | 20 | 10 | 5
Building Common Amenities & Painting | 95 | 10 | 95 | 0 | 20 | 0 | 0 | 0
Possession | 100 | 5 | 100 | 5 | 20 | 0 | 0 | 0
|  | 100 |  | 100 |  | Final Stage (%) | 85 | 95
Split % by Asmita ---OK By Ajinkya
Stage calculator as per Revised Valuation Manual
| Completed | Net completed | Recommended | Net recommended | No of floors in building | No of constructed floors | Completed (%) | Recommended (%)
Excavation | 0 | 0 | 20 | 20 | 30 | 30 | 0 | 20
Plinth | 10 | 10 | 45 | 25 | 30 | 30 | 10 | 25
RCC (Including podiums) | 50 | 40 | 75 | 30 | 35 | 35 | 40 | 30
Brickwork | 57.5 | 7.5 | 80 | 5 | 30 | 30 | 7.5 | 5
Internal Plaster | 65 | 7.5 | 85 | 5 | 30 | 30 | 7.5 | 5
External Plaster & Plumbing | 75 | 10 | 90 | 5 | 30 | 30 | 10 | 5
Flooring & Fitting | 85 | 10 | 95 | 5 | 30 | 30 | 10 | 5
Painting & Wooden | 90 | 5 | 95 | 0 | 30 | 30 | 5 | 0
Building Common Amenities | 95 | 5 | 95 | 0 | 30 | 30 | 5 | 0
Possession | 100 | 5 | 100 | 5 | 30 | 30 | 5 | 5
|  | 100 |  | 100 |  | Final Stage (%) | 100 | 100
ASMITA recommendation
Stage calculator as per Revised Valuation Manual
| Completed | Net completed | Recommended | Net recommended | No of floors in building | No of constructed floors | Completed (%) | Recommended (%)
Excavation | 0 | 0 | 20 | 20 | 30 | 30 | 0 | 20
Plinth | 10 | 10 | 45 | 25 | 30 | 30 | 10 | 25
RCC (Including podiums) | 50 | 40 | 75 | 30 | 35 | 35 | 40 | 30
Brickwork | 57.5 | 10 | 82.5 | 7.5 | 30 | 30 | 7.5 | 7.5
External Plaster & Plumbing | 62.5 | 5 | 85 | 2.5 | 30 | 30 | 5 | 2.5
Internal Plaster | 67.5 | 5 | 87.5 | 2.5 | 30 | 30 | 5 | 2.5
Flooring & Fitting | 77.5 | 10 | 90 | 2.5 | 30 | 30 | 10 | 2.5
Painting & Wooden | 87.5 | 10 | 95 | 5 | 30 | 30 | 10 | 5
Building Common Amenities | 92.5 | 5 | 97.5 | 2.5 | 30 | 30 | 5 | 2.5
Possession | 100 | 5 | 100 | 2.5 | 30 | 30 | 5 | 2.5
|  | 100 |  | 100 |  | Final Stage (%) | 97.5 | 100
Note on F4: No of habitable floors
Note on F6: No of RCC slabs including podiums
Note on G6: No of constructed RCC slabs including podium
Note on F17: No of habitable floors
Note on F19: No of RCC slabs including podiums
Note on G19: No of constructed RCC slabs including podium
Note on F34: No of habitable floors
Note on F36: No of RCC slabs including podiums
Note on G36: No of constructed RCC slabs including podium

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted