## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | Shree Sha Developers
Name of the builder company |  |  |  | Shree Sha Developers
Name of the Project |  |  |  | Nirman Signature
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Aman - 8080605404
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Wing R1 = Nirman Signature Wing R2 = Rain Basera |  |  |  | as per Rera
Name / No of the Existing Building |  |  |  | NA | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area & Cost Sheet. | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700050640 |  |  |  | #N/A |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Nirman Signature, Survey No.180, Hissa No. 3/2, near Sai Aangan, Internal Road, Chintamani Chowk, Badlapurgaon, Badlapur (West), Ambernath, Thane - 421503. | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 180, Hissa No. 3/2 | [9 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Chintamani Chowk | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Badlapurgaon | [5 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Badlapur (West) |  | District |  | Thane | [5 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Ambernath |  | Pin Code |  | 421503 | [8 empty] | Mahad | Daund
Nearby Landmark |  | Sai Aangan |  | Distance from city centre: |  | 3.20KM from Badlapur Railway Station | [8 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [10 empty] | Mangaon | Ambegaon
[15 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [10 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [10 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [10 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Survey No. 172 |  |  | Sanveg Residency
West | NA | Survey No. 181 |  |  | Sai Angan
North | NA | Survey No. 180 |  |  | Sanveg Residency
South | NA | 18.00 M. Wide Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.159705,73.263909
Location Link |  | https://maps.app.goo.gl/Y9RaUQqywenehCRF8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1140
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.8722
Total FSI availaible for the project |  |  |  | 2.9722
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3388.3
Total number of Buildings |  |  |  | 02 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgaon Badlapur Nagarparishad
Layout Approval No |  | KBNP/NRV/BD/6038-71 |  |  | Dated | 2022-06-30
Approved Floor plan No. |  | KBNP/NRV/BD/6038-71 |  |  | Dated | 2022-06-30
Commencement-CC No |  | K.B.N.P./NRV/B.P./6038/2022-2023 Unique No. 71 |  |  | Dated | 2022-06-30
Valid Up to: |  | Wing R1(Nirman Signature) = Gr/Stilt + 1st to 10th Floor Wing R2 (Rain Basera) = Gr + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3388.3
Approved no of units |  |  | Flats - 53, Shops - 12, Offices - 08
Approved no of Floors |  |  | Wing R1(Nirman Signature) = G + 1st to 10th Floor Wing R2 (Rain Basera) = G + 1st to 4th Floor
Proposed no of Floors |  |  | Wing R1 (Nirman Signature) = G + 1st to 10th Floor
Wing R2 (Rain Basera) = G + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/03/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Fitness Centre, Granite Kitchen Platform, Decorative Entrance & Landscape Garden, etc. |  |  |  |  | basic + plan
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing R1 (Nirman Signature) = G + 1st to 10th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 8 Floor, Painting upto 7 Floor, Finishing upto 2 Floor Completed | , Flooring upto 8 Floor, Painting upto 7 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 10 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 8 Floor, Painting upto 7 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% | 87.5% |  | 94% |  | Excavation in process | 5
Plinth |  | 10 | 100% |  |  |  |  | Excavation Completed | 10
RCC (Including podiums) |  | 11 | 100% |  |  |  |  | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 80% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 70% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 20% |  |  |  |  | Plinth in process | 7.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 10
Construction details: |  | Wing R2 (Rain Basera) = G + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 2 Floor, Painting upto 3 Floor Completed | , Flooring upto 2 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 2 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 83.75% |  | 92.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 50% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 8000
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 220000
Club Charges |  |  |  |  | 25000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 3200
Commercial Area Details (Shop) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | Housing | Sheet
Wing R1 |  | 6 |  | 895.1342 |  | 1387.4581 |  | 3747.5 | 4250
Wing R2 |  | 6 |  | 889.1064 |  | 1378.1149 |  | 4336.2832 | 4778.7611
Total |  | 12 |  | 1784.2406 |  | 2765.573
Commercial Area Details (Office) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | https://www.proptiger.com/mumbai/badlapur-west/shree-sha-developers-nirman-signature-3282670
Wing R1 |  | 6 |  | 798.9041 |  | 1238.3013 |  | https://housing.com/in/buy/projects/page/297866-nirman-signature-by-shree-sha-developers-in-badlapur-west
Wing R2 |  | 2 |  | 226.1247 |  | 350.4933
Total |  | 8 |  | 1025.0288 |  | 1588.7947
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing R1 |  | 47 |  | 16859.5994 |  | 26410
Wing R2 |  | 6 |  | 2395.5282 |  | 3757.6209
Total |  | 53 |  | 19255.1276 |  | 30167.6209
Grand Total |  | 73 |  | 22064.397 |  | 34521.9886
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Wing R1
Nirman Signature
Ground Floor For Commercial, Fitness centre/Creche/Society Office, Drivers Room, & Parking
1 |  | Shop | 159.8454 | 0 | 247.7604 | Ground Floor For Commercial, Fitness centre/Creche/Society Office, Drivers Room, & Parking |  | 14.85
2 |  | Shop | 127.8763 | 0 | 198.2083
3 |  | Shop | 159.8454 | 0 | 247.7604
4 |  | Shop | 159.8454 | 0 | 247.7604
5 |  | Shop | 127.8763 | 0 | 198.2083 |  |  | Nirman Signature
6 |  | Shop | 159.8454 | 0 | 247.7604
1st Floor For Commercial & Residential
1 |  | Office | 189.4464 | 0 | 293.6419 | 1st Floor For Commercial & Residential
2 |  | Office | 89.987 | 0 | 139.4799
3 |  | Office | 112.4838 | 0 | 174.3499
4 |  | Office | 112.4838 | 0 | 174.3499
5 |  | Office | 89.987 | 0 | 139.4799
6 |  | Office | 204.516 | 0 | 316.9998
Wing R2
Rain Basera
Ground Floor For Commercial
1 |  | Shop | 159.8454 | 0 | 247.7604 | Ground Floor For Commercial |  | 14.85
2 |  | Shop | 127.8763 | 0 | 198.2083
3 |  | Shop | 209.2522 | 0 | 324.3408
4 |  | Shop | 159.8454 | 0 | 247.7604
5 |  | Shop | 119.8033 | 0 | 185.6951
6 |  | Shop | 112.4838 | 0 | 174.3499
1 |  | Office | 137.5639 | 0 | 213.2241
2 |  | Office | 88.5608 | 0 | 137.2693
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
50%
Wing R1
Nirman Signature
1st Floor For Commercial & Residential
101 |  | 1BHK | 369.2052 | 0 | 565 | 1st Floor For Commercial & Residential |  |  | 565 | 1.5303
102 |  | 1RK | 258.8742 | 0 | 400 |  |  |  | 400 | 1.5452
103 |  | 1BHK | 407.9287 | 0 | 620 |  |  |  | 620 | 1.5199
2nd Floor For Residential
201 |  | 1BHK | 369.2052 | 0 | 565 | 2nd Floor For Residential |  |  | 565 | 1.5303
202 |  | 1RK | 258.8742 | 0 | 400 |  |  |  | 400 | 1.5452
203 |  | 1BHK | 407.9287 | 0 | 620 |  |  |  | 620 | 1.5199
204 |  | 1BHK | 336.6172 | 105.0836 | 670 |  |  |  | 670 | 1.9904
205 |  | 1BHK | 336.6172 | 105.0836 | 670 |  |  |  | 670 | 1.9904
4th, 6th & 10th Floor For Residential
401 ,.., 1001 |  | 1BHK | 369.2052 | 0 | 565 | 4th, 6th & 10th Floor For Residential |  |  | 565 | 1.5303
402 ,.., 1002 |  | 1RK | 258.8742 | 0 | 400 |  |  |  | 400 | 1.5452
403 ,.., 1003 |  | 1BHK | 407.9287 | 0 | 620 |  |  |  | 620 | 1.5199
404 ,.., 1004 |  | 1BHK | 376.5785 | 65.1222 | 620 |  |  |  | 620 | 1.6464 | 4500
405 ,.., 1005 |  | 1BHK | 376.5785 | 65.1222 | 620 |  |  |  | 620 | 1.6464
3rd, 5th, 7th & 9th Floor
301 ,.., 901 |  | 1BHK | 369.2052 | 0 | 565 | 3rd, 5th, 7th & 9th Floor |  |  | 565 | 1.5303
302 ,.., 902 |  | 1RK | 258.8742 | 0 | 400 |  |  |  | 400 | 1.5452
303 ,.., 903 |  | 1BHK | 407.9287 | 0 | 620 |  |  |  | 620 | 1.5199
304 ,.., 904 |  | 1BHK | 398.7793 | 0 | 610 |  |  |  | 610 | 1.5297
305 ,.., 905 |  | 1BHK | 398.7793 | 0 | 610 |  |  |  | 610 | 1.5297
8th Floor (Part Refuge Area)
801 |  | 1BHK | 369.2052 | 0 | 565 | 8th Floor (Part Refuge Area) |  |  | 565 | 1.5303
802 |  | 1RK | 258.8742 | 0 | 400 |  |  |  | 400 | 1.5452
803 |  | 1BHK | 407.9287 | 0 | 620 |  |  |  | 620 | 1.5199
- |  | Refuge Area
804 |  | 1BHK | 376.5785 | 65.1222 | 620 |  |  |  | 620 | 1.6464
Wing R2
Rain Basera
1st & 2nd Floor For Hall
3rd Floor For Residential
301 |  | 1BHK | 387.2349 | 110.3848 | 592.4694 | 3rd Floor For Residential
302 |  | 1BHK | 404.538 | 176.3681 | 618.9432
303 |  | 1BHK | 368.9899 | 184.9255 | 657.0173
4th Floor
401 |  | 1BHK | 409.4357 | 0 | 626.4365 | 4th Floor
402 |  | 1BHK | 426.7388 | 0 | 652.9103
403 |  | 1BHK | 398.5909 | 0 | 609.8441
Remarks:
* | Wing R1 & R2 = Construction work is in process at the time of Visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Open Balcony + C.P. Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Nirman Signature
Layout :
Google Map :
Formulas:
Badlapurgaon = [Badlapurgaon, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building
WING R1
WING R2
R1
R2
R2
R1
R2
R1
R2
R2
R1
R2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC