## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s. La Mer Developers Pvt. Ltd
Name of the builder company |  |  |  | M/s. La Mer Developers Pvt. Ltd
Name of the Project |  |  |  | La Mer Regency
Contact Details ( Name & Contact No.) |  |  |  | 9987300005
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Prashant Tambe 9167914158
Name / No of the Building |  |  |  | A & B Wing B Wing
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000034668
Project location details |  | La Mer Regency, Plot No.493, near La Riveria lakhani, Kalpataru Riverside Market Yard Road, Old Panvel, Panvel, Panvel West, Panvel, Raigad - 410206.
Plot No |  | 493
Locality |  | Old Panvel
Road |  | Kalpataru Riverside Market Yard Road |  | Village |  | Panvel
City |  | Panvel West |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | La Riveria lakhani |  | Distance from city centre: |  | 2.2KM from Panvel Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Vasant Aalap Co-op Housing Society
West | NA | NA |  |  | La Riveria lakhani
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 18.9791402,73.1111325
Location Link |  | https://goo.gl/maps/nss1QzVZL4PT7sHj6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3870
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.5584
Total FSI availaible for the project |  |  |  | 2.6584
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10288
Total number of Buildings |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | PMP/NRV/16293/JK-866/2022 |  |  | Dated | 2022-03-23
Approved Floor plan No. |  | PMP/NRV/16293/JK-866/2022 |  |  | Dated | 2022-03-23
Commencement-CC No Valid Up to: |  | PMP/TP/Panvel/493/21-22/16293/866/2022 |  |  | Dated | 2022-03-23
A & B Wing = G + 1st to 9th Floor B Wing = G + 1st to 9th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10288
Approved no of units |  |  | Flats -136, Offices -6, Shop -5
Approved no of Floors |  |  | A & B Wing = G + 1st to 9th Floor B Wing = G + 1st to 9th Floor
Proposed no of Floors |  |  | A Wing = G + 1st to 13th Floor
B Wing = G + 1st to 13th Floor
Expected Completion |  |  | As per RERA - 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative Entrance, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = G + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 10 Floor, Painting upto 10 Floor Completed | , Flooring upto 10 Floor, Painting upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 10 Floor, Painting upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 86.54% |  | 93.85% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 76.92% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 76.92% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | B Wing = G + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 9 Floor, Painting upto 9 Floor Completed | , External Plaster upto 12 Floor, Flooring upto 9 Floor, Painting upto 9 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 9 Floor, Painting upto 9 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 84.62% |  | 93.08% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 92.31% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 69.23% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 9 | 69.23% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 8200
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 15000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 12500
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 6560
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 6 |  | 2883.245 |  | 4613.1921
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 65 |  | 36284.6518 |  | 54585.4237
B Wing |  | 71 |  | 40148.4929 |  | 60222.7394
Total |  | 136 |  | 76433.1447 |  | 114808.1631
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
A Wing
Ground Floor For Commercial & Parking | [7 empty] | 10.764
1 |  | Shop | 602.5687 | 0 | 964.11 | Ground Floor For Commercial & Parking
2 |  | Shop | 621.621 | 0 | 994.5936 |  |  |  | 747.8569
3 |  | Shop | 641.4268 | 0 | 1026.2828
4 |  | Shop | 924.52 | 0 | 1479.2319
5 |  | Shop | 283.3085 | 0 | 453.2936 |  |  |  | 1.5
1st Floor For Commercial | [8 empty] | 1.6*
101 |  | Office | 643.5796 | 0 | 1029.7273 | 1st Floor For Commercial
102 |  | Office | 378.8928 | 0 | 606.2285 |  |  |  | 747.8569
103 |  | Office | 414.5216 | 0 | 663.2346
104 |  | Office | 460.8068 | 0 | 737.2909 |  |  | 5.45 | 7
105 |  | Office | 535.6166 | 0 | 856.9866 |  |  | 1 | 1.2844
106 |  | Office | 449.8276 | 0 | 719.7241
[8 empty] | 4 | 5.91
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor |  | 1 | 1.4775
50%
A Wing
1st Floor for Residential
1 |  | 1 | 455.4787 | 0 | 683.218 | 1st Floor for Residential
2 |  | 2 | 687.2986 | 0 | 1030.9479 |  |  | 8050.843
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 1 | 455.4787 | 0 | 683.218
2nd Floor
1 |  | 1 | 455.4787 | 0 | 683.218 | 2nd Floor |  | 8050.1393
2 |  | 2 | 687.2986 | 0 | 1030.9479 |  |  | 8059.1727
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 1 | 455.4787 | 0 | 683.218
3rd Floor for Residential & Amenities
1 |  | 1 | 455.4787 | 0 | 683.218 | 3rd Floor for Residential & Amenities
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 1 | 455.4787 | 0 | 683.218
4th Floor
1 |  | 1 | 455.4787 | 0 | 683.218 | 4th Floor
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 2 | 687.2986 | 79.223 | 1110.171
7 |  | 2 | 687.2986 | 79.223 | 1110.171
8 |  | 1 | 455.4787 | 0 | 683.218
5th Floor
1 |  | 1 | 455.4787 | 0 | 683.218 | 5th Floor
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 2 | 687.2986 | 0 | 1030.9479
7 |  | 2 | 687.2986 | 0 | 1030.9479
8 |  | 1 | 455.4787 | 0 | 683.218
6th, 7th, 9th Floor
1 |  | 1 | 455.4787 | 0 | 683.218 | 6th, 7th, 9th Floor
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 2 | 724.4344 | 0 | 1086.6516
7 |  | 2 | 724.4344 | 0 | 1086.6516
8 |  | 1 | 455.4787 | 0 | 683.218
8th Floor (Part Refuge Area)
1 |  | 1 | 455.4787 | 0 | 683.218 | 8th Floor (Part Refuge Area)
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 653.4997 | 0 | 980.2495
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 2 | 724.4344 | 0 | 1086.6516
7 |  | 1 | 455.4787 | 0 | 683.218
B Wing
Ground Floor For Parking
1st to 7th & 9th Floor For Residential
1 |  | 1 | 455.4787 | 0 | 683.218 | 1st to 7th & 9th Floor For Residential
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 687.2986 | 0 | 1030.9479
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 2 | 687.2986 | 0 | 1030.9479
7 |  | 2 | 653.4997 | 0 | 980.2495
8 |  | 1 | 455.4787 | 0 | 683.218
8th Floor (Part Refuge Area)
1 |  | 1 | 455.4787 | 0 | 683.218 | 8th Floor (Part Refuge Area)
2 |  | 2 | 687.2986 | 0 | 1030.9479
3 |  | 2 | 687.2986 | 0 | 1030.9479
4 |  | 1 | 455.4787 | 0 | 683.218
5 |  | 1 | 455.4787 | 0 | 683.218
6 |  | 2 | 653.4997 | 0 | 980.2495
7 |  | 1 | 455.4787 | 0 | 683.218
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the construction work goes beyond the Approved plan & CC permission. Please provide revised approved CC & Floor plans.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra vishwakarma |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | La Mer Regency
Google Map :
Formulas:
Panvel = [Panvel, row above]
Wing B
Wing B
Wing A
Wing A
Wing A
Wing A
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted