## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s.Om Sai Construction
Name of the builder company |  |  |  | M/s.Om Sai Construction
Name of the Project |  |  |  | Paramount Enclave Phase 02
Contact Details ( Name & Contact No.) |  |  |  | 9890496008
Name / No of the Building |  |  |  | Building No.4 (A Wing/TypeA)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet | [6 empty] | Paramount Enclave II Building No. 4 Type A Wing A
RERA No. |  |  |  | P99000028976
Project location details |  | Paramount Enclave Phase 02, S No.1023/7, near Gayatri Park, Haranwadi Road, Mahim, Palghar, Palghar, Palghar.
S No |  | 1023/7
Road |  | Haranwadi Road |  | Village |  | Mahim
City |  | Palghar |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Nearby Landmark |  | Gayatri Park |  | Distance from city centre: |  | 4.1Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Building
North | NA | NA |  |  | Haranwadi Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.6751 |  | Longitude |  | 72.7416
Location Link |  | https://goo.gl/maps/sgUk54mgnHjvXzeNA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 14600
Permissible FSI |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 0.75
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10950
Total number of Buildings |  |  |  | 01 Wing
Approval Detail : Plan approval
Layout Approval No |  | MHASUL/KS.1/MJ.1/ANAP/SR/139/19 |  |  | Dated | 06/12/2019.
Approved Floor plan No. |  | MHASUL/KS.1/MJ.1/ANAP/SR/139/19 |  |  | Dated | 06/12/2019.
Commencement Certificate No. |  | MHASUL/KS.1/MJ.1/ANAP/SR/139/19 |  |  | Dated | 06/12/2019.
Valid Up to: Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 1602.04
Approved no of units |  |  | Flats - 38, Shops - 08
Approved no of Floors |  |  | Building No.4 (A Wing/TypeA) = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.4 (A Wing/TypeA) = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.4 (A Wing/TypeA) = Gr + 1st to 7th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 5 Floor completed, Painting upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 5 Floor completed, Painting upto 2 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1.75
Excavation |  | 7 | 100% | 82.14% |  | 92.86% |  | Excavation in process |  | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed |  | 7
RCC |  | 8 | 100% |  |  |  |  | Footing in Process |  | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed |  | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 2 | 28.57% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 7
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4100 |  |  | rate is considered from paramount Encalve PH-2 (Bldg no.2,Type - D1, B - wing)
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 75,000/-
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Maintenance Charges |  |  |  |  | 1,00,000/-
Advance |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 3280
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 8 |  | 1242.8114 |  | 1242.8114
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 17415.0756 | 17415.0756
Flats |  | 38 |  | 16172.2642 |  | 16172.2642
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Building No.4 (A Wing/TypeA)
Ground Floor for Commercial & Parking
14 |  | Shop | 139.3938 | 0 | 216.0604 | Ground Floor for Commercial & Parking
15 |  | Shop | 127.7687 | 0 | 198.0415
16 |  | Shop | 184.2797 | 0 | 285.6335 |  |  | 7001.9797
17 |  | Shop | 148.2203 | 0 | 229.7414
18 |  | Shop | 119.2651 | 0 | 184.8609
19 |  | Shop | 109.0393 | 0 | 169.0109
20 |  | Shop | 179.2206 | 0 | 277.7919
21 |  | Shop | 235.624 | 0 | 365.2171
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.4 (A Wing/TypeA)
1st to 6th Floor
101 to 601 |  | 1BHK | 395.7654 | 0 | 630 | 1st to 6th Floor |  | 1.5919 | 1.5919 |  |  | 101 to 601 | 101 | 601
102 to 602 |  | 1BHK | 394.7966 | 0 | 630 |  |  |  | 1.5958 |  |  | 102 to 602 | 102 | 602
103 to 603 |  | 1BHK | 374.2912 | 0 | 630 |  |  |  | 1.6832 |  |  | 103 to 603 | 103 | 603
104 to 604 |  | 1BHK | 374.2912 | 0 | 630 |  |  |  | 1.6832 |  |  | 104 to 604 | 104 | 604
105 to 605 |  | 1BHK | 396.4112 | 0 | 630 |  |  |  | 1.5893 |  |  | 105 to 605 | 105 | 605
106 to 606 |  | 2BHK | 594.7379 | 0 | 950 |  |  | 4100 | 1.5973 |  |  | 106 to 606 | 106 | 606
7th Floor (Part Terrace Area)
701 |  | 1BHK | 395.7654 | 0 | 630 | 7th Floor (Part Terrace Area) |  |  | 1.5919
702 |  | 2BHK | 594.7379 | 0 | 950 |  |  |  | 1.5973
703 |  |  |  | 0 | #REF! | 0 |  |  | #REF!
704 |  |  |  | 0 | #REF! | 0 |  |  | #REF!
705 |  |  |  | 0 | #REF! | 0 |  |  | #REF!
706 |  |  |  | 0 | #REF! | 0 |  |  | #REF!
1st, 2nd, 3rd, 5th, 7th & 9th Floor | [8 empty] | #DIV/0!
101,..,901 |  |  |  | 0 | #REF! | 1st, 2nd, 3rd, 5th, 7th & 9th Floor |  |  | #REF! |  |  | 101,..,901 | 101 | 901
102,..,902 |  |  |  | 0 | #REF! | 1st, 2nd, 3rd, 5th, 7th & 9th Floor |  |  | #REF! |  |  | 102,..,902 | 102 | 902
103,..,903 |  |  |  | 0 | #REF! | 1st, 2nd, 3rd, 5th, 7th & 9th Floor |  |  | #REF! |  |  | 103,..,903 | 103 | 903
104,..,904 |  |  |  | 0 | #REF! | 1st, 2nd, 3rd, 5th, 7th & 9th Floor |  |  | #REF! |  |  | 104,..,904 | 104 | 904
105,..,905 |  |  |  | 0 | #REF! | 1st, 2nd, 3rd, 5th, 7th & 9th Floor |  |  | #REF! |  |  | 105,..,905 | 105 | 905
106,..,906 |  |  |  | 0 | #REF! | 1st, 2nd, 3rd, 5th, 7th & 9th Floor |  |  | #REF! |  |  | 106,..,906 | 106 | 906
1st & 20th Floor | [8 empty] | #DIV/0!
101 & 2001 |  |  |  | 0 | #REF! | 1st & 20th Floor |  |  | #REF! |  |  | 101 & 2001 | 101 | 2001
102 & 2002 |  |  |  | 0 | #REF! | 1st & 20th Floor |  |  | #REF! |  |  | 102 & 2002 | 102 | 2002
103 & 2003 |  |  |  | 0 | #REF! | 1st & 20th Floor |  |  | #REF! |  |  | 103 & 2003 | 103 | 2003
104 & 2004 |  |  |  | 0 | #REF! | 1st & 20th Floor |  |  | #REF! |  |  | 104 & 2004 | 104 | 2004
105 & 2005 |  |  |  | 0 | #REF! | 1st & 20th Floor |  |  | #REF! |  |  | 105 & 2005 | 105 | 2005
106 & 2006 |  |  |  | 0 | #REF! | 1st & 20th Floor |  |  | #REF! |  |  | 106 & 2006 | 106 | 2006
Remarks:
1 | Construction work is in the process. (Slow Speed) | [6 empty] | Construction work was stopped. Work is same as last visit dtd.13/04/2024
2 | We considered Saleable area of shop as per our calculation & Flat area as per builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area+W.S Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | As per RERA, completion period of project Paramount Enclave Phase 02 is expired on Date 31/12/2023 but still project is under construction
8 | On Site, we meet Mr.Vikas - 9673439288.
7 | The project has received first CC on 06/12/2019, But construction work is not yet completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Paramount Enclave Phase 02
Google Map :

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.74 | 3.57 | 9.7818 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.13 | 1.74 | 3.7062 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.74 | 2.74 | 7.5076 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.83 | 1.22 | 2.2326 | DB |  |  | 0 |  |  | 0
| toilet2 | 0.91 | 1.22 | 1.1102 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 261.9785 | 24.3384 |  |  | 0 | 0 |  | 0 | 0
|  |  | 261.9785 | 24.3384
31.06

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted