## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-10 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder |  |  |  | Suraj Pandharinath Keni | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Parshuputra Group | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Parshu Heritage |  |  |  | Approved Sign is not Visible in my PC but visibl in sachin sir pc | [5 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Suraj Keni 7021124492
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Roshal 9619372306
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Cost Sheet | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000051367 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Parshu Heritage, Plot No.70 & Sector No.R2, near Vandana Liberty, Internal Road, Vadghar, Pushpak, Panvel West, Panvel, Raigad - 410206. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 70 & Sector No.R2 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Vadghar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Pushpak | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Panvel West |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410206 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Vandana Liberty |  | Distance from city centre: |  | 4 KM from Panvel Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Plot No. 69 |  |  | Other Building
West | NA | Plot No. 71 |  |  | Other Building
North | NA | Plot No. 75 & 76 |  |  | Vandana Liberty
South | NA | 20 M W Road |  |  | Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.9827007, 73.0926224
Location Link |  | https://maps.app.goo.gl/m9Aqxm3Xm4iaGRQr9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 699.84
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.7423
Total FSI availaible for the project |  |  |  | 3.2423
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2269.1
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | City and Industrial Development Corporation (CIDCO) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | CIDCO/BP-18148/TPO(NM & K)/2022/11484 |  |  | Dated | 2023-10-18 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | CIDCO/BP-18148/TPO(NM & K)/2022/11484 |  |  | Dated | 2023-10-18 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | CIDCO/BP-18148/TPO(NM & K)/2022/11484 |  |  | Dated | 2023-10-18 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | G + 1st to 7th Floor (Total Builtup Area = 2269.10 Sq.mtrs.) | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | G + 1st to 7th Floor (Total Builtup Area = 2269.10 Sq.mtrs.) |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 2269.1
Approved no of units |  |  | Flats - 44, Shops -5, Offices -2
Approved no of Floors |  |  | G + 1st to 7th Floor
Proposed no of Floors |  |  | G + 1st to 7th Floor
Expected Completion |  |  | Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, Landscaping & Garden, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | G + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | Work not yet Started.
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | 0 | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | 0 | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6100 |  |  | rate 6100 by smith Verbal 06/01/2025 | [8 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 11500 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 8500 | [11 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges |  |  |  |  | 200000 | [11 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges |  |  |  |  | 50000 | [11 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 250000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 4880 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 5 |  | 1349.3966 |  | 2024.0949
Offices |  | 2 |  | 1122.33 |  | 1683.495
Total |  | 7 |  | 2471.7266 |  | 3707.5898
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 44 |  | 16772.8092 |  | 25634.7405
Total |  | 44 |  | 16772.8092 |  | 25634.7405
Grand Total |  | 51 |  | 19244.5358 |  | 29342.3303
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Ground Floor For Commercial, Parking & Lobby | [8 empty] | 10.764
1 |  | Shop | 182.5897 | 0 | 182.5897 | 0 | 273.8846 | 16.9625
2 |  | Shop | 359.2485 | 0 | 359.2485 | 0 | 538.8727
3 |  | Shop | 273.1903 | 0 | 273.1903 | 0 | 409.7855
4 |  | Shop | 251.6623 | 0 | 251.6623 | 0 | 377.4935 | 22.68
5 |  | Shop | 282.7057 | 0 | 282.7057 | 0 | 424.0585
1st Floor For Commercial & Residential
1 |  | Office | 458.0082 | 0 | 458.0082 | 0 | 687.0123 | 42.36
2 |  | Office | 664.3218 | 0 | 664.3218 | 0 | 996.4827
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Balcony Area + Chajja Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
1st Floor For Residential, Commercial, Society Office & Drivers Room
101 |  | 1BHK | 315.1699 | 114.9595 | 430.1294 | 0 | 645.1942 | 28.145 | 10.53
102 |  | 1BHK | 315.1699 | 111.9456 | 427.1155 | 0 | 640.6733
103 |  | 1RK | 201.5559 | 0 | 201.5559 | 0 | 302.3338 | 18.285
104 |  | MP Room | 239.6389 | 0 | 239.6389 | 0 | 359.4584
105 |  | Commercial
106
107 |  | Society Office/ Drivers Room
2nd Floor For Residential
201 |  | 1BHK | 315.1699 | 114.9595 | 430.1294 | 0 | 645.1942
202 |  | 1BHK | 315.1699 | 111.9456 | 427.1155 | 0 | 640.6733
203 |  | 1RK | 201.5559 | 0 | 201.5559 | 0 | 302.3338
204 |  | 1BHK | 322.7585 | 0 | 322.7585 | 104.2493 | 536.2625 | 28.845
205 |  | 1BHK | 321.0471 | 0 | 321.0471 | 92.2475 | 573.8181
206 |  | 1BHK | 318.6144 | 0 | 318.6144 | 97.9524 | 575.874
207 |  | 1BHK | 317.4842 | 0 | 317.4842 | 184.0644 | 568.2585
3rd & 4th Floor
301 & 401 |  | 1BHK | 315.1699 | 114.9595 | 430.1294 | 0 | 645.1942
302 & 402 |  | 1BHK | 315.1699 | 111.9456 | 427.1155 | 0 | 640.6733
303 & 403 |  | 1RK | 201.5559 | 43.5942 | 245.1501 | 0 | 367.7251
304 & 404 |  | 1BHK | 322.7585 | 76.828 | 399.5866 | 0 | 599.3799 |  | 3.5
305 & 405 |  | 1BHK | 321.0471 | 80.5309 | 401.5779 | 0 | 602.3669
306 & 406 |  | 1BHK | 318.6144 | 100.5519 | 419.1663 | 0 | 628.7495
307 & 407 |  | 1BHK | 317.4842 | 80.9453 | 398.4295 | 0 | 597.6442 |  | 7.5
5th Floor For Residential
501 |  | 1BHK | 315.1699 | 114.9595 | 430.1294 | 0 | 645.1942
502 |  | 1BHK | 315.1699 | 111.9456 | 427.1155 | 0 | 640.6733
503 |  | 2BHK | 545.3796 | 128.7267 | 674.1063 | 0 | 1011.1594 | 49.6427 | 6.1092
504 |  | 1BHK | 321.0471 | 80.5309 | 401.5779 | 0 | 602.3669
505 |  | 1BHK | 318.6144 | 100.5519 | 419.1663 | 0 | 628.7495
506 |  | 1BHK | 317.4842 | 80.9453 | 398.4295 | 0 | 597.6442
6th Floor
601 |  | 1BHK | 315.1699 | 79.9873 | 395.1572 | 0 | 592.7358 |  | 7.28
602 |  | 1BHK | 315.1699 | 76.9734 | 392.1433 | 0 | 588.2149
603 |  | 1RK | 217.1529 | 43.5942 | 260.7471 | 0 | 391.1207 | 19.635
604 |  | 1BHK | 310.3261 | 94.6801 | 405.0063 | 0 | 607.5094 | 28.025 | 6.7707
605 |  | 1BHK | 321.0471 | 63.1739 | 384.221 | 0 | 576.3315
606 |  | 1BHK | 318.6144 | 78.3512 | 396.9656 | 0 | 595.4483
607 |  | 1BHK | 317.4842 | 80.9453 | 398.4295 | 0 | 597.6442
7th Floor
701 |  | 1BHK | 320.4443 | 91.0311 | 411.4754 | 0 | 617.2131 | 27.9063 | 8.415
702 |  | 1BHK | 322.1665 | 87.4683 | 409.6348 | 85.1971 | 699.6492
703 |  | 1BHK | 302.2316 | 60.9511 | 363.1827 | 111.9456 | 600.7469
704 |  | 1BHK | 321.0471 | 60.9511 | 381.9982 | 0 | 572.9973
705 |  | 1BHK | 318.6144 | 61.7585 | 380.3728 | 0 | 570.5593
706 |  | 1BHK | 304.9656 | 58.5293 | 363.4949 | 0 | 545.2423
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | All work Completed. Please provide OC.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 06/01/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Parshu Heritage
Layout :
Google Map :
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F106: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H139: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate