## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s.Brajbhoomi Developers
Name of the builder company |  |  |  | M/s.Brajbhoomi Developers
Name of the Project |  |  |  | Paramount Enclave
Contact Details ( Name & Contact No.) |  |  |  | 9867724573/8446550091
Name / No of the Building |  |  |  | Phase II = Building No.3 - Wing A (Type C)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P99000029292
Project location details |  | Paramount Enclave, Survey No.1023/7, near Gayatri Park, Haranwadi Road, Mahim, Palghar (East), Palghar, Palghar.
Survey No |  | 1023/7
Road |  | Haranwadi Road |  | Locality/Village |  | Mahim
City |  | Palghar (East) |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Nearby Landmark |  | Gayatri Park |  | Distance from city centre: |  | 4.1 Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open land
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Av Prp Housing Projects
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.6746 |  | Longitude |  | 72.7428
Location Link |  | https://goo.gl/maps/eU62wmGbqK83so2M7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 14600
Permissible FSI |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 0.75
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10950
Total number of Buildings |  |  |  | 01 Wing
Approval Detail : Plan approval
Layout Approval No |  | MAHSUL/KAKSH-1/T-1/NAP/SR/139/19 |  |  | Dated | 2019-12-06
Approved Floor plan No. |  | MAHSUL/KAKSH-1/T-1/NAP/SR/139/19 |  |  | Dated | 2019-12-06
Commencement Certificate No. |  | MAHSUL/KAKSH-1/T-1/NAP/SR-139/2019 |  |  | Dated | 2019-12-06
Valid Up to: Building No.3 - Wing A (Type C) = G/St + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10950
Approved no of units |  |  | Flats -37
Approved no of Floors |  |  | Building No.3 - Wing A (Type C) = G/St + 1st to 4th Floor
Proposed no of Floors |  |  | Building No.3 - Wing A (Type C) = G/St + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/03/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.3 - Wing A (Type C) = G/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3.5 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3.5 Floor, Painting upto 1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 85% |  | 94.38% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3.5 | 87.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 25% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3800
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 1,00,000/-
Other Charges |  |  |  |  | 65,000/-
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | 1,00,000/-
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 3040
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 37 |  | 13430.0275 |  | 22065
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.3
Wing A (Type - C)
Ground Floor for Residential & Parking
1 | 5 | 1 BHK | 316.7845 | 0 | 605 | Ground Floor for Residential & Parking
2 | 4 | 1 BHK | 318.3991 | 0 | 605 | Ground Floor for Residential & Parking |  | 3699.1736 | 1.9098
3 | 3 | 2 BHK | 464.4666 | 0 | 865 | Ground Floor for Residential & Parking |  | 3742.1965
4 | 2 | 1 BHK | 314.9546 | 0 | 605 | Ground Floor for Residential & Parking
5 | 1 | 1 RK | 221.0926 | 0 | 425 | Ground Floor for Residential & Parking |  | 3698.8235
1st to 4th Floor
1 | 8 | 1 BHK | 360.89 | 0 | 605 | 1st to 4th Floor |  |  |  | 101 to 401 | 101 | 401
2 | 7 | 1 BHK | 381.3954 | 0 | 605 | 1st to 4th Floor |  |  |  | 102 to 402 | 102 | 402
3 | 6 | 1 BHK | 383.4675 | 0 | 605 | 1st to 4th Floor |  |  |  | 103 to 403 | 103 | 403
4 | 5 | 2 BHK | 554.3998 | 0 | 865 | 1st to 4th Floor |  |  |  | 104 to 404 | 104 | 404
5 | 4 | 1 BHK | 379.7001 | 0 | 605 | 1st to 4th Floor |  |  |  | 105 to 405 | 105 | 405
6 | 3 | 1 RK | 265.9784 | 0 | 425 | 1st to 4th Floor |  |  |  | 106 to 406 | 106 | 406
7 | 2 | 1 RK | 265.6555 | 0 | 425 | 1st to 4th Floor |  |  |  | 107 to 407 | 107 | 407
8 | 1 | 1 BHK | 357.0957 | 0 | 605 | 1st to 4th Floor |  |  |  | 108 to 408 | 108 | 408
Remarks:
1 | Work is same as last visit (07/04/2025). | [6 empty] | Construction work is the same as last visit dtd.13/04/2024, but work is in process at the time of the visit. (Slow Speed)
2 | We considered Saleable area as per Builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + W.S Area.
5 | We have considered rate by verifying it from market inquire.
6 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes).
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr. Manoj (Watchmen) : 8976568751.
9 | As per RERA, completion period of project Paramount Enclave is expired on 31/03/2025 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Paramount Enclave
Google Map :
Formulas:
Mahim = [Mahim, row above]

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted