## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | M/s.Shreenath Enterprises
Name of the builder company |  |  |  | M/s.Shreenath Enterprises
Name of the Project |  |  |  | Parasnath Corner
Contact Details ( Name & Contact No.) |  |  |  | 7709011112/774090078/8411885552
Name / No of the Building |  |  |  | Building No. 1 (Wing A to E) Building No. 2 (Wing A)
Docouments Provided |  |  |  | Approved Plans, Sale Plans.
RERA No. |  |  |  | P99000018754
Project location details |  | Parasnath Corner, Gut No.92, 168 & 169, Hissa No. 1, near Parasnath Nagari, Internal road, Umroli, Umroli east, Palghar, Palghar - 401205.
Gut No |  | 92, 168 & 169, Hissa No. 1
Road |  | Internal road |  | Locality/Village |  | Umroli
City |  | Umroli east |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401205
Nearby Landmark |  | Parasnath Nagari |  | Distance from city centre: |  | 0.6 KM from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Parasnath garden
West | NA | NA |  |  | Padghe road
North | NA | NA |  |  | Yasuvansi Complex
South | NA | NA |  |  | Open plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.7543 |  | Longitude |  | 72.763
Location Link |  | https://goo.gl/maps/RenwKGZCgmsCjgrH7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5276.3
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | -0.01972
Total FSI availaible for the project |  |  |  | 0.98028
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5172.25
Total number of Buildings |  |  |  | 6 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Office Of District Collector, Palghar
Layout Approval No |  | Mahsul/K-1/Mej-1/BSP/SR/CR/233/17 |  |  | Dated | 2018-06-25
Approved Floor plan No. |  | Mahsul/K-1/Mej-1/BSP/SR/CR/233/17 |  |  | Dated | 2018-06-25
Commencement-CC No Valid Up to: |  | Mahsul/Kash-1/T-1/NAP/SR-233/2017 |  |  | Dated | 2018-06-25
Building No. 1 (Wing A to D) = G/St + 1st to 4th Floor Building No. 1 (Wing E) = G/St + 1st to 2nd Floor Building No. 2 (Wing A) = Ground Floor.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5172.25
Approved no of units |  |  | Flats - 124, Shops - 16
Approved no of Floors |  |  | Building No. 1 (Wing A to D) = G/St + 1st to 4th Floor Building No. 1 (Wing E) = G/St + 1st to 2nd Floor Building No. 2 (Wing A) = Ground Floor.
Proposed no of Floors |  |  | Building No. 1 (Wing A & B) = G/St + 1st to 4th Floor
Building No. 1 (Wing C) = G/St + 1st to 4th Floor
Building No. 1 (Wing D) = G/St + 1st to 4th Floor
Building No. 1 (Wing E) = G/St + 1st to 4th Floor
Building No. 2 (Wing A) = G/St + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/03/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 1 (Wing A & B) = G/St + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3 Floor, Painting upto 3.5 Floor Completed | , Flooring upto 3 Floor, Painting upto 3.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3 Floor, Painting upto 3.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 86.88% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3.5 | 87.5% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 1 (Wing C) = G/St + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 3.5 Floor, Flooring upto 0.5 Floor Completed | , External Plaster upto 3.5 Floor, Flooring upto 0.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 3.5 Floor, Flooring upto 0.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 75% |  | 90% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.5 | 87.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0.5 | 12.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 1 (Wing D) = G/St + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 2.5 Floor, Flooring upto 0.5 Floor Completed | , External Plaster upto 2.5 Floor, Flooring upto 0.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 2.5 Floor, Flooring upto 0.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 72.5% |  | 88.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2.5 | 62.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0.5 | 12.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 1 (Wing E) = G/St + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 2.5 Floor Completed | , Brickwork upto 2.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 2.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 54.69% |  | 78.12% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 2.5 | 62.5% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (Wing A) = G/St + 1st to 4th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 10% |  | 45% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500 |  |  | 3200 to 3500 & OC |  | Nikhil | Cost sheet | 2023-02-21
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 5500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges, Water, Electricity |  |  |  |  | 170000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 50000
Advance Maintenance Charges |  |  |  |  | 50000
Recommended rate of Parking |  |  |  |  | 100000 |  |  | Rate sheet | shop - 5500
Distressed valuation of the Property |  |  |  |  | 2800 |  |  | Visitor | flat - 3200
Commercial Area Details :
Building & Wing |  | No. of Shops |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 | Wing A | 5 |  | 829.5815 |  | 1244.3722
| Wing B | 6 |  | 1126.6679 |  | 1690.0018
| Wing C | 5 |  | 961.1176 |  | 1441.6763
Total |  | 16 |  | 2917.3669 |  | 4376.0504
Residential Area Details :
Building & Wing |  | No. of Flats |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 | Wing A | 13 |  | 5373.0659 |  | 7790.9455
| Wing B | 17 |  | 5820.7406 |  | 8440.0739
| Wing C | 37 |  | 12125.0002 |  | 17581.2502
| Wing D | 29 |  | 10368.8536 |  | 15034.8377
| Wing E | 22 |  | 6738.1564 |  | 9770.3267
Building No. 2 | Wing A | 6 |  | 2113.8343 |  | 3065.0598
Total |  | 124 |  | 42539.6509 |  | 61682.4938
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
50%
Building No. 1
Wing A (Type - 1)
Ground Floor for Commercial & Parking
1 |  | Shop | 124.6471 | 0 | 186.9707 | Ground Floor for Commercial & Parking
2 |  | Shop | 150.9113 | 0 | 226.3669
3 |  | Shop | 213.1272 | 0 | 319.6908
4 |  | Shop | 186.3248 | 0 | 279.4873
5 |  | Shop | 154.571 | 0 | 231.8566 |  |  | 151.6378
Wing B (Type - 2)
Ground Floor for Commercial & Parking
1 |  | Shop | 190.1999 | 0 | 285.2998 | Ground Floor for Commercial & Parking
2 |  | Shop | 186.3248 | 0 | 279.4873
3 |  | Shop | 213.0196 | 0 | 319.5293
4 |  | Shop | 150.9113 | 0 | 226.3669
5 |  | Shop | 213.1272 | 0 | 319.6908 |  |  | 151.6378
6 |  | Shop | 173.0851 | 0 | 259.6277 |  |  | 151.6378
Wing C (Type - 3)
Ground Floor for Commercial & Parking
1 |  | Shop | 213.0196 | 0 | 319.5293 | Ground Floor for Commercial & Parking
2 |  | Shop | 213.0196 | 0 | 319.5293
3 |  | Shop | 147.0362 | 0 | 220.5544
4 |  | Shop | 174.915 | 0 | 262.3725
5 |  | Shop | 213.1272 | 0 | 319.6908 |  |  | 151.6378
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Building No. 1
Wing A (Type - 1)
Ground Floor for Residential & Parking
1 |  | 1BHK | 385.4588 | 0 | 558.9153 | Ground Floor for Residential & Parking
1st to 4th Floor for Residential
1 |  | 1BHK | 337.9896 | 0 | 490.0849 | 1st to 4th Floor for Residential
2 |  | 2BHK | 436.1573 | 0 | 632.4281
3 |  | 1BHK | 472.7549 | 0 | 685.4946
Wing B (Type - 2)
Ground Floor for Residential & Parking
4 |  | 1BHK | 337.9896 | 0 | 490.0849 | Ground Floor for Residential & Parking
1st to 4th Floor for Residential
1 |  | 1RK | 258.0131 | 0 | 374.119 | 1st to 4th Floor for Residential
2 |  | 1RK | 338.5278 | 0 | 490.8653
3 |  | 2BHK | 436.1573 | 0 | 632.4281
4 |  | 1BHK | 337.9896 | 0 | 490.0849
Wing C (Type - 3)
Ground Floor for Residential & Parking
1 |  | 1BHK | 337.9896 | 0 | 490.0849 | Ground Floor for Residential & Parking
2 |  | 1BHK | 325.5034 | 0 | 471.9799
3 |  | 1BHK | 337.9896 | 0 | 490.0849
4 |  | 1BHK | 337.9896 | 0 | 490.0849
5 |  | 1BHK | 337.9896 | 0 | 490.0849
1st to 4th Floor for Residential
1 |  | 1BHK | 337.9896 | 0 | 490.0849 | 1st to 4th Floor for Residential
2 |  | 1BHK | 325.5034 | 0 | 471.9799
3 |  | 1BHK | 337.9896 | 0 | 490.0849
4 |  | 1BHK | 337.9896 | 0 | 490.0849
5 |  | 1BHK | 337.9896 | 0 | 490.0849
6 |  | 1BHK | 337.9896 | 0 | 490.0849
7 |  | 1BHK | 338.4202 | 0 | 490.7092
8 |  | 1RK | 258.0131 | 0 | 374.119
Wing D (Type - 4)
Ground Floor for Residential & Parking
1 |  | 1BHK | 358.1183 | 0 | 519.2715 | Ground Floor for Residential & Parking
2 |  | 1BHK | 337.9896 | 0 | 490.0849
3 |  | 1BHK | 337.9896 | 0 | 490.0849
4 |  | 2BHK | 431.2058 | 0 | 625.2485
5 |  | 1BHK | 337.9896 | 0 | 490.0849
1st to 4th Floor for Residential
1 |  | 1BHK | 358.1183 | 0 | 519.2715 | 1st to 4th Floor for Residential
2 |  | 1BHK | 337.9896 | 0 | 490.0849
3 |  | 1BHK | 337.9896 | 0 | 490.0849
4 |  | 2BHK | 431.3135 | 0 | 625.4045
5 |  | 1BHK | 337.9896 | 0 | 490.0849
6 |  | 1BHK | 337.9896 | 0 | 490.0849
Wing E (Type - 5)
Ground Floor for Residential & Parking
1 |  | 1BHK | 337.9896 | 0 | 490.0849 | Ground Floor for Residential & Parking
2 |  | 1BHK | 329.0555 | 0 | 477.1304
3 |  | 1BHK | 322.92 | 0 | 468.234
4 |  | 1BHK | 337.9896 | 0 | 490.0849
5 |  | 1RK | 239.3914 | 0 | 347.1175
6 |  | 1BHK | 337.9896 | 0 | 490.0849
1st & 2nd Floor for Residential
1 |  | 1BHK | 337.9896 | 0 | 490.0849 | 1st & 2nd Floor for Residential
2 |  | 1RK | 239.3914 | 0 | 347.1175
3 |  | 1BHK | 339.8195 | 0 | 492.7382
4 |  | 1BHK | 322.92 | 0 | 468.234
5 |  | 1BHK | 337.9896 | 0 | 490.0849
6 |  | 1RK | 239.3914 | 0 | 347.1175
7 |  | 1RK | 260.9194 | 0 | 378.3331
8 |  | 1BHK | 337.9896 | 0 | 490.0849
Building No. 2
Wing A (Type - 6)
Ground Floor for Residential & Parking
1 |  | 1BHK | 337.9896 | 0 | 490.0849 | Ground Floor for Residential & Parking
2 |  | 2BHK | 441.7546 | 0 | 640.5441
3 |  | 2BHK | 427.9766 | 0 | 620.5661
4 |  | 1BHK | 337.9896 | 0 | 490.0849
5 |  | 1RK | 230.1343 | 0 | 333.6948
6 |  | 1BHK | 337.9896 | 0 | 490.0849
Remarks:
* | Building No. 1 (Wing A to E) = Construction Work is in process at the time of visit (Slow Speed). Building No.2 (Wing A) = Construction work is same as last visit (10/02/2023).
* | We have considered Saleable area of Flats as per our Calculation. | [6 empty] | As per site visit dtd. 27/07/2024, Around 5 to 10 labours found in Wing E only.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + C.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation. | [6 empty] | On Site, we meet Mr.Rakesh (7498195988).
* | Since the project has received first CC on 25/06/2018, But still construction work is pending
* | Please provide revised CC for Bldg No.1 (Wing E).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Parasnath Corner
Google Map :
Formulas:
Umroli = [Umroli, row above]
A Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted