## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 15/07/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-07-10
Name of the builder group |  |  |  |  | M/s.Sai Krishna Signature Homes LLP
Name of the builder company |  |  |  |  | M/s.Sai Krishna Signature Homes LLP
Name of the Project |  |  |  |  | Sai Krishna Aanandi
Contect Details ( Name & Contect No.) |  |  |  |  | 9819048949/7977811324
Name / No of the Building |  |  |  |  | Building No.1 Building No.2
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P99000021204
Project location details |  | Sai Krishna Aanandi, Gut No.68/2, Staion Road, Navali, Palghar.
Gut No |  | 68/2
Road |  | Staion Road |  |  | Locality/Village |  | Navali
City |  | Palghar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 400063
Near by Landmark |  | mahaveer krupa |  |  | Distance from city centre: |  | About 1.2Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Open Plot |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.6883 |  | Longitude |  | 72.7752
Location Link |  | https://goo.gl/maps/RJkXbHMCvMgK77pR7?coh=178572&entry=tt
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 2695.2
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 3234.24
Total number of Buildings |  |  |  |  | 2 Building
Approval Detail : Plan approval
Layout Approval No |  | KBV/199 |  |  |  | Dated | 01/01/2019.
Approved Floor plan No. |  | KBV/199 |  |  |  | Dated | 01/01/2019.
Commencement Certificate No. |  | PNP/BD/KY-199/2018-1019 Valid Up to: Building No.1 & 2 = G + 1st to 4th Floor |  |  |  | Dated | 01/01/2019.
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 01/01/2019. |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 3234.24 |  | Approved no of units |  | Flats =84 & shop = 4
Approved no of Floors |  | Blg No.1 & 2 = G + 1st to 4th Floor |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details:
Stage of construction - Bldg No.1: Plinth & RCC upto 4th slab work completed. Other work in process……..
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 100%
|  | RCC |  |  | 80%
|  | Brick |  |  | 0%
|  | Plaster |  |  | 0%
|  | Flooring |  |  | 0%
|  | Painting & Wooden Work |  |  | 0%
|  | Finishing |  |  | 0%
% Progress |  |  | 42% |  | % Disbursement |  |  | 54%
Stage of construction - Bldg No.2 : Work not yet started.
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 0%
|  | RCC |  |  | 0%
|  | Brick |  |  | 0%
|  | Plaster |  |  | 0%
|  | Flooring |  |  | 0%
|  | Painting & Wooden Work |  |  | 0%
|  | Finishing |  |  | 0%
% Progress |  |  | 0% |  | % Disbursement |  |  | 0%
Construction details: |  | Building No.1 = G + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% |  | 90% |  | 95% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 4
Construction details: |  | Building No. 2 = G + 1st to 4th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process |  | 2
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed |  | 4
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500 |  |  |  | 3500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6000 |  |  |  | 6000
Society Charges, Electric Meter Connection | [5 empty] | 65,000/-
Development Charges | [5 empty] | 75,000/-
Recommended rate of Parking | [5 empty] | 50000/-
Distressed valuation of the Property | [5 empty] | 2800
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Blg No.1 |  | 4 | 381.2609 |  |  | 571.8913 |  |  |  | 32924.6272
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Blg No.1 |  | 42 | 16440.9336 |  |  | 23839.3537
Blg No.2 |  | 42 | 16102.4327 |  |  | 23348.5274
Total |  | 84 | 32543.3663 |  |  | 47187.8811
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1
Ground Floor for Parking , Commercial & Residential
1 |  | Shop | 106.6712 |  | 0 | 160.0069 | N | Ground Floor |  | 960041.16
2 |  | Shop | 83.9592 |  | 0 | 125.9388 | N |  |  | 755632.8
3 |  | Shop | 83.9592 |  | 0 | 125.9388 | N |  |  | 755632.8
4 |  | Shop | 106.6712 |  | 0 | 160.0069 | N |  |  | 960041.16
1 |  | 1RK | 261.4576 |  | 0 | 379.1135 | N |  |  | 1326897.117
2 |  | 1RK | 246.9262 |  | 0 | 358.0429 | N |  |  | 1253150.262
1st To 4th Floor
1 |  | 2BHK | 575.5242 |  | 0 | 834.51 | N | 1st To 4th Floor |  | 2670432.1488 | 1.45
2 |  | 1BHK | 385.2974 |  | 0 | 558.6812 | N |  |  | 1787779.8432
3 |  | 1BHK | 389.6568 |  | 0 | 565.0024 | N |  |  | 1808007.552
4 |  | 1BHK | 389.6568 |  | 0 | 565.0024 | N |  |  | 1808007.552
5 |  | 1BHK | 385.2974 |  | 0 | 558.6812 | N |  |  | 1787779.8432
6 |  | 1BHK | 385.2974 |  | 0 | 558.6812 | N |  |  | 1787779.8432
7 |  | 1BHK | 370.9274 |  | 0 | 537.8448 | N |  |  | 1721103.3216
8 |  | 1BHK | 370.9274 |  | 0 | 537.8448 | N |  |  | 1721103.3216
9 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N |  |  | 1694882.2176
10 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N |  |  | 1694882.2176
Building No.2
Ground Floor for Residential & Parking
1 |  | 1RK | 261.4576 |  | 0 | 379.1135 | N | Ground Floor
2 |  | 1BHK | 327.3332 |  | 0 | 474.6332 | N
3 |  | 1RK | 217.3252 |  | 0 | 315.1215 | N
1st To 3rd Floor
1 |  | 2BHK | 575.5242 |  | 0 | 834.51 | N | 1st To 3rd Floor
2 |  | 1BHK | 391.7558 |  | 0 | 568.0459 | N
3 |  | 1BHK | 389.6568 |  | 0 | 565.0024 | N
4 |  | 1BHK | 389.6568 |  | 0 | 565.0024 | N
5 |  | 1BHK | 385.2974 |  | 0 | 558.6812 | N
6 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N
7 |  | 1BHK | 370.9274 |  | 0 | 537.8448 | N
8 |  | 1BHK | 370.9274 |  | 0 | 537.8448 | N
9 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N
10 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N
4th Floor (Part Terrace Area)
1 |  | 1BHK | 385.2974 |  | 0 | 558.6812 | N | 4th Floor
2 |  | 1BHK | 389.6568 |  | 0 | 565.0024 | N
3 |  | 1BHK | 389.6568 |  | 0 | 565.0024 | N
4 |  | 1BHK | 385.2974 |  | 0 | 558.6812 | N
5 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N
6 |  | 1BHK | 370.9274 |  | 0 | 537.8448 | N
7 |  | 1BHK | 370.9274 |  | 0 | 537.8448 | N
8 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N
9 |  | 1BHK | 365.2763 |  | 0 | 529.6507 | N
Remarks:
1. Building No.1 = Lift work is pending. Building No.2 = Work not yet started. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + W.S Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Since Building No.2 have received CC on 01/01/2019, but as of construction work is not started. 8. On site we met Watchmen : 8180005236. As per RERA, completion period of project Sai Krishna Aanandi is expired on 30/10/2023 but still project is incompleted. 7. On site, we meet Mr.Binay (Site Supervisor) - 9022273487. | [10 empty] | 20000
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report Prepared By : |  |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sai Krishna Aanandi
Google Map :
Wing C
Wing B
Wing C
Wing B

## B1 - C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 4 | 80% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 32 | 0 | 0 | 0 | 0 | 0
RCC | 32 | 24 |  | Recommended |  | 30 | 24 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 42% | 54% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2 - C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 0 | 0%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 0 | 20 |  | Progress |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 0% | 20% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-10-14 | Pratiksha

## Valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Sai Krishna Aanandi |  |  |  |  | 55800000
Magic Brick | [5 empty] | 120000000
Magic Brick | [5 empty] | 76300000
Magic Brick | [5 empty] | 118500000
Magic Brick | [5 empty] | 139000000
99 Acres | [5 empty] | 77400000
99 Acres | [5 empty] | 86300000
Average |  |  |  |  | #DIV/0!
Valuation Adopted |  |  |  |  | 32000

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.05 | 3.25 | 9.9125 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 106.6981 | 9.9125 |  |  | 0 | 0 |  | 0 | 0
|  |  | 106.6981 | 9.9125