## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | Shristhi Developers
Name of the builder company |  |  |  | Shristhi Developers
Name of the Project |  |  |  | Riverside
Provided Contact Details ( Name & Contact No.) |  |  |  | 9082645403
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Ankush : 9082645403 |  |  |  | Mr. Sameer 9082645403
Name / No of the Building |  |  |  | Riverside - Nest Building
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000045602
Project location details |  | Riverside, Survey No.43/1/5, near Kamdhenu Lifespaces Gardenia, Internal Road, Ghotkamp Koyana Vele, Koyanavele, Taloja, Panvel, Raigad - 410208.
Survey No |  | 43/1/5
Locality |  | Ghotkamp Koyana Vele
Road |  | Internal Road |  | Locality/Village |  | Koyanavele
City |  | Taloja |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Kamdhenu Lifespaces Gardenia |  | Distance from city centre: |  | 3.9KM from Taloja Panchand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Cemetery/Taloje River
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Internal Rd
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.0812048,73.1072428
Location Link |  | https://goo.gl/maps/6e3WvhkkiEYt3Ls18
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5810
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.72
Total FSI availaible for the project |  |  |  | 2.82
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 16384.3
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | PMP/NRV/16152/JK/949-1/2022 |  |  | Dated | 2022-03-31
Approved Floor plan No. |  | PMP/NRV/16152/JK/949-1/2022 |  |  | Dated | 2022-03-31
Commencement-CC No Valid Up to: |  | PMC/TP/Koyanavele/43/1/5/21-22/16152/949/1/2022 |  |  | Dated | 2022-03-31
St/Gr + 1st to 13th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 16384.3
Approved no of units |  |  | Flats - 325
Approved no of Floors |  |  | St/Gr + 1st to 13th Floor
Proposed no of Floors |  |  | St/Gr + 1st to 13th Floor
St/Gr + 1st to 13th Floor
C Wing = G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/05/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Part I (Flat No. 1 to 6 & 19 to 25) = St/Gr + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 12 Floor Completed | , Painting upto 12 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 12 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 89.62% |  | 95% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 92.31% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | Part II (Flat No. 7 to 18) = St/Gr + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 5 Floor, Painting upto 5 Floor Completed | , External Plaster upto 12 Floor, Flooring upto 5 Floor, Painting upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 5 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 80% |  | 91.54% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 92.31% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 38.46% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 38.46% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | C Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction Average Of Part I & II |  | Progress : |  | 84.81% | Disbursement : |  | 93.27%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5800
Development Charges |  |  |  |  | 100000
Society Formation Charges |  |  |  |  | 75000
Other Charges |  |  |  |  | 100000
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4640
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 325 |  | 149179.0564 |  | 223768.5846
Total
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Ground Floor For Parking | [8 empty] | 10.764
1st to 7th, 9th to 11th & 13th Floor For Residential
1 |  | 1BHK | 419.1771 | 0 | 628.7656 | 1st to 7th, 9th to 11th & 13th Floor For Residential |  | 31.8773 | 4.87 | 4023200
2 |  | 1BHK | 419.1771 | 0 | 628.7656 |  |  | 4755.3492
3 |  | 1BHK | 419.1771 | 0 | 628.7656 |  |  | 6870.6048
4 |  | 1BHK | 419.1771 | 0 | 628.7656
5 |  | 1BHK | 419.1771 | 0 | 628.7656
6 |  | 1BHK | 419.1771 | 0 | 628.7656
7 |  | 1BHK | 419.1771 | 0 | 628.7656
8 |  | 1BHK | 419.1771 | 0 | 628.7656
9 |  | 1BHK | 419.1771 | 0 | 628.7656
10 |  | 1BHK | 419.1771 | 0 | 628.7656
11 |  | 1BHK | 419.1771 | 0 | 628.7656
12 |  | 1BHK | 419.1771 | 0 | 628.7656
13 |  | 1BHK | 419.1771 | 0 | 628.7656
14 |  | 1BHK | 419.1771 | 0 | 628.7656
15 |  | 1BHK | 419.1771 | 0 | 628.7656
16 |  | 2BHK | 585.1579 | 0 | 877.7369 |  |  | 4841.9975 | 6876.7757
17 |  | 2BHK | 585.1579 | 0 | 877.7369 |  |  | 4827553.0875 | 5266421.55 | 6876.7757
18 |  | 1BHK | 419.1771 | 0 | 628.7656 |  |  | 3458210.8275 | 3772593.63 | 6870.6048
19 |  | 1BHK | 419.1771 | 0 | 628.7656
20 |  | 2BHK | 585.1579 | 0 | 877.7369 |  |  | 6038.2557
21 |  | 2BHK | 585.1579 | 0 | 877.7369
22 |  | 2BHK | 585.1579 | 0 | 877.7369
23 |  | 2BHK | 585.1579 | 0 | 877.7369
24 |  | 1BHK | 419.1771 | 0 | 628.7656
25 |  | 1BHK | 419.1771 | 0 | 628.7656
8th & 12th Floor (Part Refuge Balcony Area)
1 |  | 1BHK | 419.1771 | 0 | 628.7656 | 8th & 12th Floor (Part Refuge Balcony Area) |  | 35.7078
2 |  | 1BHK | 419.1771 | 0 | 628.7656
3 |  | 1BHK | 419.1771 | 0 | 628.7656 |  |  | 6361.6711
4 |  | 1BHK | 419.1771 | 0 | 628.7656
5 |  | 1BHK | 419.1771 | 0 | 628.7656
6 |  | 1BHK | 419.1771 | 0 | 628.7656
7 |  | 1BHK | 419.1771 | 0 | 628.7656
8 |  | 1BHK | 419.1771 | 0 | 628.7656
9 |  | 1BHK | 419.1771 | 0 | 628.7656
10 |  | 1BHK | 419.1771 | 0 | 628.7656
11 |  | 1BHK | 419.1771 | 0 | 628.7656
12 |  | 1BHK | 419.1771 | 0 | 628.7656
13 |  | 1BHK | 419.1771 | 0 | 628.7656
14 |  | 1BHK | 419.1771 | 0 | 628.7656
15 |  | 1BHK | 419.1771 | 0 | 628.7656
16 |  | 2BHK | 585.1579 | 0 | 877.7369
17 |  | 2BHK | 585.1579 | 0 | 877.7369
18 |  | 1BHK | 419.1771 | 0 | 628.7656
19 |  | 1BHK | 419.1771 | 0 | 628.7656
20 |  | 2BHK | 585.1579 | 0 | 877.7369
21 |  | 2BHK | 585.1579 | 0 | 877.7369
22 |  | 2BHK | 585.1579 | 0 | 877.7369
23 |  | 2BHK | 585.1579 | 0 | 877.7369
24 |  | 1BHK | 419.1771 | 0 | 628.7656
25 |  | 1BHK | 419.1771 | 0 | 628.7656
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | The Cementry of Hindu is located 30m from the west side of the project.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Riverside
Layout :
Google Map :
Taloje River
Taloje River
Cemetery
PART - 2
PART - 2
PART - 1
PART - 1
PART - 1
PART - 2
PART - 2
PART - 2
Part I
Part I
Part II
Part II
Part II
Part II

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted