## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | Sri Venkateshwara Builders
Name of the builder company |  |  |  | Sri Venkateshwara Builders
Name of the Project |  |  |  | Sai Shri Narayana |  |  |  |  | Building No. 2 Wing B Extra construction given till 23/04/2024
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Zubair Khan 9372537476
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Patel : 9892212203
Name / No of the Building |  |  |  | Building No. 1 (Wing A, B, C & D) & Building No. 2 (Wing A, B & C)
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000035119
Project location details |  | Sai Shri Narayana, Survey No.63/4, near Jijai Angan, Internal Rd, Taloja, Ghot, Panvel, Panvel, Raigad - 410208.
Survey No |  | 63/4
Locality |  | Taloja
Road |  | Internal Rd |  | Locality/Village |  | Ghot
City |  | Panvel |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Jijai Angan |  | Distance from city centre: |  | 4.2KM from Taloja Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Arihant Anshula
West | NA | NA |  |  | Iinternal Rd/Open Plot
North | NA | NA |  |  | Open Plot/ Lake
South | NA | NA |  |  | Jijaji Angan
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.085187,73.110579
Location Link |  | https://goo.gl/maps/Ab4dfTycUVfJLGsP7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5504.995
Permissible FSI |  |  |  | 1.6
Permissible TDR/Paid FSI |  |  |  | 0.88246
Total FSI availaible for the project |  |  |  | 2.4825
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13665.943
Total number of Buildings |  |  |  | 07 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | J.K./PMP/NRV/15984/J.K.408/2022 |  |  | Dated | 2022-02-21
Approved Floor plan No. |  | J.K./PMP/NRV/15984/J.K.408/2022 |  |  | Dated | 2022-02-21
Commencement-CC No Valid Up to: |  | PMC/TP/Ghot/63/4/21-22/15984/ 408/2022 |  |  | Dated | 2022-02-21
Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 13665.943
Approved no of units |  |  | Flats -257, Shops -16
Approved no of Floors |  |  | Building No. 1 Wing A & B = Gr + 1st to 6th Floor Building No. 1 Wing C & D = Gr + 1st to 7th Floor Building No. 2 Wing A, B & C = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building No. 1 Wing A & B = Gr + 1st to 7th Floor
Building No. 1 Wing C & D = Gr + 1st to 7th Floor
Building No. 2 Wing A & B= Gr + 1st to 7th Floor
Building No. 2 Wing C = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Garden, Shopping Center, Fitness Center, Club House, Children Play Area, Power Backup
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 1 Wing A & B = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 5 Floor, Internal Plaster upto 5 Floor Completed | , RCC upto 7 Slab, Brickwork upto 5 Floor, Internal Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 5 Floor, Internal Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 55.71% |  | 78.39% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 7 | 87.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 5 | 71.43% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 71.43% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 1 Wing B = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 15% |  | 48.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 1 | 12.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 1 Wing C = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 3 Floor Completed | , Internal Plaster upto 6 Floor, External Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 68.21% |  | 86.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 42.86% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 1 Wing D = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor Completed | , External Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 72.14% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 2 Wing A = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3 Floor, Painting upto 3 Floor Completed | , Flooring upto 3 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 81.43% |  | 92.14% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 42.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 42.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 2 Wing B = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 4 Floor, Painting upto 1 Floor Completed | , External Plaster upto 4 Floor, Painting upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 4 Floor, Painting upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 71.43% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 57.14% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 14.29% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 2 Wing C = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Painting upto 3 Floor Completed | , Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 77.14% |  | 90% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 42.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4600 |  |  | 4500 to 4600 on 27/02/2025 & 2.5L OC Charegs & 2.5L Parking added on 03/02/2025 Cost Sheet by smith
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft. | [8 empty] | 4500
Floor Rise Rate
Development Charges |  |  |  |  | 125000
Club Charges |  |  |  |  | 75000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 3680
Commercial Area Details : Building No. 1 | [8 empty] | Cost Sheet
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 4500 | 4402.9851 | 4029.8507
Building No. 1 | Wing A | 9 |  | 1601.737 |  | 2562.7792 |  |  |  | 4411.7647
| Wing B | 7 |  | 1323.4338 |  | 2117.4941 |  |  |  | 4420.2899
Total |  | 16 |  | 2925.1708 |  | 4680.2733 |  |  |  | 4387.7551
Residential Area Details : | [9 empty] | 4405.9406
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  | 4405.7471
Building No. 1 | Wing A | 24 |  | 14608.9008 |  | 24240
| Wing B | 36 |  | 15823.7258 |  | 26100
| Wing C | 42 |  | 18433.1347 |  | 30450 |  | https://www.propertypistol.com/projects/d87f5b2e-bb5e-42b2-8695-c3d6f8855702/sai-shri-narayana-by-sri-venkateshwara-builders-in-taloja
| Wing D | 42 |  | 18957.1801 |  | 30800
Building No. 2 | Wing A | 53 |  | 22215.3352 |  | 36570
| Wing B | 30 |  | 12554.3223 |  | 20700
| Wing C | 30 |  | 12554.3223 |  | 20700
Total |  | 257 |  | 115146.9212 |  | 189560
Grand Total |  | 273 |  | 118072.0921 |  | 194240.2733
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Building No. 1
Wing A
Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
1 |  | Shop | 258.3629 | 0 | 413.3807 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking |  |  | 10.764
2 |  | Shop | 177.3638 | 0 | 283.7821 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
3 |  | Shop | 161.0294 | 0 | 257.6471 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
4 |  | Shop | 171.4705 | 0 | 274.3528 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
5 |  | Shop | 100.751 | 0 | 161.2017 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
6 |  | Shop | 185.0332 | 0 | 296.0531 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
7 |  | Shop | 161.0294 | 0 | 257.6471 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
8 |  | Shop | 175.9914 | 0 | 281.5862 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
9 |  | Shop | 210.7053 | 0 | 337.1285 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
Wing B
Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
10 |  | Shop | 210.7053 | 0 | 337.1285 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
11 |  | Shop | 154.3558 | 0 | 246.9692 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
12 |  | Shop | 186.4863 | 0 | 298.3781 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
13 |  | Shop | 230.0805 | 0 | 368.1288 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
14 |  | Shop | 148.3548 | 0 | 237.3677 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
15 |  | Shop | 158.3115 | 0 | 253.2984 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
16 |  | Shop | 235.1396 | 0 | 376.2233 | Ground Floor For Entrance Lobby, Commercial, Meter Room, & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No. 1
Wing A
1st Floor For Residential | [8 empty] | 10.764
1 |  | 2BHK | 608.7042 | 73.8949 | 1010 | 1st Floor For Residential
2 |  | 2BHK | 608.7042 | 73.8949 | 1010 | 1st Floor For Residential
3 |  | 2BHK | 608.7042 | 100.751 | 1010 | 1st Floor For Residential |  |  | 6.865
4 |  | 2BHK | 608.7042 | 0 | 1010 | 1st Floor For Residential
2nd to 6th Floor | [8 empty] | 10.764
1 |  | 2BHK | 608.7042 | 0 | 1010 | 2nd to 6th Floor
2 |  | 2BHK | 608.7042 | 0 | 1010 | 2nd to 6th Floor
3 |  | 2BHK | 608.7042 | 0 | 1010 | 2nd to 6th Floor |  |  | 6.865
4 |  | 2BHK | 608.7042 | 0 | 1010 | 2nd to 6th Floor
Wing B
1st Floor For Residential | [8 empty] | 10.764
1 |  | 1BHK | 405.749 | 0 | 680 | 1st Floor For Residential |  | 4116.1765 | 5000
2 |  | 1BHK | 413.6336 | 0 | 680 | 1st Floor For Residential |  | 4116.1765 | 5000
3 |  | 2BHK | 590.2978 | 0 | 980 | 1st Floor For Residential |  | 4182.6531 | 4285.7143
4 |  | 1BHK | 408.7629 | 0 | 670 | 1st Floor For Residential
5 |  | 1BHK | 410.3102 | 0 | 670 | 1st Floor For Residential
6 |  | 1BHK | 408.5342 | 0 | 670 | 1st Floor For Residential
2nd to 6th Floor | [8 empty] | 10.764
1 |  | 1BHK | 405.749 | 0 | 680 | 2nd to 6th Floor
2 |  | 1BHK | 413.6336 | 0 | 680 | 2nd to 6th Floor
3 |  | 2BHK | 590.2978 | 0 | 980 | 2nd to 6th Floor
4 |  | 1BHK | 408.7629 | 0 | 670 | 2nd to 6th Floor
5 |  | 1BHK | 410.3102 | 0 | 670 | 2nd to 6th Floor
6 |  | 1BHK | 408.5342 | 0 | 670 | 2nd to 6th Floor
Wing C
Ground Floor For Society Office, Meter Room, Driver Room & Parking
1st Floor For Residential | [8 empty] | 10.764
1 |  | 1BHK | 408.5342 | 0 | 670 | 1st Floor For Residential
2 |  | 1BHK | 410.3102 | 0 | 670 | 1st Floor For Residential
3 |  | 1BHK | 408.7629 | 0 | 670 | 1st Floor For Residential
4 |  | 2BHK | 591.9124 | 0 | 980 | 1st Floor For Residential
5 |  | 1BHK | 406.8927 | 0 | 680 | 1st Floor For Residential
6 |  | 1BHK | 406.8927 | 0 | 680 | 1st Floor For Residential
2nd to 7th Floor | [8 empty] | 10.764
1 |  | 1BHK | 408.5342 | 0 | 670 | 2nd to 7th Floor
2 |  | 1BHK | 410.3102 | 0 | 670 | 2nd to 7th Floor
3 |  | 1BHK | 408.7629 | 0 | 670 | 2nd to 7th Floor
4 |  | 2BHK | 591.9124 | 0 | 980 | 2nd to 7th Floor
5 |  | 1BHK | 406.8927 | 0 | 680 | 2nd to 7th Floor
6 |  | 1BHK | 406.8927 | 0 | 680 | 2nd to 7th Floor
Wing D
Ground Floor For Entrance Lobby, Meter Room & Parking
1st Floor For Residential | [8 empty] | 10.764
1 |  | 1BHK | 421.2222 | 0 | 680 | 1st Floor For Residential
2 |  | 1BHK | 421.2222 | 0 | 680 | 1st Floor For Residential
3 |  | 1BHK | 417.993 | 0 | 680 | 1st Floor For Residential
4 |  | 1BHK | 421.2222 | 0 | 680 | 1st Floor For Residential
5 |  | 2BHK | 613.1982 | 0 | 1010 | 1st Floor For Residential
6 |  | 1BHK | 413.3107 | 0 | 670 | 1st Floor For Residential
2nd to 7th Floor | [8 empty] | 10.764
1 |  | 1BHK | 421.2222 | 0 | 680 | 2nd to 7th Floor
2 |  | 1BHK | 421.2222 | 0 | 680 | 2nd to 7th Floor
3 |  | 1BHK | 417.993 | 0 | 680 | 2nd to 7th Floor
4 |  | 1BHK | 421.2222 | 0 | 680 | 2nd to 7th Floor
5 |  | 2BHK | 613.1982 | 0 | 1010 | 2nd to 7th Floor
6 |  | 1BHK | 413.3107 | 0 | 670 | 2nd to 7th Floor
Building No. 2
Wing A
Ground Floor For Entrance Lobby, Residential & Parking
1 |  | 1BHK | 418.4774 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
2 |  | 1BHK | 421.6528 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
3 |  | 1BHK | 419.3654 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
4 |  | 1BHK | 419.3654 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
1st to 7th Floor
1 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
2 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
3 |  | 1BHK | 419.3654 | 0 | 690 | 1st to 7th Floor
4 |  | 1BHK | 419.3654 | 0 | 690 | 1st to 7th Floor
5 |  | 1BHK | 419.3654 | 0 | 690 | 1st to 7th Floor
6 |  | 1BHK | 419.3654 | 0 | 690 | 1st to 7th Floor
7 |  | 1BHK | 419.3654 | 0 | 690 | 1st to 7th Floor
Wing B
Ground Floor For Entrance Lobby, Residential & Parking
1 |  | 1BHK | 418.4774 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
2 |  | 1BHK | 418.4774 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
1st to 7th Floor
1 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
2 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
3 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
4 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
Wing C
Ground Floor For Entrance Lobby, Residential & Parking
1 |  | 1BHK | 418.4774 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
2 |  | 1BHK | 418.4774 | 0 | 690 | Ground Floor For Entrance Lobby, Residential & Parking
1st to 7th Floor
1 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
2 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
3 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
4 |  | 1BHK | 418.4774 | 0 | 690 | 1st to 7th Floor
Remarks:
* | Wing 1A & 1B = Construction work is in process at the time of visit. Wing 1C, 1D & 2A, 2B, 2C = Construction work is in process at the time of Visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 03/02/2025 & 27/02/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sai Shri Narayana
Layout :
Google Map :
Formulas:
Ghot = [Ghot, row above]
BLDG No. 1
Wing A
BLDG No. 1
Wing B
BLDG No. 1
Wing C
BLDG No. 1
Wing D
BLDG No. 2
Wing C
BLDG No. 2
Wing B
BLDG No. 2
Wing A
BLDG No. 2
Wing C
BLDG No. 2
Wing B
Bldg - 1 B
Bldg - 1 C
Bldg - 1 D
Bldg - 2 A
Bldg - 2 B
Bldg - 2 C
Bldg - 1 A
Bldg - 1 B
Bldg - 1 C
Bldg - 1 D
Bldg - 2B
Bldg - 2A
Bldg - 2C
Bldg - 1 A
Bldg - 1 C
Bldg - 1 C
Bldg - 2 A
Bldg - 2B
Bldg - 2C
Bldg - 2 A
Bldg - 1 A
Bldg - 1A
Bldg - 1A
Bldg - 1A
Bldg - 1B
Bldg - 1C
Bldg - 1D
Bldg - 2A
Bldg - 2A
Bldg - 2B
Bldg - 2B
Bldg - 2C
Bldg - 1A
Bldg - 1A
Bldg - 1A
Bldg - 1B
Bldg - 1B
Bldg - 1C
Bldg - 1D
Bldg - 2A
Bldg - 2A
Bldg - 2B
Bldg - 2B
Bldg - 2C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted