## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | M/s.Anand Associates
Name of the builder company |  |  |  | M/s.Anand Associates
Name of the Project |  |  |  | Saket World
Contact Details ( Name & Contact No.) |  |  |  | 8652304304
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Ms. Priyanka 8291130877 & Ms. Rashmi : 9070500200
Name / No of the Building |  |  |  | Building Type A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | Building Type A = P51700024797 Building Type B = P51700030224 Building Type C = P51700032180
Project location details |  | Saket World, Survey No.15, 16/6A, 17/2A of village Pisavali & S.No.58/5A & 5A of village Tisgaon, Malangad Road, Pisavali, Tisgaon, Thane.
Survey No |  | 15, 16/6A, 17/2A of village Pisavali & S.No.58/5A & 5A of village Tisgaon
Road |  | Malangad Road |  | Locality/Village |  | Pisavali, Tisgaon
City |  | Kalyan East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421306
Near by Landmark |  | Godavari Apartment |  | Distance from city centre: |  | 3.7Km from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Building
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.218689,73.1268511
Location Link |  | https://goo.gl/maps/zcKHAKZzEsWei21RA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6167.4
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1212
Total FSI availaible for the project |  |  |  | 2.2212
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13698.95
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Layout Approval No Building Type A |  | KDMC/TPP/BP/27Village/2018-19/15/72 |  |  | Dated | 31/05/2021.
Approved Floor plan No. Building Type A |  | KDMC/TPP/BP/27Village/2018-19/15/72 |  |  | Dated | 31/05/2021.
Layout Approval No Building Type B & C |  | KDMC/TPD/BP/27Village/2018-19/15/337 |  |  | Dated | 2021-11-03
Approved Floor plan No. Building Type B & C |  | KDMC/TPD/BP/27Village/2018-19/15/337 |  |  | Dated | 2021-11-03
Commencement Certificate No. |  | KDMC/TPD/BP/27Village/2018-19/15/337 |  |  | Dated | 2021-11-03
Valid Up to: Building Type A, B, C = Stilt + 1st to 22nd Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 13698.95
Approved no of units |  |  | Sale Flats - 392, Mhada Flats - 44
Approved no of Floors |  |  | Building Type A, B, C = Stilt + 1st to 4th Floor (MHADA) + 5th to 22nd Floor
Proposed no of Floors |  |  | Building Type A - Stilt + (1st to 4th Floor - MHADA) + 5th to 22nd Floor
Building Type B - Stilt + (1st to 4th Floor - MHADA) + 5th to 22nd Floor
Building Type C - Stilt + (1st to 4th Floor - MHADA) + 5th to 22nd Floor
Expected Completion |  |  | As per RERA - Building Type A - Completed Building Type B (31/12/2026) Building Type C (30/06/2027) |  |  |  |  | (30/06/2026)
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc.
Construction details: |  | Building Type A - Stilt + (1st to 4th Floor - MHADA) + 5th to 22nd Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received. |  |  |  | a b c g+23 per wing 3 lift per floor a c 8 b 6 a wing rcc Breck work plaster in out complete kitchen platform bathroom style flooring doors complete doors and plumbing elc work working progress b rcc Breck work plaster in out complete kitchen platform bathroom style plumbing elc work working progress c wing 10 th slap complete4 th floor Breck work completed total 3 wing working progress poss 2025/26/27 side meet Sudeep Ghosh 7977663174 direct visit complete internal visit photos not allowed side person
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 100% |  | 100% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 22 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 22 | 100% |  |  |  |  | Plinth in process | 16.5
Possession |  | 22 | 100% |  |  |  |  | Plinth completed | 22
Construction details: |  | Building Type B - Stilt + (1st to 4th Floor - MHADA) + 5th to 22nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 16 Floor, Painting upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 16 Floor, Painting upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 83.41% |  | 93.64% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 16 | 72.73% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 22.73% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Building Type C - Stilt + (1st to 4th Floor - MHADA) + 5th to 22nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 11 Floor, External Plaster upto 8 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 11 Floor, External Plaster upto 8 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 64.89% |  | 84.32% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 11 | 50% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 36.36% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Sale flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7000 |  |  | 6000 to 7000 | Abhishek | Cost sheet | 2022-09-19
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Maintainace Charges |  |  |  |  | 100000/-
Legal Charges |  |  |  |  | 10,000/-
Infra Charges |  |  |  |  | 3,00,000/-
Recommended rate of Parking |  |  |  |  | 5,00,000/-
Distressed valuation of the Property |  |  |  |  | 5600
Sale Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Building Type A (Sale Flat) |  | 144 | 77559.41 |  | 122771.3584
Building Type B (Sale Flat) |  | 104 | 54612.042 |  | 81918.063
Building Type C (Sale Flat) |  | 144 | 74393.8898 |  | 115252.7475
Total |  | 392 | 206565.3418 |  | 319942.169
Building Type A (Mhada Flat) |  | 15 | 8087.2892 |  | 12130.9338
Building Type B (Mhada Flat) |  | 4 | 2692.7491 |  | 62139.6167
Building Type C (Mhada Flat) |  | 25 | 13122.9467 |  | 19684.4201
Total |  | 44 | 23902.9851 |  | 93954.9706
Building details Floor Wise
Details of Flats in Building
Flat Type | Flat No. | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Building Type A
Stilt Floor For Parking
1st Floor For Parking & Residential
Mhada | 1 | 2BHK | 540.3259 | 0 | 810.4888 | 1st Floor
Mhada | 2 | 1BHK | 557.7636 | 0 | 836.6454
Mhada | 3 | 1BHK | 587.1493 | 0 | 880.7239
Mhada | 4 | Double Height Entrance Lobby
2nd & 4th Floor For Parking & Residential
Mhada | 1 | 2BHK | 540.3259 | 0 | 810.4888 | 2nd & 4th Floor |  | 8019.8514
Mhada | 2 | 1BHK | 557.7636 | 0 | 836.6454 |  |  | 5378.6231
Mhada | 3 | 1BHK | 587.1493 | 0 | 880.7239 |  |  | 5109.4331
Mhada | 4 | 1BHK | 448.7781 | 0 | 673.1671
3rd Floor For Parking & Residential
Mhada | 1 | 2BHK | 540.3259 | 0 | 810.4888 | 3rd Floor For Parking & Residential
Mhada | 2 | 1BHK | 557.7636 | 0 | 836.6454
Mhada | 3 | 1BHK | 587.1493 | 0 | 880.7239
Mhada | 4 | 1BHK | 448.7781 | 0 | 673.1671
5th Floor (Part Garden Area)
1 | 1 | 1BHK | 448.8857 | 56.8339 | 730.1625 | 5th Floor
2 | 2 | 2BHK | 688.1425 | 67.8132 | 1100.027 |  |  | 5908.946
3 | 3 | 2BHK | 688.1425 | 237.0233 | 1150.7254 |  |  | 5648.6108
4 | 4 | 1BHK | 448.8857 | 221.7384 | 784.1978
5 | 5 | 1BHK | 448.8857 | 221.7384 | 784.1978
6 | 6 | 1BHK | 448.8857 | 221.7384 | 784.1978
7 | 7 | 2BHK | 688.1425 | 67.8132 | 1100.027
8 | 8 | 1BHK | 448.8857 | 56.8339 | 730.1625
6th, 8th, 10th, 12th, 14th, 16th, 18th Floor
1 | 1 | 1BHK | 448.8857 | 0 | 673.3286 | 6th, 8th, 10th, 12th, 14th, 16th, 18th Floor
2 | 2 | 2BHK | 688.1425 | 67.8132 | 1100.027
3 | 3 | 2BHK | 688.1425 | 67.8132 | 1100.027
4 | 4 | 1BHK | 448.8857 | 0 | 673.3286
5 | 5 | 1BHK | 448.8857 | 0 | 673.3286
6 | 6 | 1BHK | 448.8857 | 0 | 673.3286
7 | 7 | 2BHK | 688.1425 | 67.8132 | 1100.027
8 | 8 | 1BHK | 448.8857 | 0 | 673.3286
7th, 9th, 11th, 13th, 15th, 17th Floor
1 | 1 | 1BHK | 448.8857 | 56.8339 | 730.1625 | 7th, 9th, 11th, 13th, 15th, 17th Floor
2 | 2 | 2BHK | 688.1425 | 67.8132 | 1100.027
3 | 3 | 2BHK | 688.1425 | 67.8132 | 1100.027
4 | 4 | 1BHK | 448.8857 | 56.8339 | 730.1625
5 | 5 | 1BHK | 448.8857 | 56.8339 | 730.1625
6 | 6 | 1BHK | 448.8857 | 56.8339 | 730.1625
7 | 7 | 2BHK | 688.1425 | 67.8132 | 1100.027
8 | 8 | 1BHK | 448.8857 | 56.8339 | 730.1625
19th & 21st Floor
1 | 1 | 1BHK | 448.8857 | 56.8339 | 730.1625 | 19th & 21st Floor
2 | 2 | 2BHK | 688.1425 | 67.8132 | 1100.027
3 | 3 | 2BHK | 688.1425 | 67.8132 | 1100.027
4 | 4 | 1BHK | 448.8857 | 56.8339 | 730.1625
5 | 5 | 1BHK | 448.8857 | 56.8339 | 730.1625
6 | 6 | 1BHK | 448.8857 | 56.8339 | 730.1625
7 | 7 | 2BHK | 688.1425 | 67.8132 | 1100.027
8 | 8 | 1BHK | 448.8857 | 56.8339 | 730.1625
20th & 22nd Floor
1 | 1 | 1BHK | 448.8857 | 0 | 673.3286 | 20th & 22nd Floor
2 | 2 | 2BHK | 688.1425 | 67.8132 | 1100.027
3 | 3 | 2BHK | 688.1425 | 67.8132 | 1100.027
4 | 4 | 1BHK | 448.8857 | 0 | 673.3286
5 | 5 | 1BHK | 448.8857 | 0 | 673.3286
6 | 6 | 1BHK | 448.8857 | 0 | 673.3286
7 | 7 | 2BHK | 688.1425 | 67.8132 | 1100.027
8 | 8 | 1BHK | 448.8857 | 0 | 673.3286
Building Type B
Stilt Floor For Parking
1st Floor For Parking & Residential
Mhada | 1 | 1RK | 471.3825 | 0 | 707.0737 | 1st Floor
2nd Floor For Parking & Residential
Mhada | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 2nd Floor
3rd Floor For Parking & Residential
Mhada | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 3rd Floor For Parking & Residential
4th Floor For Parking & Residential
Mhada | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 4th Floor For Parking & Residential
5th Floor (Part Garden Area)
1 | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 5th Floor |  | 5852.2531
2 | 2 | 1BHK | 556.6872 | 0 | 835.0308 |  |  | 5389.0231
3 | 3 | 1BHK | 556.6872 | 0 | 835.0308
4 | 4 | 1BHK | 556.6872 | 0 | 835.0308
5 | 5 | 1BHK | 556.6872 | 0 | 835.0308
6 | 6 | 1RK | 351.9828 | 0 | 527.9742
6th, 8th, 9th to 11th, 13th to 16th Floor
1 | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 6th, 8th, 9th to 11th, 13th to 16th Floor
2 | 2 | 1BHK | 477.8409 | 0 | 716.7613
3 | 3 | 1BHK | 477.8409 | 0 | 716.7613
4 | 4 | 1BHK | 477.8409 | 0 | 716.7613
5 | 5 | 1BHK | 477.8409 | 0 | 716.7613
6 | 6 | 1BHK | 477.8409 | 0 | 716.7613
7th & 12th Floor
1 | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 7th & 12th Floor
2 | 2 | 1BHK | 477.8409 | 0 | 716.7613
3 | 3 | 1BHK | 477.8409 | 0 | 716.7613
4 | 4 | 1BHK | 477.8409 | 0 | 716.7613
5 | 5 | 1BHK | 477.8409 | 0 | 716.7613
6 | 6 | Refuge Area
18th to 21th Floor
1 | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 18th to 21th Floor
2 | 2 | 1BHK | 477.8409 | 0 | 716.7613
3 | 3 | 1BHK | 477.8409 | 0 | 716.7613
4 | 4 | 1BHK | 477.8409 | 0 | 716.7613
5 | 5 | 1BHK | 477.8409 | 0 | 716.7613
6 | 6 | 1BHK | 477.8409 | 0 | 716.7613
17th & 22nd Floor
1 | 1 | 2BHK | 740.4556 | 0 | 1110.6833 | 17th & 22nd Floor
2 | 2 | 1BHK | 477.8409 | 0 | 716.7613
3 | 3 | 1BHK | 477.8409 | 0 | 716.7613
4 | 4 | 1BHK | 477.8409 | 0 | 716.7613
5 | 5 | 1BHK | 477.8409 | 0 | 716.7613
6 | 6 | Refuge Area
Building Type C
Stilt Floor For Parking
1st Floor For Residential
Mhada | 1 | 1BHK | 477.8409 | 0 | 716.7613 | 1st Floor
Mhada | 2 | 1BHK | 492.2915 | 0 | 738.4373
Mhada | 3 | 2BHK | 589.8349 | 0 | 884.7524
Mhada | 4 | Double Height Entrance Lobby
Mhada | 5 | 2BHK | 708.5403 | 0 | 1062.8104
Mhada | 6 | 1BHK | 477.1143 | 0 | 715.6715
Mhada | 7 | 1BHK | 477.1143 | 0 | 715.6715
Mhada | 8 | 1BHK | 477.1143 | 0 | 715.6715
2nd Floor For Parking & Residential
Mhada | 1 | Parking Area |  |  |  | 2nd Floor For Parking & Residential
Mhada | 2 | 1BHK | 492.2915 | 0 | 738.4373
Mhada | 3 | 2BHK | 589.8349 | 0 | 884.7524
3rd & 4th Floor For Residential
Mhada | 1 | 1BHK | 477.8409 | 0 | 716.7613 | 3rd & 4th Floor For Residential
Mhada | 2 | 1BHK | 492.2915 | 0 | 738.4373 |  |  | 25
Mhada | 3 | 2BHK | 589.8349 | 0 | 884.7524
Mhada | 4 | 2BHK | 589.5873 | 0 | 884.381
Mhada | 5 | 2BHK | 589.5873 | 0 | 884.381
Mhada | 6 | 1BHK | 477.1143 | 0 | 715.6715
Mhada | 7 | 1BHK | 477.1143 | 0 | 715.6715
Mhada | 8 | 1BHK | 477.1143 | 0 | 715.6715
5th, 6th, 8th to 11th, 13th to 17th, 19th to 22nd Floor
1 | 1 | 1BHK | 477.8409 | 0 | 716.7613 | 5th, 6th, 8th to 11th, 13th to 17th, 19th to 22nd Floor
2 | 2 | 1BHK | 492.2915 | 67.8132 | 806.2505
3 | 3 | 2BHK | 589.8349 | 67.8132 | 952.5656
4 | 4 | 2BHK | 589.5873 | 0 | 884.381
5 | 5 | 2BHK | 589.5873 | 0 | 884.381
6 | 6 | 1BHK | 477.1143 | 0 | 715.6715
7 | 7 | 1BHK | 477.1143 | 67.8132 | 783.4847
8 | 8 | 1BHK | 477.1143 | 0 | 715.6715
7th, 12th & 18th Floor (Part Terrace Area)
1 | 1 | 1BHK | 477.8409 | 0 | 716.7613 | 7th, 12th & 18th Floor (Part Terrace Area)
2 | 2 | 1BHK | 492.2915 | 67.8132 | 806.2505
3 | 3 | 2BHK | 589.8349 | 67.8132 | 952.5656
4 | 4 | 1BHK | 477.1143 | 0 | 715.6715
5 | 5 | 1BHK | 477.1143 | 0 | 715.6715
6 | 6 | 1BHK | 477.1143 | 0 | 715.6715
7 | 7 | 1BHK | 477.1143 | 67.8132 | 783.4847
8 | 8 | 1BHK | 477.1143 | 0 | 715.6715
Remarks:
1. Wing A = All work competed, provide OC. Some flats are occupied by tenants. Wing B = Construction work is in process at the time of Visit. Wing C = Construction work is in process at the time of visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + balcony + C.B Area + W.S Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 8. We have considered Other charges from cost sheet. 9. We update revised approved Plans of Building A & B (on 02/07/2021) 10.We have updated revised approved floor plan & C.C of Building B & C (on 21/12/2021).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Saket World
Google Map :
Formulas:
Pisavali, Tisgaon = [Pisavali, Tisgaon, row above]
Wing A & B
Wing A
C
A
B
C
C

## Note
11/09/2020.

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Saket World | 1BHK | 420 | 630 | 7142.8571 | 4500000
housing | Saket World | 2BHK | 641 | 961.5 | 6760.2704 | 6500000
squareyards. | Saket World | 1BHK | 417 | 625.5 | 7194.2446 | 4500000
squareyards. | Saket World | 1BHK | 424 | 636 | 7193.3962 | 4575000
Average |  |  |  |  | 7072.6921
Valuation Adopted |  |  |  |  | 7100