## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | P.G. Constructions
Name of the builder company |  |  |  | P.G. Constructions
Name of the Project |  |  |  | Precious Harmony NX
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Sachin 8767662233
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Shirke 9854593593
Name / No of the Building |  |  |  | Wing A to D
Docouments Provided |  |  |  | Approved Plans, CC, Cost sheet
RERA No. |  |  |  | P51700049260
Project location details |  | Precious Harmony NX, Survey No.40, Hissa No.1/2, near Siddharth Complex, Sidh Swayambhu Shiv Mandir Road, Katrap, Belavali, Badlapur, Ambernath, Thane - 421503.
Survey No |  | 40, Hissa No.1/2
Locality |  | Katrap
Road |  | Sidh Swayambhu Shiv Mandir Road |  | Locality/Village |  | Belavali
City |  | Badlapur |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Nearby Landmark |  | Siddharth Complex |  | Distance from city centre: |  | 2.8 KM from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Sidh Swayambhu Shiv Mandir Road
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Siddharth Complex
South | NA | NA |  |  | Vastu Swapnapurti Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.1738466,73.2287622
Location Link |  | https://goo.gl/maps/UM4dJfEsdXx1J2y88
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2898
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.8643
Total FSI availaible for the project |  |  |  | 2.9643
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8590.45
Total number of Buildings |  |  |  | 04 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgoan Badlapur Municipal Council
Layout Approval No |  | KBNP/NRV/BP/6126-89 |  |  | Dated | 2022-06-30
Approved Floor plan No. |  | KBNP/NRV/BP/6126-89 |  |  | Dated | 2022-06-30
Commencement-CC No Valid Up to: |  | KBNP/NRV/BP/6126/2022-2023/Unique No.89 |  |  | Dated | 2022-06-30
Wing A, C & D = Gr/Stilt + 1st to 7th Floor Wing B = Stilt + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8590.45
Approved no of units |  |  | Flats - 168, Shops - 11
Approved no of Floors |  |  | Wing A to D = Gr/Stilt + 1st to 7th Floor
Proposed no of Floors |  |  | Wing A & B = Gr/Stilt + 1st to 7th Floor
Wing C = Gr/Stilt + 1st to 7th Floor
Wing D = Gr/Stilt + 1s to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 4 Floor Completed | , External Plaster upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 70.71% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 57.14% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor, Painting upto 1 Floor Completed | , External Plaster upto 5 Floor, Painting upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor, Painting upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 72.86% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 14.29% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing C = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 3 Floor Completed | , Flooring upto 4 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 82.86% |  | 92.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 57.14% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 42.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing D = Gr/Stilt + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Inspection | MIS | Builder sheet | Online
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4300 |  |  | 4329.4454 | 5000 | 4000 | 3988.3361
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000
Other Charges |  |  |  |  | 200000 |  |  | 2L Added by rushikesh on 19/09/2024.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 3440
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 4 |  | 1148.8417 |  | 1838.1468
Wing D |  | 7 |  | 1089.5321 |  | 1743.2513
Total |  | 11 |  | 2238.3738 |  | 3581.3981
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 28 |  | 16883.5579 |  | 24481.1589
Wing B |  | 28 |  | 14246.6491 |  | 20657.6413 |  |  | 130389.5632
Wing C |  | 56 |  | 27508.7712 |  | 39887.7182
Wing D |  | 56 |  | 28814.9288 |  | 41781.6467
Total |  | 168 |  | 87453.907 |  | 126808.1651
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing A
Ground Floor for Commercial & Parking
1 |  | Shop | 238.4226 | 0 | 381.4762 | Ground Floor for Commercial & Parking
2 |  | Shop | 327.0103 | 0 | 523.2165
3 |  | Shop | 327.0103 | 0 | 523.2165
4 |  | Shop | 256.3985 | 0 | 410.2376
Wing D
Ground Floor for Commercial & Parking
1 |  | Shop | 153.1717 | 0 | 245.0748 | Ground Floor for Commercial & Parking
2 |  | Shop | 138.748 | 0 | 221.9967
3 |  | Shop | 181.6963 | 0 | 290.7141
4 |  | Shop | 201.9326 | 0 | 323.0922
5 |  | Shop | 150.4807 | 0 | 240.7692
6 |  | Shop | 125.1853 | 0 | 200.2965
7 |  | Shop | 138.3174 | 0 | 221.3078
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Wing A
Ground Floor for Commercial & Parking
1st to 7th Floor for Residential
101 to 701 |  | 1BHK | 479.5534 | 0 | 695.3525 | 1st to 7th Floor for Residential |  | 34.9076 |  | 4055.4973
102 to 702 |  | 1BHK | 479.5534 | 0 | 695.3525
103 to 703 |  | 3BHK | 787.8473 | 0 | 1142.3786 |  |  |  |  | 4009.1788
104 to 704 |  | 2BHK | 664.9827 | 0 | 964.2249 |  |  |  |  | 3692.0847
Wing B
Ground Floor for Parking
1st to 7th Floor for Residential
101 to 701 |  | 1BHK | 471.7345 | 0 | 684.015 | 1st to 7th Floor for Residential |  |  |  | 4122.7169
102 to 702 |  | 2BHK | 604.3943 | 0 | 876.3717 |  |  |  |  | 4062.2032
103 to 703 |  | 1BHK | 479.5534 | 0 | 695.3525
104 to 704 |  | 1BHK | 479.5534 | 0 | 695.3525
Wing C
Ground Floor for Driver's Room, Society Office & Parking
1st to 7th Floor for Residential
101 to 701 |  | 1BHK | 480.0916 | 0 | 696.1329 | 1st to 7th Floor for Residential
102 to 702 |  | 1BHK | 480.0916 | 0 | 696.1329
103 to 703 |  | 1BHK | 469.6032 | 0 | 680.9246
104 to 704 |  | 1BHK | 471.5407 | 0 | 683.734
105 to 705 |  | 1BHK | 480.7375 | 0 | 697.0693
106 to 706 |  | 2BHK | 604.6785 | 0 | 876.7838
107 to 707 |  | 1BHK | 471.5407 | 0 | 683.734
108 to 708 |  | 1BHK | 471.5407 | 0 | 683.734
Wing D
Ground Floor for Commercial & Parking
1st to 7th Floor for Residential
101 to 701 |  | 1BHK | 477.6762 | 0 | 692.6305 | 1st to 7th Floor for Residential
102 to 702 |  | 1BHK | 477.6762 | 0 | 692.6305
103 to 703 |  | 1BHK | 507.6475 | 0 | 736.0888
104 to 704 |  | 2BHK | 664.8449 | 0 | 964.0251
105 to 705 |  | 1BHK | 477.0519 | 0 | 691.7252
106 to 706 |  | 2BHK | 571.0883 | 0 | 828.0781 |  |  | 40.2386
107 to 707 |  | 1BHK | 474.1456 | 0 | 687.5111
108 to 708 |  | 1BHK | 466.2879 | 0 | 676.1174
Remarks:
* | Wing A, B & C = Construction work is in process at the time of visit. Wing D = All work Completed. Please provide OC.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + A.P. Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 19/09/2024
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Sudhir Bhosale |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Precious Harmony NX
Layout :
Google Map :
Formulas:
Belavali = [Belavali, row above]
Wing A
Wing B
Wing C
Wing D
Precious Harmony NX
Wing D
A Wing
A Wing
A Wing
B Wing
C Wing
D Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted