## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s. Tharwani Realtors
Name of the builder company |  |  |  | M/s. Tharwani Realtors
Name of the Project |  |  |  | Tharwani Millennium City Phase I, II & III
Provided Contact Details (Name & Contact No.) |  |  |  | 9209205666
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss.Payal : 7770019388
Name / No of the Building |  |  |  | PLOT 2 Phase I = Wing A1 (Allura) Phase II = Wing B1 (Blissta) Phase III = Wing C1 (Celestia)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans.
RERA No. |  |  |  | Phase I = Wing A1 (Allura) = P51700023974 Phase II = Wing B1 (Blissta) = P51700023782 Phase III = Wing C1 (Celestia) = P51700023784
Project location details |  | Tharwani Millennium City Phase I, II & III, Plot No.1 & 2, S. No. 63/1/1/2A(p), 63/1/1/2B, 63/1/3, 63/1/4, 64/1, 64/2, 64/3, 64/4(p), near Kartik Residency, Proposed Panvel Hwy, Belavali, Badlapur East, Ambarnath, Thane - 421503.
Plot No |  | 1 & 2, S. No. 63/1/1/2A(p), 63/1/1/2B, 63/1/3, 63/1/4, 64/1, 64/2, 64/3, 64/4(p)
Road |  | Proposed Panvel Hwy |  | Locality/Village |  | Belavali
City |  | Badlapur East |  | District |  | Thane
Taluka |  | Ambarnath |  | Pin Code |  | 421503
Nearby Landmark |  | Kartik Residency |  | Distance from city centre: |  | 2.10Km from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | 30.00 M. Wide DP Road |  |  | Proposed Panvel Hwy
West | NA | Other Plot |  |  | Open Plot
North | NA | Other Plot |  |  | Kartik Residency
South | NA | S. No. 63 |  |  | Open Plot/Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.175145,73.223507
Location Link |  | https://maps.app.goo.gl/2NpXjUnkzfnemSam6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9227.98
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.2434
Total FSI availaible for the project |  |  |  | 3.3434
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 30852.8
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgoan Badlapur Municipal Council
Wing A1
Layout Approval No |  | KBNP/NRV/BD/6989-59/2019-20 |  |  | Dated | 2019-08-09
Approved Floor plan No. |  | KBNP/NRV/BD/6989-59/2019-20 |  |  | Dated | 2019-08-09
Commencement Certificate No. |  | KBNP./B.P/2019-2020/6989/59 |  |  | Dated | 2019-08-09
Valid Up to: A1 Wing = G + 12th Floor
O. Certificate No.: Approved upto : |  | KBNP/NRV/367/2022-2023 Wing A1 = G/St + 1st to 12th Floor (Shops = 16 Nos. & Flats = 117 Nos.) |  | Date of approval: | Dated | 2022-10-04
Wing B1
Layout Approval No |  | KBNP/NRV/BP/5319-57 |  |  | Dated | 2021-06-29
Approved Floor plan No. |  | KBNP/NRV/BP/5319-57 |  |  | Dated | 2021-06-29
Commencement Certificate No. |  | KBNP/BP/2021-2022/5319/Unique No. 57 |  |  | Dated | 2021-06-29
Valid Up to: B1 Wing = G/St + 1st to 14th Floor C1 Wing = G/St + 1st to 7th Floor
Wing C1
Layout Approval No |  | KBNP/NRV/BD/432-171 |  |  | Dated | 2023-02-24
Approved Floor plan No. |  | KBNP/NRV/BD/432-171 |  |  | Dated | 2023-02-24
Commencement Certificate No. |  | KBNP/BP/2022-2023/432/Unique No.171 |  |  | Dated | 2023-02-24
Valid Up to: C1 Wing = G/St + 1st to 14th Floor
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 30852.8
Approved no of units |  |  | Flats - 449, Shops - 16
Approved no of Floors |  |  | A1 Wing = G/St + 1st to 12th Floor B1 & C1 Wing = G/St + 1st to 14th Floor C1 Wing = G/St + 1st to 14th Floor
Proposed no of Floors |  |  | A1 Wing = G/St + 1st to 12th Floor
|  |  | B1 Wing = G/St + 1st to 14th Floor |  |  |  |  | As per rera
|  |  | C1 Wing = G/St + 1st to 14th Floor |  |  |  |  | As per rera
Expected Completion |  |  | As per RERA - A1 Wing = Completed B1 Wing = 29/06/2025 C1 Wing = 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Decorative Entrance Lobby, Gymnasium, Kids Play Area, Swimming Pool, Squash Court, Indoor Games, etc. |  |  |  |  | https://tharwanirealty.com/ongoing-residential/tharwani-millennium-city
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A1 Wing = G/St + 1st to 12th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 100% |  | 100% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 100% |  |  |  |  | Plinth in process | 9
Possession |  | 12 | 100% |  |  |  |  | Plinth completed | 12
Construction details: |  | B1 Wing = G/St + 1st to 14th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 13 Floor, Painting upto 13 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 13 Floor, Painting upto 13 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 88.93% |  | 94.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 92.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 13 | 92.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | C1 Wing = G/St + 1st to 14th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 13 Floor, Internal Plaster upto 5 Floor, External Plaster upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 13 Floor, Internal Plaster upto 5 Floor, External Plaster upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 61.07% |  | 82.14% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 13 | 92.86% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 5 | 35.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4800 |  |  |  | Rate 4500 for case 211 blista by Rushikesh verbal On 05/09/2024
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6500 |  |  |  | 4500 to 4800 rate 2.5 lacs development charges and 3 lacs car park
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 250000
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 3840
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A1 (Allura) |  | 16 |  | 4563.6023 |  | 7301.7637
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A1 (Allura) |  | 117 |  | 51547.3698 |  | 82939.5397
Wing B1 (Blissta) |  | 166 |  | 95485.937 |  | 143228.9056
Wing C1 (Celestia) |  | 166 |  | 96815.8292 |  | 145223.7439
Total |  | 449 |  | 243849.136 |  | 371392.1892
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
PLOT 2
Phase I
Wing A1 (Allura)
Ground Floor for Commercial & Parking
1 |  | Shop | 227.0397 | 0 | 363.2635 | Ground Floor for Commercial & Parking
2 |  | Shop | 263.4489 | 0 | 421.5182
3 |  | Shop | 263.4489 | 0 | 421.5182
4 |  | Shop | 263.4489 | 0 | 421.5182
5 |  | Shop | 263.4489 | 0 | 421.5182
6 |  | Shop | 292.1888 | 0 | 467.502
7 |  | Shop | 258.0669 | 0 | 412.907
8 |  | Shop | 196.5506 | 0 | 314.481
9 |  | Shop | 480.7471 | 0 | 769.1954
10 |  | Shop | 196.5506 | 0 | 314.481
11 |  | Shop | 272.4907 | 0 | 435.9851
12 |  | Shop | 443.9881 | 0 | 710.3809
13 |  | Shop | 245.6883 | 0 | 393.1013
14 |  | Shop | 234.7359 | 0 | 375.5775
15 |  | Shop | 330.88 | 0 | 529.408
16 |  | Shop | 330.88 | 0 | 529.408
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
PLOT 2
Phase I
Wing A1 (Allura)
1st Floor for Residential
1 |  | 2BHK | 497.6466 | 44.1324 | 790.6023 | 1st Floor for Residential
2 |  | 1BHK | 382.9831 | 48.438 | 622.9127
3 |  | 1BHK | 382.9831 | 48.438 | 622.9127
4 |  | 2BHK | 497.6466 | 44.1324 | 790.6023
5 |  | 1BHK | 409.0858 | 44.1324 | 657.7611
6 |  | 2BHK | 497.6466 | 44.1324 | 790.6023
7 |  | Double Height
8
9 |  | 2BHK | 497.6466 | 44.1324 | 790.6023
10 |  | 1BHK | 409.0858 | 44.1324 | 657.7611
2nd, 4th, 6th, 10th & 12th Floor
1 |  | 2BHK | 512.9853 | 96.4185 | 865.8965 | 2nd, 4th, 6th, 10th & 12th Floor
2 |  | 1BHK | 398.3218 | 0 | 597.4827
3 |  | 1BHK | 398.3218 | 0 | 597.4827
4 |  | 2BHK | 512.9853 | 96.4185 | 865.8965
5 |  | 1BHK | 399.8019 | 59.0944 | 658.7972
6 |  | 2BHK | 512.9853 | 96.4185 | 865.8965
7 |  | 1BHK | 398.3218 | 0 | 597.4827
8 |  | 1BHK | 398.3218 | 0 | 597.4827
9 |  | 2BHK | 512.9853 | 96.4185 | 865.8965
10 |  | 1BHK | 399.8019 | 59.0944 | 658.7972
8th Floor (Part Refuge Area)
1 |  | 2BHK | 512.9853 | 96.4185 | 865.8965 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 398.3218 | 0 | 597.4827
3 |  | 1BHK | 398.3218 | 0 | 597.4827
4 |  | 2BHK | 512.9853 | 96.4185 | 865.8965
5 |  | 1BHK | 399.8019 | 59.0944 | 658.7972
6 |  | 2BHK | 512.9853 | 96.4185 | 865.8965
7 |  | 1BHK | 398.3218 | 0 | 597.4827
8 |  | 1BHK | 398.3218 | 0 | 597.4827
9 |  | 2BHK | 512.9853 | 96.4185 | 865.8965
10 |  | Refuge area
3rd, 5th, 7th, 9th & 11th Floor
1 |  | 2BHK | 497.6466 | 44.1324 | 790.6023 | 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 1BHK | 382.9831 | 48.438 | 622.9127
3 |  | 1BHK | 382.9831 | 48.438 | 622.9127
4 |  | 2BHK | 497.6466 | 44.1324 | 790.6023
5 |  | 1BHK | 409.0858 | 44.1324 | 657.7611
6 |  | 2BHK | 497.6466 | 44.1324 | 790.6023
7 |  | 1BHK | 382.9831 | 48.438 | 622.9127
8 |  | 1BHK | 382.9831 | 48.438 | 622.9127
9 |  | 2BHK | 497.6466 | 44.1324 | 790.6023
10 |  | 1BHK | 409.0858 | 44.1324 | 657.7611
Phase II
Wing B1 (Blissta)
Ground Floor for Parking
1st to 7th, 9th to 12th & 14th Floor for Residential
1 |  | 2BHK | 719.5734 | 0 | 1079.3601 | 1st to 7th, 9th to 12th & 14th Floor for Residential |  |  |  | 101,..,1401 | 101 | 1401
2 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 102,..,1402 | 102 | 1402
3 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 103,..,1403 | 103 | 1403
4 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 104,..,1404 | 104 | 1404
5 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 105,..,1405 | 105 | 1405
6 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 106,..,1406 | 106 | 1406
7 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 107,..,1407 | 107 | 1407
8 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 108,..,1408 | 108 | 1408
9 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 109,..,1409 | 109 | 1409
10 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 110,..,1410 | 110 | 1410
11 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 111,..,1411 | 111 | 1411
12 |  | 2BHK | 719.5734 | 0 | 1079.3601 |  |  |  |  | 112,..,1412 | 112 | 1412
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 719.5734 | 0 | 1079.3601 | 8th & 13th Floor (Part Refuge Area) |  |  |  | 801,..,1301 | 801 | 1301
2 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 802,..,1302 | 802 | 1302
3 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 803,..,1303 | 803 | 1303
4 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 804,..,1304 | 804 | 1304
5 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 805,..,1305 | 805 | 1305
6 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 806,..,1306 | 806 | 1306
7 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 807,..,1307 | 807 | 1307
8 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 808,..,1308 | 808 | 1308
9 |  | 2BHK | 630.6897 | 0 | 946.0345 |  |  |  |  | 809,..,1309 | 809 | 1309
10 |  | Refuge area | [7 empty] | 810,..,1310 | 810 | 1310
11 |  | 1BHK | 488.0398 | 0 | 732.0596 |  |  |  |  | 811,..,1311 | 811 | 1311
12 |  | 2BHK | 719.5734 | 0 | 1079.3601 |  |  |  |  | 812,..,1312 | 812 | 1312
Phase III
Wing C1 (Celestia)
Ground Floor for Meter Room, drivers Room & Parking
1st to 7th, 9th to 12th & 14th Floor for Residential
1 |  | 2BHK | 561.0735 | 0 | 841.6103 | 1st to 7th, 9th to 12th & 14th Floor for Residential |  |  |  | 101 to 1401 | 101 | 1401
2 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 102 to 1402 | 102 | 1402
3 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 103 to 1403 | 103 | 1403
4 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 104 to 1404 | 104 | 1404
5 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 105 to 1405 | 105 | 1405
6 |  | 2BHK | 552.6103 | 0 | 828.9155 |  |  |  |  | 106 to 1406 | 106 | 1406
7 |  | 2BHK | 552.6103 | 0 | 828.9155 |  |  |  |  | 107 to 1407 | 107 | 1407
8 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 108 to 1408 | 108 | 1408
9 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 109 to 1409 | 109 | 1409
10 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 110 to 1410 | 110 | 1410
11 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 111 to 1411 | 111 | 1411
12 |  | 2BHK | 561.0735 | 0 | 841.6103 |  |  |  |  | 112 to 1412 | 112 | 1412
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 561.0735 | 0 | 841.6103 | 8th & 13th Floor (Part Refuge Area) |  |  |  | 801 to 1301 | 801 | 1301
2 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 802 to 1302 | 802 | 1302
3 |  | Refuge area | [7 empty] | 803 to 1303 | 803 | 1303
4 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 804 to 1304 | 804 | 1304
5 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 805 to 1305 | 805 | 1305
6 |  | 2BHK | 552.6103 | 0 | 828.9155 |  |  |  |  | 806 to 1306 | 806 | 1306
7 |  | 2BHK | 552.6103 | 0 | 828.9155 |  |  |  |  | 807 to 1307 | 807 | 1307
8 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 808 to 1308 | 808 | 1308
9 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 809 to 1309 | 809 | 1309
10 |  | 2BHK | 607.278 | 0 | 910.917 |  |  |  |  | 810 to 1310 | 810 | 1310
11 |  | 2BHK | 586.4227 | 0 | 879.6341 |  |  |  |  | 811 to 1311 | 811 | 1311
12 |  | 2BHK | 561.0735 | 0 | 841.6103 |  |  |  |  | 812 to 1312 | 812 | 1312
Remarks:
1 | A1 Wing = All work Completed. OC Received. B1 & C1 Wing = Construction work is in process. (Internal visit not allowed only for C1 Wing).
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We have considered proposed No. of Floor for Stage Calculation.
6 | We considered Gross carpet area = Net carpet + Balcony + ORA Projection Area.
7 | We have considered rate by verifying it from market inquire.
8 | Car parking is subjected to authentic documentation.
9 | We have updated approved plans & CC of Wing B1 & C1 (on 30/12/2021).
10 | We have updated OC for Wing A1 from Rera (On 17/06/2024).
11 | Recommended Rates of the Property have been revised on 05/09/2024 & 27/11/2024.
12 | We have updated latest approved floor plans & CC for Wing C1 (On 06/11/2024).
13 | As per RERA, completion period of project Tharwani Millennium City Phase II is expired on 30/12/2024 but still project is under construction.
13 | As per RERA, completion period of project Tharwani Millennium City Phase II is expired on 29/06/2025 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tharwani Millennium City Phase I, II & III
Layout :
Google Map :
Formulas:
Belavali = [Belavali, row above]
Wing A1
Wing C1
Wing B1
A1
A1
B1
C1
Phase III
Phase III
Phase II
Phase II

## C% for old Flormat
Add 14 Black Row in OLD APF format
Construction details: |  | Building No. = G + 1st to 20th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 20
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% |  | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% | [5 empty] | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% | [5 empty] | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 15
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 20
[5 empty] | 50% |  | 75%

## C% for new format
Construction details: |  | Building No. = G + 20th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
|  |  |  | 50% |  | 75%

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted