## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | M/s.Vaastu Enteprises
Name of the builder company |  |  |  | M/s.Vaastu Enteprises
Name of the Project |  |  |  | Vaastu Sankalp
Contact Details ( Name & Contact No.) |  |  |  | Mr. Bhaskar - 8080904210
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Amol Kolekar 8693865186
Name / No of the Building |  |  |  | Wing A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000026957
Project location details |  | Vaastu Sankalp, Survey No.168, H.No.1A + 2A + 3A/3, near Himalaya Complex, Pashane Road, Pashane, Vangani, Karjat, Raigad.
Survey No |  | 168, H.No.1A + 2A + 3A/3
Road |  | Pashane Road |  | Locality/Village |  | Pashane
City |  | Vangani |  | District |  | Raigad
Taluka |  | Karjat |  | Pin Code |  | 410101
Nearby Landmark |  | Himalaya Complex |  | Distance from city centre: |  | 2.6 Km from Vangani Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | Himalaya Complex
North | NA | NA |  |  | Himalaya Complex
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.106574,73.316254
Location Link: |  | https://goo.gl/maps/T3Vhdh1txtrctDyU9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1764.9
Permissible FSI |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  | 0.22209
Total FSI availaible for the project |  |  |  | 1.4221
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2509.85
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Layout Approval No |  | MASHA/LNA1B/SR/P.No.02 |  |  | Dated | 2020-10-01
Approved Floor plan No. |  | MASHA/LNA1B/SR/P.No.02 |  |  | Dated | 2020-10-01
Commencement Certificate No. |  | MASHA/LNA1B/SR/P.No.02 |  |  | Dated | 2020-10-01
Valid Up to: Wing A, B & C = Gr + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2509.85
Approved no of units |  |  | Flats - 72, Shops - 25
Approved no of Floors |  |  | Wing A, B & C = Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Wing A = Gr + 1st to 4th Floor
Wing B & C = Gr + 1st to 4th Floor
Wing C = Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 29/06/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Wing A = Gr + 1st to 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | All work completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 93.75% |  | 95% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 3 | 75% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | Wing B = Gr + 1st to 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed , External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed , External Plaster upto 2 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 62.5% |  | 82.5% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | Wing C = Gr + 1st to 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 66.25% |  | 85% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 2 | 50% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3300 |  |  | 2850 to 3300 | Abhishek | 2022-12-27 | IGR
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5200
Development Charges |  |  |  |  | 1,75,000/-
Legal Fee |  |  |  |  | 10,000/-
Electricity Charges |  |  |  |  | 20,000/-
Society Charges |  |  |  |  | 40,000/-
Advance Maintenance Charges |  |  |  |  | 24,000/-
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 2640
Commercial Area Details :Shop
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 10 |  | 961.871 |  | 2142
Wing B |  | 5 |  | 423.0252 |  | 844
Wing C |  | 10 |  | 1045.615 |  | 2134
Total |  | 25 |  | 2430.5112 |  | 5120
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 24 |  | 7508.1053 |  | 11100
Wing B |  | 24 |  | 7748.3578 |  | 11380
Wing C |  | 24 |  | 7760.844 |  | 11180
Total |  | 72 |  | 23017.307 |  | 33660
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Wing A, B & C
Ground Floor for Commercial & Parking
1 |  | Shop | 93.4315 | 0 | 208 | Ground Floor for Commercial & Parking |  | 3.2216
2 |  | Shop | 112.4838 | 0 | 224
3 |  | Shop | 112.4838 | 0 | 304
4 |  | Shop | 104.3032 | 0 | 282
5 |  | Shop | 58.9867 | 0 | 118
6 |  | Shop | 72.7646 | 0 | 188
7 |  | Shop | 94.5079 | 0 | 190
8 |  | Shop | 115.4977 | 0 | 232
9 |  | Shop | 115.4977 | 0 | 232
10 |  | Shop | 81.914 | 0 | 164
Wing B
Ground Floor for Commercial & Parking
11 |  | Shop | 62.2159 | 0 | 124 | Ground Floor for Commercial & Parking
12 |  | Shop | 50.9137 | 0 | 102
13 |  | Shop | 115.4977 | 0 | 230
14 |  | Shop | 112.4838 | 0 | 224
15 |  | Shop | 81.914 | 0 | 164
Wing C
Ground Floor for Commercial & Parking
16 |  | Shop | 81.914 | 0 | 164 | Ground Floor for Commercial & Parking
17 |  | Shop | 115.4977 | 0 | 232
18 |  | Shop | 115.4977 | 0 | 232
19 |  | Shop | 94.2926 | 0 | 190
20 |  | Shop | 90.4176 | 0 | 180
21 |  | Shop | 74.5945 | 0 | 192
22 |  | Shop | 104.1955 | 0 | 208
23 |  | Shop | 152.4182 | 0 | 304
24 |  | Shop | 112.4838 | 0 | 224
25 |  | Shop | 104.3032 | 0 | 208
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Wing A
1st to 4th Floor for Residential | [11 empty] | 1 to 1 | 1 | 1
101 to 401 |  | 1RK | 237.3462 | 0 | 350 | 1st to 4th Floor for Residential | [5 empty] | 2 to 2 | 2 | 2
102 to 402 |  | 1BHK | 401.2819 | 0 | 590 | 1st to 4th Floor for Residential | [5 empty] | 3 to 3 | 3 | 3
103 to 403 |  | 1BHK | 401.0666 | 0 | 590 | 1st to 4th Floor for Residential | [5 empty] | 4 to 4 | 4 | 4
104 to 404 |  | 1BHK | 351.6599 | 0 | 525 | 1st to 4th Floor for Residential | [5 empty] | 5 to 5 | 5 | 5
105 to 405 |  | 1RK | 242.6206 | 0 | 360 | 1st to 4th Floor for Residential | [5 empty] | 107 to 407 | 107 | 407
106 to 406 |  | 1RK | 243.0511 | 0 | 360 | 1st to 4th Floor for Residential |  | 2819.4444 |  |  |  | 108 to 408 | 108 | 408
Wing B
1st to 4th Floor | [11 empty] | 1 to 1 | 1 | 1
101 to 401 |  | 1BHK | 374.5872 | 0 | 555 | 1st to 4th Floor | [5 empty] | 2 to 2 | 2 | 2
102 to 402 |  | 1BHK | 361.2398 | 0 | 535 | 1st to 4th Floor | [5 empty] | 3 to 3 | 3 | 3
103 to 403 |  | 1BHK | 347.3543 | 0 | 510 | 1st to 4th Floor | [5 empty] | 4 to 4 | 4 | 4
104 to 404 |  | 1RK | 255.2144 | 0 | 370 | 1st to 4th Floor | [5 empty] | 5 to 5 | 5 | 5
105 to 405 |  | 1RK | 255.2144 | 0 | 370 | 1st to 4th Floor | [5 empty] | 107 to 407 | 107 | 407
106 to 406 |  | 1BHK | 343.4792 | 0 | 505 | 1st to 4th Floor | [5 empty] | 108 to 408 | 108 | 408
Wing C
1st to 4th Floor | [11 empty] | 1 to 1 | 1 | 1
101 to 401 |  | 1RK | 255.2144 | 0 | 370 | 1st to 4th Floor | [5 empty] | 2 to 2 | 2 | 2
102 to 402 |  | 1RK | 248.8637 | 0 | 370 | 1st to 4th Floor | [5 empty] | 3 to 3 | 3 | 3
103 to 403 |  | 1BHK | 353.8127 | 0 | 525 | 1st to 4th Floor | [5 empty] | 4 to 4 | 4 | 4
104 to 404 |  | 1BHK | 422.5946 | 0 | 590 | 1st to 4th Floor | [5 empty] | 5 to 5 | 5 | 5
105 to 405 |  | 1BHK | 422.5946 | 0 | 590 | 1st to 4th Floor | [5 empty] | 107 to 407 | 107 | 407
106 to 406 |  | 1RK | 237.1309 | 0 | 350 | 1st to 4th Floor | [5 empty] | 108 to 408 | 108 | 408
Remarks:
1 | Wing A = Lift work is pending. Work is same as last visit dtd.15/07/2024 Wing B & C = Work is same as last visit (dtd.09/01/2025). Wing C = Construction work is in process at the time of Visit.
2 | We considered Saleable area as per Builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + E.P Area.
5 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes).
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
#REF! | On Site, we meet Mr. Amol - 8693865186.
8 | As per RERA, completion period of project Vaastu Sankalp is expired on 29/06/2025 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vaastu Sankalp
Google Map :
Formulas:
Pashane = [Pashane, row above]
C
B
C
A
C
B
A
C
Wing A
Wing B
Wing C

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
2021-10-21 | Asmi | Abhishek