## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | M/s. Greenscape Ventures
Name of the builder company |  |  |  | M/s. Greenscape Ventures
Name of the Project |  |  |  | Cyber Works
Contact Details ( Name & Contact No.) |  |  |  | 9967740099
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Siddhesh 8976116863
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51700022663
Project location details |  | Cyber Works, Plot No.A-606/1A, TTC Industrial Area, near Glenmark Pharmaceuticals, Mahape Road, Mahape, MIDC, Ghansoli, Thane, Thane - 400703.
Plot No |  | A-606/1A, TTC Industrial Area
Road |  | Mahape Road |  | Locality/Village |  | Mahape, MIDC
City |  | Ghansoli |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400703
Nearby Landmark |  | Glenmark Pharmaceuticals |  | Distance from city centre: |  | 1.5KM from Ghansoli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Altruist Customer Management India Pvt. Ltd.
West | NA | NA |  |  | Glenmark Pharmaceuticals
North | NA | NA |  |  | Steri Max
South | NA | NA |  |  | Majesco
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.11235271,73.01622284
Location |  | https://goo.gl/maps/yBE9scNmAErBA627A
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6420
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 3
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19260
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Industrial Development Corporation
Layout Approval No |  | EE/DN.II/MHP/SPA/C43478/ of 2019 |  |  | Dated | 2021-07-23
Approved Floor plan No. |  | EE/DN.II/MHP/SPA/C43478/ of 2019 |  |  | Dated | 2021-07-23
Commencement-CC No Valid Up to: |  | EE/DN.II/MHP/SPA/C43478/ of 2019 |  |  | Dated | 2021-07-23
Basement + Gr + 1st to 10th Floor
Combined Building Approval Letter No. Valid Up for: |  | EE/Dn. II/MHP/SPA/A88591/of 2023 |  |  | Dated | 2023-03-14
Basement + Gr + 1st to 15th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 19260
Approved no of units |  |  | Office - 147, Shops - 26
Approved no of Floors |  |  | Basement + Gr + 1st to 24th Floor
Proposed no of Floors |  |  | Basement + Gr + 1st to 25th Floor
Expected Completion |  |  | As per RERA - 30/06/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Basement + Gr + 1st to 25th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 12 Floor, Internal Plaster upto 6 Floor Completed | , RCC upto 17 Slab, Brickwork upto 12 Floor, Internal Plaster upto 6 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 25 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 12 Floor, Internal Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 41.55% |  | 68.22% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 17 | 65.38% |  |  |  |  | Footing in Process | 6.25
Brickwork | Brickwork & Internal Plaster | 12 | 48% |  |  |  |  | Footing Completed | 12.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 24% |  |  |  |  | Basement 1 | 0 |  | 1050 | 187
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft.
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 18000
Recommended rate of the Office Per Sq. Ft. (1st to 8th Floor) |  |  |  |  | 8200 |  |  | 7800 to 8200 | Smith | 2023-12-18 | verbal
Recommended rate of the Office Per Sq. Ft. (9th to 25th Floor) |  |  |  |  | 7800
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 500000
Distressed valuation of the Property |  |  |  |  | 14400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 26 |  | 15174 |  | 34207
Office |  | 147 |  | 205759.9309 |  | 395074
Total |  | 173 |  | 220933.9309 |  | 429281
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Basement Floor for Parking
Ground Floor for Commercial & Parking
1 |  | IT Support Services/Shop | 740 | 0 | 1595 | Ground Floor for Commercial & Parking |  | 21943.5737 | 2.1554
2 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  | 22208.1218 | 2.1589
3 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  |  | 2.1589
4 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  |  | 2.1589
5 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  |  | 2.1589
6 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  |  | 2.1589
7 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  |  | 2.1589
8 |  | IT Support Services/Shop | 730 | 0 | 1576 | Ground Floor for Commercial & Parking |  |  | 2.1589
9 |  | IT Support Services/Shop | 740 | 0 | 2337 | Ground Floor for Commercial & Parking |  |  | 3.1581
11 |  | IT Support Services/Shop | 521 | 0 | 1160 | Ground Floor for Commercial & Parking |  |  | 2.2265
12 |  | IT Support Services/Shop | 580 | 0 | 1291 | Ground Floor for Commercial & Parking |  |  | 2.2259
13 |  | IT Support Services/Shop | 454 | 0 | 1011 | Ground Floor for Commercial & Parking |  |  | 2.2269
14 |  | IT Support Services/Shop | 454 | 0 | 1011 | Ground Floor for Commercial & Parking |  |  | 2.2269
15 |  | IT Support Services/Shop | 454 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.5154
16 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
17 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
18 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
19 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
20 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
21 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
22 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
23 |  | IT Support Services/Shop | 513 | 0 | 1142 | Ground Floor for Commercial & Parking |  |  | 2.2261
24 |  | IT Support Services/Shop | 484 | 0 | 1078 | Ground Floor for Commercial & Parking |  | 13450.8349 | 2.2273
25 |  | IT Support Services/Shop | 484 | 0 | 1078 | Ground Floor for Commercial & Parking |  |  | 2.2273
26 |  | IT Support Services/Shop | 484 | 0 | 1078 | Ground Floor for Commercial & Parking |  |  | 2.2273
27 |  | IT Support Services/Shop | 565 | 0 | 1258 | Ground Floor for Commercial & Parking |  |  | 2.2265
1st Podium Floor for Parking
2nd to 4th Podium Floor for Parking
5th Podium Floor for Parking
6th, 8th to 10th, 12th to 14th, 16th to 18th, 20th, 21st & 22nd Floor
1 |  | IT Office | 1383.9544 | 0 | 2527 | 6th, 8th to 10th, 12th to 14th, 16th to 18th, 20th, 21st & 22nd Floor |  | 7716.6601 | 1.8259
2 |  | IT Office | 1914.1083 | 0 | 3638 |  |  |  | 1.9006
3 |  | IT Office | 950.1921 | 0 | 1832 |  |  | 7205.2402 | 1.928
4 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
5 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
6 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
7 |  | IT Office | 1914.1083 | 0 | 3638 |  |  | 7751.5118 | 1.9006
8 |  | IT Office | 1382.0976 | 0 | 2527 |  |  |  | 1.8284
7th, 11th, 15th & 19th Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th, 11th, 15th & 19th Floor(Part Refuge Area)
2 |  | IT Office | 1914.1083 | 0 | 3638 |  |  |  | 1.9006
3 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
4 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
5 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
6 |  | IT Office | 950.1921 | 0 | 1832 |  |  |  | 1.928
7 |  | IT Office | 1914.1083 | 0 | 3638 |  |  |  | 1.9006
8 |  | IT Office | 1382.0976 | 0 | 2527 |  |  |  | 1.8284
23rd Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 23rd Floor(Part Refuge Area)
2 |  | IT Support Services | 1914.1083 | 0 | 3638 | 23rd Floor(Part Refuge Area) |  |  | 1.9006
3 |  | IT Support Services | 950.1921 | 0 | 1832 | 23rd Floor(Part Refuge Area) |  |  | 1.928
4 |  | IT Support Services | 950.1921 | 0 | 1832 | 23rd Floor(Part Refuge Area) |  |  | 1.928
5 |  | IT Support Services | 950.1921 | 0 | 1832 | 23rd Floor(Part Refuge Area) |  |  | 1.928
6 |  | IT Support Services | 950.1921 | 0 | 1832 | 23rd Floor(Part Refuge Area) |  |  | 1.928
7 |  | IT Support Services | 1914.1083 | 0 | 3638 | 23rd Floor(Part Refuge Area) |  |  | 1.9006
8 |  | IT Support Services | 1382.0976 | 0 | 2527 | 23rd Floor(Part Refuge Area) |  |  | 1.8284
24th Floor
1 |  | IT Support Services | 1383.9544 | 0 | 2527 | 24th Floor |  |  | 1.8259
2 |  | IT Support Services | 1914.1083 | 0 | 3638 | 24th Floor |  |  | 1.9006
3 |  | IT Support Services | 950.1921 | 0 | 1832 | 24th Floor |  |  | 1.928
4 |  | IT Support Services | 950.1921 | 0 | 1832 | 24th Floor |  |  | 1.928
5 |  | IT Support Services | 950.1921 | 0 | 1832 | 24th Floor |  |  | 1.928
6 |  | IT Support Services | 950.1921 | 0 | 1832 | 24th Floor |  |  | 1.928
7 |  | IT Support Services | 1914.1083 | 0 | 3638 | 24th Floor |  |  | 1.9006
8 |  | IT Support Services | 1382.0976 | 0 | 2527 | 24th Floor |  |  | 1.8284
Remarks:
* | Construction work is in process at the time of Visit. Internal photo was not allowed (Slow Speed)
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Sidhheshwar Jagtap(Site Engg.) - 8976116863.
* | We have refered revised Combined Building Approval Letter from RERA (on 18/04/2024)
* | Please provide latest CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Mohite |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Cyber Works
Google Map :
Formulas:
Mahape, MIDC = [Mahape, MIDC, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted