## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 11/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-10
Name of the builder group |  |  |  |  | M/s.Continental Sidhant Reality
Name of the builder company |  |  |  |  | M/s.Continental Sidhant Reality
Name of the Project |  |  |  |  | Continental Futura
Contact Details ( Name & Contact No.) |  |  |  |  | 2249749317
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Ramesh 9820656519 / Mr. Shoeb 9324852383
Name / No of the Building |  |  |  |  | Building No.1 Building No.2 (A & B wings)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC, Cost Sheet.
RERA No. |  |  |  |  | P51700015939
Project location details |  | Continental Futura, S no.238/1/2, 239/1/A/1Pt, 239/1/A/2Pt, 239/1/A/3Pt, 258/3/4/5/8, Kalyan Bhiwandi road, Kon gaon, Bhiwandi, Thane.
S no |  | 238/1/2, 239/1/A/1Pt, 239/1/A/2Pt, 239/1/A/3Pt, 258/3/4/5/8 |  |  |  |  | Locality | Kon gaon
Road |  | Kalyan Bhiwandi road |  |  | District |  | Thane
City |  | Bhiwandi |  |  | Pin Code |  | 421302
Near by Landmark |  | Al mussvir complex |  |  | Distance from city centre: |  | 3Km from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Open |  | Open |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.249217,73.1102875
Location Link |  | https://goo.gl/maps/V5hxeGMK2bkoJ4gW9
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 9637.16
Permissible FSI |  |  |  |  | 0.95
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.95
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 9155.302
Total number of Buildings |  |  |  |  | 3 Buildings
Approval Detail : Plan approval
Layout Approval No |  | SROT/BSNA/2501/BP/KON-37/1502/2017 |  |  |  | Dated | 2017-10-27
Approved Floor plan No. |  | SROT/BSNA/2501/BP/KON-37/1502/2017 |  |  |  | Dated | 2017-10-27
Commencement Certificate No. Valid Up to: |  | SROT/BSNA/2501/BP/Revised CC/Kon-37/ Vol-III/07/2022 |  |  |  | Dated | 2023-01-02
Building No.1 = Stilt + 1st to 11th Floor Building No.2 - A & B wing = Stilt + 1st to 13th Floor
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2023-01-02 |  | Expected Completion |  | 31/03/2028
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 9155.302 |  | Approved no of units |  |  | 182
Approved no of Floors |  | Building No.1 = St + 1st to 11th floor Building No.2 - A wing = St+ 1st to 8th floor Building No.2 - B wing = St + 1st to 14th floor
Proposed no of Floors |  | Building No.1 = St + 1st to 11th floor Building No.2 - A wing = St+ 1st to 13th floor Building No.2 - B wing = St + 1st to 14th floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building No.1 = Stilt + 1st to 11th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 11
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% |  | 100% |  | 100% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% | [5 empty] | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% | [5 empty] | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 11 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 11 | 100% | [5 empty] | Plinth in process | 8.25
Possession |  | 11 | 100% | [5 empty] | Plinth completed | 11
Construction details: |  | Building No.2 - A wing = St + 1st to 13th floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 13
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% |  | 12.86% |  | 47.14% |  | Excavation in process | 6.5 | plitth in processs already given hence progress not increased 08/10/2024
Plinth |  | 13 | 100% | [5 empty] | Excavation Completed | 13
RCC (Including podiums) |  | 1 | 7.143% | [5 empty] | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 13
Construction details: |  | Building No.2 - B wing = Stilt + 1st to 14th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% |  | 20.67% |  | 53% |  | Excavation in process | 7
Plinth |  | 14 | 100% | [5 empty] | Excavation Completed | 14
RCC (Including podiums) |  | 4 | 26.67% | [5 empty] | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 10.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 14
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4700
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 200000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3760
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Building No.1 |  | 66 | 28499.8428 |  |  | 54868
BuildingNo.2 - A wing |  | 32 | 12439.7395 |  |  | 20046.3569
BuildingNo.2 - B wing |  | 84 | 31459.297 |  |  | 60760
Total |  | 182 | 72398.8793 |  |  | 135674.3569
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.1
Ground Floor is for Parking
1st, 3rd, 5th, 7th, 9th & 11th floor
1 |  | 1.5 BHK | 431.4211 |  | 50.2302 | 820 | N | 1st, 3rd, 5th, 7th, 9th & 11th floor
2 |  | 1.5 BHK | 431.4211 |  | 50.2302 | 820 | N
3 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
4 |  | 1 BHK | 346.0626 |  | 37.7547 | 675 | N
5 |  | 2 BHK | 517.9637 |  | 52.5283 | 999 | N
6 |  | 2 BHK | 517.9637 |  | 52.5283 | 999 | N
2nd, 4th, 6th & 10th Floor
1 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N | 2nd, 4th, 6th & 10th Floor
2 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N
3 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
4 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
5 |  | 2 BHK | 517.9637 |  | 57.4528 | 999 | N
6 |  | 2 BHK | 517.9637 |  | 57.4528 | 999 | N
8th Floor (Part Refuge Area)
1 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N | 8th Floor (Part Refuge Area)
2 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N
3 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
4 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
5 |  | 2 BHK | 517.9637 |  | 57.4528 | 999 | N
6 |  | 2 BHK | 517.9637 |  | 57.4528 | 999 | N
Building No.2
A Wing
Ground Floor is for Parking
1st, 3rd, 5th & 7th Floor
1 |  | 1 BHK | 346.0626 |  | 39.3962 | 558.4901 | N | 1st, 3rd, 5th & 7th Floor
2 |  | 1.5 BHK | 431.4211 |  | 50.2302 | 697.3619 | N
3 |  | 1.5 BHK | 431.4211 |  | 50.2302 | 697.3619 | N | 1st, 3rd, 5th & 7th Floor
4 |  | 1 BHK | 346.0626 |  | 39.3962 | 558.4901 | N
2nd, 4th, 6th & 8th Floor
1 |  | 1 BHK | 346.0626 |  | 39.3962 | 558.4901 | N | 2nd, 4th, 6th & 8th Floor
2 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 691.4524 | N
3 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 691.4524 | N
4 |  | 1 BHK | 346.0626 |  | 39.3962 | 558.4901 | N
Building No.2
B Wing
Ground Floor is for Parking
1st, 3rd, 5th, 7th, 9th, 11th & 13th Floor
1 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N | 1st, 3rd, 5th, 7th, 9th, 11th & 13th Floor
2 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
3 |  | 1.5 BHK | 431.4211 |  | 50.2302 | 820 | N
4 |  | 1.5 BHK | 431.4211 |  | 50.2302 | 820 | N
5 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
6 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
2nd, 4th, 6th, 10th, 12th & 14th Floor
1 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N | 2nd, 4th, 6th, 10th, 12th & 14th Floor
2 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
3 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N
4 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N
5 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
6 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
8th Floor (Part Refuge Area)
1 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N | 8th Floor (Part Refuge Area)
2 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
3 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N
4 |  | 1.5 BHK | 431.4211 |  | 44.3208 | 820 | N
5 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
6 |  | 1 BHK | 346.0626 |  | 39.3962 | 675 | N
Remarks:
1. Building No.1 = All work completed. Please provide OC Building No.2B = Construction work is in process at the time of Visit (Slow Speed) Building No.2A = Construction work is the same as last visit (dtd.08/04/2025), but work is in process at the time of the visit. (Slow Speed) 2. We considered Saleable area for Building-1 & Building-2(B wing) as per Builder area sheet & for Building-2(A wing) as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Car parking is subjected to authentic documentation. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Please provide revised approved plans. 7. On Site We Meet With Mr. Inam (9004287366).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Continental Futura
Google Map :
Formulas:
Locality = [Locality, row above]
Building No.1
Wing A
B
A

## C%
Particulars | totaL floor | 11
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 41.6667 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 12 | 5 | 9.0909 | Progress |  |  | 10 | 16.6667 | 1.3636 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 12.5 | 1.3636 | 0 | 0 | 0 | 0
| 11 | 1 | 0
plaster | Total Floor | completed Floor | 0
| 11 | 0 | 0
Flooring | Total Floor | completed Floor
| 11 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 11 | 0 |  | RCC | 16.6667 | 12.5
Finishing | Total Floor | completed Floor |  | Bricks | 1.3636 | 1.3636
| 11 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 28.0303 | 43.8636

## Note
2021-02-12 | Pratiksha

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0