## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 09/07/2025.
Name of the builder group |  |  |  | M/s.Dosti Enterprises
Name of the builder company |  |  |  | M/s.Dosti Enterprises
Name of the Project |  |  |  | Dosti West County Sector 2 - Dosti Tulip
Contact Details ( Name & Contact No.) |  |  |  | Mr.Pratik Gada 7208964023
Name / No of the Building |  |  |  | Wing A = Building No.1 (A wing) Wing B = Building No.2 (A wing) Wing C = Building No.3
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51700032666
Project location details |  | Dosti West County Sector 2 - Dosti Tulip, Survey No.43/2 (pt), 43/3, 43/4, 43/5, 44/1(pt), 45/1 (pt), 46/1/A, 47/1, 47/2/A, 47/2/3/2 A(pt), 47/3/1/A, 47/4/A, 47/5(pt), near NG Regency, Bhiwandi - Wada Road, Balkum, Thane West, Thane, Thane - 400608.
Survey No |  | 43/2 (pt), 43/3, 43/4, 43/5, 44/1(pt), 45/1 (pt), 46/1/A, 47/1, 47/2/A, 47/2/3/2 A(pt), 47/3/1/A, 47/4/A, 47/5(pt)
Road |  | Bhiwandi - Wada Road |  | Locality/Village |  | Balkum
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400608
Nearby Landmark |  | NG Regency |  | Distance from city centre: |  | 5.9 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Balkum Pipeline Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2287 |  | Longitude |  | 72.9942
Location Link |  | https://goo.gl/maps/qKjLwohE11YyBaW36
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 11210
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.3823
Total FSI availaible for the project |  |  |  | 4.4823
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 50246.5
Total number of Buildings |  |  |  | 3 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation (TMC)
Layout Approval No |  | V.P.SO5/0177/19/TMC/TDD/3803/21 |  |  | Dated | 2021-12-10
Approved Floor plan No. |  | V.P.SO5/0177/19/TMC/TDD/3803/21 |  |  | Dated | 2021-12-10
Commencement-CC No Valid Up to: |  | S05/0177/19/TMC/TDD/4428/23 |  |  | Dated | 2023-06-27
Building No.1 (A Wing) = G + 1st to 4th Podium Floor + 1st to 14th floor Building No.2 (A wing) = G + 1st to 4th Podium Floors + 1st to 14th Floor Building No.3 = G + 1st to 4th Podium Floors + 1st to 13th floors.
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 50246.5 |  |  |  |  | Wing A = (Building No.1/Wing A, as per sanctioned plan) = G + 1st to 4th Podium Floors + 1st to 14th Floor
Approved no of units |  |  | Sale Flats - 517, Sale Shops - 26, Mhada Flats - 49
Approved no of Floors |  |  | Wing A (as per sale plan) = Building No.1-Wing A (as per sanctioned plan) = G + 1st to 4th Podium Floor + 1st to 29th floor Wing B (as per sale plan) = Building No.2 -Wing A (as per sanctioned plan) = G + 1st to 4th Podium Floor + 1st to 29th floor Wing C (as per sale plan) = Building No.3 (as per sanctioned plan) = G + 1st to 4th Podium Floor + 1st to 13th floor
Proposed no of Floors |  |  | Building No.1 (A Wing), Building No.2 (A Wing) & Building No.3 = G + 1st to 4th Podium Floor + 1st to 30th floor
Expected Completion |  |  | As per RERA - 31/10/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A (as per sale plan) = Building No.1 Wing A (as per sanctioned plan) - G + 1st to 4th Podium Floor + 1st to 30th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 26 Floor Completed, Painting upto 23 Floor Completed, Finishing upto 4 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 4 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 26 Floor Completed, Painting upto 23 Floor Completed, Finishing upto 4 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 88.17% |  | 94.33% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 35 | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 30 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 26 | 86.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 23 | 76.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 13.33% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Wing B (as per sale plan) = Building No.2 -Wing A (as per sanctioned plan) = G + 1st to 4th Podium Floor + 1st to 30th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 26 Floor Completed, Painting upto 22 Floor Completed, Finishing upto 3 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 4 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 26 Floor Completed, Painting upto 22 Floor Completed, Finishing upto 3 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 87.83% |  | 94.33% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 35 | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 30 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 26 | 86.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 22 | 73.33% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 10% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Wing C (as per sale plan) = Building No.3 (as per sanctioned plan) = G + 1st to 4th Podium Floor + 1st to 30th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 28 Slab Completed, Brickwork upto 23 Floor Completed, Internal Plaster upto 17.25 Floor Completed, External Plaster upto 16.1 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 4 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 28 Slab Completed, Brickwork upto 23 Floor Completed, Internal Plaster upto 17.25 Floor Completed, External Plaster upto 16.1 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 57.43% |  | 78.39% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 28 | 80% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 23 | 76.67% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 17.25 | 57.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.1 | 53.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 12600 |  |  | 8800/- to 11000/- Costsheet 19/05/2022 - By Akash Sir.
Recommended rate of the Shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 19000
Floor Rise Rate Per Sq.ft |  |  |  |  | 50/­ from 1st Floor |  |  |  | 11000 12600 | sanket 27/04/2023 | same rate as Dosti Nest
Other Charges |  |  |  |  | 215000
MSEDCL |  |  |  |  | 60000
Water Charges |  |  |  |  | 30000
Society Formation Charges |  |  |  |  | 5000
Corpus Fund - For Club House |  |  |  |  | 25000
Clubhouse Membership |  |  |  |  | 225000
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 10080
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 ( A wing) |  | 13 |  | 4107.1118 |  | 6571.3789
Building No.2 ( A wing) |  | 13 |  | 4065.4552 |  | 6504.7283
Total |  | 26 |  | 8172.567 |  | 13076.1072
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1( A wing) Sale |  | 181 |  | 135485.4992 |  | 216776.7988
Building No.2 ( A wing) |  | 230 |  | 163052.3185 |  | 260883.7096
Building No.3 |  | 106 |  | 75612.2562 |  | 120979.6099
Total Sale Flats |  | 517 |  | 374150.074 |  | 598640.1183
Building No.1( A wing) Mhada Flats |  | 49 |  | 24135.4714 |  | 38616.7542
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop (Mhada Or Sale) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A (as per sale plan) = Building No.1-Wing A (as per sanctioned plan)
Ground Floor for Commercial & Parking
1 | Sale | Shop | 346.4932 | 0 | 554.3891 | Ground Floor for Commercial & Parking
2 | Sale | Shop | 212.2661 | 0 | 339.6257 | Ground Floor for Commercial & Parking
3 | Sale | Shop | 309.8956 | 0 | 495.8329 | Ground Floor for Commercial & Parking
4 | Sale | Shop | 321.9512 | 0 | 515.122 | Ground Floor for Commercial & Parking
5 | Sale | Shop | 422.9176 | 0 | 676.6681 | Ground Floor for Commercial & Parking
6 | Sale | Shop | 325.611 | 0 | 520.9776 | Ground Floor for Commercial & Parking
7 | Sale | Shop | 366.2989 | 0 | 586.0783 | Ground Floor for Commercial & Parking
8 | Sale | Shop | 267.8083 | 0 | 428.4933 | Ground Floor for Commercial & Parking
9 | Sale | Shop | 309.8956 | 0 | 495.8329 | Ground Floor for Commercial & Parking
10 | Sale | Shop | 212.2661 | 0 | 339.6257 | Ground Floor for Commercial & Parking
11 | Sale | Shop | 346.4932 | 0 | 554.3891 | Ground Floor for Commercial & Parking
12 | Sale | Shop | 332.6076 | 0 | 532.1722 | Ground Floor for Commercial & Parking
13 | Sale | Shop | 332.6076 | 0 | 532.1722 | Ground Floor for Commercial & Parking
Wing B (as per sale plan) = Building No.2 -Wing A (as per sanctioned plan)
Ground Floor for Commercial & Parking
1 | Sale | Shop | 332.6076 | 0 | 532.1722 | Ground Floor for Commercial & Parking
2 | Sale | Shop | 332.6076 | 0 | 532.1722 | Ground Floor for Commercial & Parking
3 | Sale | Shop | 346.4932 | 0 | 554.3891 | Ground Floor for Commercial & Parking
4 | Sale | Shop | 212.2661 | 0 | 339.6257 | Ground Floor for Commercial & Parking
5 | Sale | Shop | 309.8956 | 0 | 495.8329 | Ground Floor for Commercial & Parking
6 | Sale | Shop | 267.8083 | 0 | 428.4933 | Ground Floor for Commercial & Parking
7 | Sale | Shop | 355.8578 | 0 | 569.3725 | Ground Floor for Commercial & Parking
8 | Sale | Shop | 306.6664 | 0 | 490.6662 | Ground Floor for Commercial & Parking
9 | Sale | Shop | 410.6466 | 0 | 657.0346 | Ground Floor for Commercial & Parking
10 | Sale | Shop | 321.9512 | 0 | 515.122 | Ground Floor for Commercial & Parking
11 | Sale | Shop | 309.8956 | 0 | 495.8329 | Ground Floor for Commercial & Parking
12 | Sale | Shop | 212.2661 | 0 | 339.6257 | Ground Floor for Commercial & Parking
13 | Sale | Shop | 346.4932 | 0 | 554.3891 | Ground Floor for Commercial & Parking
Flat No. (Approved Plan) | Flat (Sale Or Mhada) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A (as per sale plan) = Building No.1-Wing A (as per sanctioned plan)
Ground Floor For Parking
1st to 3rd Podium Floor For Parking
4th Podium Floor For Parking & Residential
1 | - | Parking Area |  |  |  | 4th Podium Floor For Parking & Residential
2 | -
3 | -
4 | -
5 | Sale | 2BHK | 752.7265 | 0 | 1204.3624
6 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
7 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
1st Floor
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 1st Floor
2 | Mhada | 1.5BHK | 492.5606 | 0 | 788.097
3 | Mhada | 1.5BHK | 492.5606 | 0 | 788.097
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 2BHK | 752.7265 | 0 | 1204.3624
6 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
7 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
2 | - | Refuge Area
3 | Mhada | 1.5BHK | 492.5606 | 0 | 788.097
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
7 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th Floor
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th Floor
2 | Mhada | 1.5BHK | 492.5606 | 0 | 788.097
3 | Mhada | 1.5BHK | 492.5606 | 0 | 788.097
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
7 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
28th Floor
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 28th Floor
2 | Mhada | 1.5BHK | 492.5606 | 0 | 788.097
3 | Sale | 1.5BHK | 492.5606 | 0 | 788.097
4 | Sale | 2BHK | 923.7665 | 0 | 1478.0264
5 | Sale | 3BHK | 752.7265 | 0 | 1204.3624
6 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
7 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
29th Floor
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 29th Floor
2 | Sale | 1.5BHK | 492.5606 | 0 | 788.097
3 | Sale | 1.5BHK | 492.5606 | 0 | 788.097
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
7 | Sale | 2BHK | 674.5799 | 0 | 1079.3278
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
Wing B (as per sale plan) = Building No.2 -Wing A (as per sanctioned plan)
Ground Floor For Parking
1st to 3rd Podium Floor For Parking
4th Podium Floor For Parking & Residential
1 | - | Parking Area |  |  |  | 4th Podium Floor For Parking & Residential
2 | -
3 | -
4 | -
5 | Sale | 2BHK | 752.7265 | 0 | 1204.3624
6 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
7 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
8 | Sale | 2BHK | 752.7265 | 0 | 1204.3624
1st Floor
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 1st Floor
2 | Sale | 1.5BHK | 580.6102 | 0 | 928.9763
3 | Sale | 1.5BHK | 580.6102 | 0 | 928.9763
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
7 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
8 | Sale | 2BHK | 752.7265 | 0 | 1204.3624
2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
2 | - | Refuge Area
3 | Sale | 1.5BHK | 580.6102 | 0 | 928.9763
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
7 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th & 29th Floor
1 | Sale | 2BHK | 661.3402 | 0 | 1058.1443 | 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th & 29th Floor
2 | Sale | 1.5BHK | 580.6102 | 0 | 928.9763
3 | Sale | 1.5BHK | 580.6102 | 0 | 928.9763
4 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
7 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
8 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
Wing C (as per sale plan) = Building No.3 (as per sanctioned plan)
Ground Floor For Parking
1st to 3rd Podium Floor For Parking
4th Podium Floor For Parking & Residential
1 | Sale | 2BHK | 674.0417 | 0 | 1078.4667 | 4th Podium Floor For Parking & Residential
2 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
3 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
4 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
5 | Sale | 2BHK | 752.7265 | 0 | 1204.3624
1st, 3rd to 6th, 8th to 11th & 13th Floor
1 | Sale | 2BHK | 674.0417 | 0 | 1078.4667 | 1st, 3rd to 6th, 8th to 11th & 13th Floor
2 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
3 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
4 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | Sale | 1.5BHK | 582.9782 | 0 | 932.7652
7 | Sale | 1.5BHK | 582.9782 | 0 | 932.7652
8 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
2nd, 7th & 12th Floor (Part Refuge Area)
1 | Sale | 2BHK | 674.0417 | 0 | 1078.4667 | 2nd, 7th & 12th Floor (Part Refuge Area)
2 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
3 | Sale | 2BHK | 659.8332 | 0 | 1055.7331
4 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
5 | Sale | 3BHK | 923.7665 | 0 | 1478.0264
6 | - | Refuge Area
7 | Sale | 1.5BHK | 582.9782 | 0 | 932.7652
8 | Sale | 2BHK | 661.3402 | 0 | 1058.1443
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Utility Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr.Sandip - 7208964023.
* | We have updated CC from RERA site on 14/01/2023.
* | Construction work goes beyond approved no. of floor. Please Provide revised approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Dosti West County Sector 2 - Dosti Tulip
Google Map :
Formulas:
Balkum = [Balkum, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted