## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | M/s. Fortune Infracreators Private Limited
Name of the builder company |  |  |  | M/s. Fortune Infracreators Private Limited
Name of the Project |  |  |  | Superio Grand Central
Contact Details ( Name & Contect No.) |  |  |  | 9820108795
Name / No of the Building |  |  |  | 1 Building (Existing Building No.24 & 31)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700025980
Project location details |  | Superio Grand Central is Revelopment of Vrtak Nagar Vikas CHS (Building No. 24) & Vartak Nagar Janakdevi CHS (Building No.31) part of housing layout of Vartak Nagar S.no.206/3(pt) to 7(pt), 209/5(pt), 7(pt) & 10(pt) at village-Majiwada, Thane.
Survey No |  | 206 Hissa no.5, 6, 7(Part) & 209 Hissa no.5
Road |  | Pokhran Road No.1 |  | Locality/Village |  | Vartak Nagar
City |  | Thane |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400606
Near by Landmark |  | Savtribai Thirane school |  | Distance from city centre: |  | 5Km from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open plot
West | NA | NA |  |  | Open plot
North | NA | NA |  |  | Sangram CHS
South | NA | NA |  |  | Savitribai Thirane School
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.21447735, 72.96100027
Location Link |  | https://goo.gl/maps/sRveZG46qZLsNQjb7?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1902.35
Permissible FSI |  |  |  | 2
Permissible TDR/Paid FSI |  |  |  | 2.3938
Total FSI availaible for the project |  |  |  | 4.3938
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8358.56
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | VPS04/0145/18/TMC/TD-DP/ TPS/3051/19 |  |  | Dated | 16/04/2019.
Approved Floor plan No. |  | VPS04/0145/18/TMC/TD-DP/ TPS/3051/19 |  |  | Dated | 16/04/2019.
Commencement Certificate No. |  | V.P.NO.S04/0145/18/TMC/TDD/4139/22 |  |  | Dated | 19/07/2022.
Valid Up to: 1B + Gr (Part Comm. + Common facilities, meter room, common toilet, electrical services) + 1st Floor (Part Commercial) + 2nd to 30th floor + 31st floor (Part Fitness Centre)
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8358.56
Approved no of units |  |  | Flats - 192, Shops - 18
Approved no of Floors |  |  | Gr + 1st Floor + 2nd to 10th (P) + 11th to 30th Floor
Proposed no of Floors |  |  | 1B + Gr + 1st Floor + 2nd to 10th (P) + 11th to 32nd Floor
Expected Completion |  |  | As per RERA - 01/03/2030.
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Gr + 1st Floor + 2nd to 10th (Po) + 11th to 31st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 27 Floor, External Plaster upto 27 Floor, Flooring upto 9 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 31
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 27 Floor, External Plaster upto 27 Floor, Flooring upto 9 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.75
Excavation |  | 31 | 100% | 75.65% |  | 90.16% |  | Excavation in process | 15.5
Plinth |  | 31 | 100% |  |  |  |  | Excavation Completed | 31
RCC (Including podiums) |  | 32 | 100% |  |  |  |  | Footing in Process | 7.75
Brickwork | Brickwork & Internal Plaster | 31 | 100% |  |  |  |  | Footing Completed | 15.5
Internal Plaster | Brickwork & Internal Plaster | 27 | 87.1% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 27 | 87.1% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 29.03% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 23.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 31
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 13000
Recommended rate of the shop at Ground Foor Per Sq. Ft. (on Saleable area) |  |  |  |  | 25000
Recommended rate of the Shop at 1st Floor Per Sq. Ft. (on Saleable area) |  |  |  |  | 22000
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 500000/-
Distressed valuation of the Property |  |  |  |  | 10400
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shop |  | 18 | 6093.6995 |  | 9749.9193
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Flat |  | 192 | 77213.8963 |  | 115820.8445
Total |  | 210 | 83307.5959 |  | 125570.7638
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Ground Floor for Commercial (Part area for 12 Rehab Shops)
Sale | 1 | Shop | 428.7839 | 0 | 686.0543 | Ground Floor
Sale | 2 | Shop | 716.398 | 0 | 1146.2368
Sale | 3 | Shop | 313.7168 | 0 | 501.9468
Sale | 4 | Shop | 379.2695 | 0 | 606.8313
Sale | 5 | Shop | 407.3636 | 0 | 651.7817
Sale | 6 | Shop | 146.7133 | 0 | 234.7413 |  |  |  | 55380.1114
Sale | 7 | Shop | 394.6082 | 0 | 631.3732
Sale | 8 | Shop | 718.2548 | 0 | 1149.2077
Sale | 9 | Shop | 484.676 | 0 | 775.4816
Sale | 10 | Shop | 537.2312 | 0 | 859.57
1st Floor
Sale | 11 | Shop | 136.7781 | 0 | 218.845 | 1st Floor |  |  | 59402.7637
Sale | 12 | Shop | 246.4095 | 0 | 394.2552
Sale | 13 | Shop | 167.0573 | 0 | 267.2916
Sale | 14 | Shop | 195.7702 | 0 | 313.2324
Sale | 15 | Shop | 195.7702 | 0 | 313.2324
Sale | 16 | Shop | 195.7702 | 0 | 313.2324
Sale | 17 | Shop | 174.8881 | 0 | 279.8209
Sale | 18 | Shop | 254.2403 | 0 | 406.7845
2nd to 10th Floor for Podium Parking
11th & 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor for Residential
1 |  | 1BHK | 392.2778 | 0 | 588.4168 | 11th & 12th, 14th to 17th, 19th to 22nd, 14th to 27th, 29th & 30th Floor |  | 12576.1206
2 |  | 2BHK | 467.5968 | 0 | 701.3952 |  |  | 13829.5794
3 |  | 1BHK | 334.7712 | 0 | 502.1567 |  |  | 14736.4345
4 |  | 1BHK | 334.7712 | 0 | 502.1567 |  |  | 14736.4345
5 |  | 2BHK | 467.5968 | 0 | 701.3952
6 |  | 1BHK | 392.2778 | 0 | 588.4168 |  |  | 12576.1206
7 |  | 2BHK | 468.1726 | 0 | 702.259
8 |  | 1BHK | 334.7712 | 0 | 502.1567 |  |  | 14736.4345
9 |  | 1BHK | 334.7712 | 0 | 502.1567 |  |  | 14736.4345
10 |  | 2BHK | 467.5968 | 0 | 701.3952
Fire Check Floor Between 23rd & 24th Floor
13th, 18th, 23rd & 28th (Part Refuge Floor)
1 |  | 1BHK | 392.2778 | 0 | 588.4168 | 13th, 18th, 23rd & 28th (Part Refuge Floor)
2 |  | 2BHK | 467.5968 | 0 | 701.3952
3 |  | 1BHK | 334.7712 | 0 | 502.1567
4 |  | 1BHK | 334.7712 | 0 | 502.1567
5 |  | 2BHK | 467.5968 | 0 | 701.3952
6 |  | 1BHK | 392.2778 | 0 | 588.4168
7 |  | 2BHK | 468.1726 | 0 | 702.259
8 |  | Refuge Area
9
10 |  | 2BHK | 467.5968 | 0 | 701.3952
Remarks:
1. Construction work was in process at the time of visit. Internal photographs was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 8. On Site, we meet Mr. Vikrant : 9920695454. 9. We have updated latest CC from Rera (On 14/10/2024). 10. Construction Work Goes beyond approved no. of floor. Please provide revised approved plans.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Superio Grand Central
Google Map :

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted